## RioGen
Thermal Power Plant Permit Matrix
Project | RioGen
Last Update | 2026-07-29 | LNTP = Limited Notice to Proceed
NTP = Notice To Proceed
SPR = Site Preparation Release
COD = Commerical Operation Date
|  | Description of Permit | Condition Precedent | Issuing Authority | Request filed on | Party Responsible | Status
1. State Environmental Licenses
|  | A. Previous License (LP) | LNTP | FEEMA |  | ESA
|  | Application for LP | LNTP | FEEMA | December 1999 | ESA | December 1999
|  | Approval of Environmental Impact Assessment (EIA-RIMA) | LNTP | FEEMA |  | ESA | September 2000
|  | Public Hearing | LNTP | CECA |  | ESA | October 18 2000
|  | Issuance of Previous License (LP) | LNTP | FEEMA |  | ESA | December 6 2000
|  | B. Installation License (LI) | NTP | FEEMA |  | ESA
|  | Basic Environmental Plan (PBA) Approval | NTP | FEEMA |  | ESA | December 21 2000
|  | Issuance of Installation License (LI) | NTP | FEEMA |  | ESA | December 21 2000
|  | C. Operation License (LO) | COD | FEEMA |  | ESA
|  | Application for LO | COD | FEEMA |  | ESA | August 2002
|  | Issuance of Operation License (LO) | COD | FEEMA |  | ESA | September 2002
2. Regulatory Licenses
|  | A. Approval of Feasibility Study | LNTP | ANEEL |  | ESA | February 2000
|  | B. Issuance of Independent Power Producer (IPP) License | NTP | ANEEL |  | ESA | June 6 2000
|  | C. Issuance of Construction Permit | NTP | ANEEL |  | ESA | June 6 2000
|  | D. Approval of Basic Engineering Project | LNTP | ANEEL |  | ESA | January 5 2001
|  | E. Transfer of Ownership of the Controlling Block of Shares | NTP | ANEEL |  | ESA | January 2001
|  | F. Insertion in the Priority Program | LNTP | MME |  | ESA | February 2000
|  | G. Project Design Registration | SPR | CREA |  | ESA | December 2000
|  | H. Project Construction Registration | SPR | CREA |  | ESA | December 2000
|  | I. Wholesale Power Market Registration | COD | MAE |  | ESA | June 2002
3. Grid Connection
|  | A. Completion of Electrical Studies | LNTP | CEPEL |  | ESA | December 12 2000
|  | B. Issuance of Authorization | LNTP | ONS |  | ESA | December 20 2000
|  | C. Approval of Connection to Transmission (CCT) | NTP | Furnas |  | ESA | March 2001
|  | D. Approval of Connection to Transmission System (CUST) | NTP | ONS |  | ESA | March 2001
4. Administrative Licenses
|  | A. Construction Approval from Seropédica Prefecture | NTP | Seropédica Prefecture |  | EE&CC/NEPCO | December 2000
|  | B. Fire Department Approval | COD | State Fire Department |  | EE&CC/NEPCO | August 2002
|  | C. Construction of Access Road | LNTP | DNER |  | ESA | November 10 2000
|  | D. Construction of Access Road | LNTP | Nova Dutra |  | ESA | November 10 2000
|  | E. Municipal Health and Welfare Secretarial (SUDS) Approval | COD | Municipal Health Department |  | EE&CC/NEPCO | August 2002
|  | F. Zoning | LNTP | Seropédica Prefecture |  | ESA | April 2000
|  | G. Good Standing Tax Certificate | NTP | Seropédica Prefecture |  | ESA | December 2000
|  | H. Land Title (after split) | NTP | Land Title Registry |  | ESA | December 2000
|  | I. Project Completion Certificate (HABITE-SE) | COD | Seropédica Prefecture |  | EE&CC/NEPCO | August 2002
|  | J. Stack Heights and Lighting | NTP | COMAR |  | ESA | December 2001
|  | K. Approval of ICMS Deferral | NTP | State Government |  | ESA | March 2001
|  | L. Approval of Import under Grupo Eletrogêneo Regime | NTP | Secretaria de Receita Federal (SRF) |  | ESA | June 2001
|  | M. Construction Power | LNTP | Light |  | ESA | December 2000
|  | N. Heavy Load Transportation | NTP | Nova Dutra |  | EE&CC/NEPCO | June 2001
|  | O. Heavy Load Transportation | NTP | DNER |  | EE&CC/NEPCO | June 2001
|  | P. Transmission Line ROW (700 meters) | NTP | Landowner |  | ESA | January 2001
|  | Q. Contruction of Water Intake/Discharge Structure | NTP | IEF (IBAMA) |  | ESA | January 2001
|  | R. Provisional Access Road | LNTP | Nova Dutra |  | ESA | December 2000
|  | S. Provisional Access Road | LNTP | DNER |  | ESA | December 2000
|  | T. Use of Radio Frequency | NTP | ANATEL |  | ESA | April 2001
|  | U. Use of Radio Frequency | NTP | FISTEL |  | ESA | April 2001
|  | V. Land Fill / Waste Truck Traffic | LNTP | Nova Dutra |  | ESA | December 2000
5. Water Licenses
|  | A. Water Quantity | NTP | SERLA |  | ESA | December 2000
|  | B. Water Intake/Discharge Structures | NTP | SERLA |  | ESA | December 2000
|  | C. Water Well | NTP | SERLA |  | ESA | March 2000
|  | D. Construction Water | LNTP | SERLA |  | ESA | December 2000
|  | E. Placement of Barge in the Guandu River to Install Structures | NTP | SERLA |  | ESA | December 2000

## RioGen Merchant
Thermal Power Plant Permit Matrix
Project | RioGen Merchant
Last Update | 2026-07-29 | LNTP = Limited Notice to Proceed
NTP = Notice To Proceed
SPR = Site Preparation Release
COD = Commerical Operation Date
|  | Description of Permit | Condition Precedent | Issuing Authority | Request filed on | Party Responsible | Status
1. State Environmental Licenses
|  | A. Previous License (LP) | LNTP | FEEMA |  | ESA
|  | Application for LP | LNTP | FEEMA | August 4 2000 | ESA | August 4 2000
|  | Approval of Environmental Impact Assessment (EIA-RIMA) | LNTP | FEEMA |  | ESA | December 21 2000
|  | Public Hearing | LNTP | CECA |  | ESA | January 26 2001
|  | Issuance of Previous License (LP) | LNTP | FEEMA |  | ESA | February 20 2001
|  | B. Installation License (LI) | NTP | FEEMA |  | ESA
|  | Basic Environmental Plan (PBA) Approval | NTP | FEEMA |  | ESA | March 25 2001
|  | Issuance of Installation License (LI) | NTP | FEEMA |  | ESA | March 25 2001
|  | C. Operation License (LO) | COD | FEEMA |  | ESA
|  | Application for LO | COD | FEEMA |  | ESA | August 2001
|  | Issuance of Operation License (LO) | COD | FEEMA |  | ESA | September 2001
2. Regulatory Licenses
|  | A. Approval of Feasibility Study | LNTP | ANEEL | July 19 2000 | ESA | August 2000
|  | B. Issuance of Independent Power Producer (IPP) License | NTP | ANEEL | September 13 2000 | ESA | November 2000
|  | C. Issuance of Construction Permit | NTP | ANEEL | September 13 2000 | ESA | November 2000
|  | D. Approval of Basic Engineering Project | LNTP | ANEEL |  | ESA | January 30 2001
|  | E. Transfer of Ownership of the Controlling Block of Shares | NTP | ANEEL |  | ESA | January 2001
|  | F. Insertion in the Priority Program | LNTP | MME |  | ESA | August 2000
|  | G. Project Design Registration | SPR | CREA |  | ESA | February 11 2001
|  | H. Project Construction Registration | SPR | CREA |  | ESA | February 11 2001
|  | H. Wholesale Power Market Registration | COD | MAE |  | ESA | June 2001
3. Grid Connection
|  | A. Completion of Electrical Studies | LNTP | CEPEL | August 15 2000 | ESA | November 30 2000
|  | B. Issuance of Authorization to Connect to Grid | LNTP | Light / ONS | September 6 2000 | ESA | January 10 2001
|  | C. Approval of Connection to Transmission (CCD) | NTP | Light | September 6 2000 | ESA | December 2000
|  | D. Approval of Connection to Distribution System (CUSD) | NTP | Light | September 6 2000 | ESA | December 2000
|  | E. Approval of Connection to Transmission System (CUST) | NTP | ONS | October 10 2000 | ESA | December 2000
4. Administrative Licenses
|  | A. Construction Approval from Seropédica Prefecture | NTP | Seropédica Prefecture |  | EE&CC/NEPCO | December 2000
|  | B. Fire Department Approval | COD | State Fire Department |  | EE&CC/NEPCO | July 2001
|  | C. Municipal Health and Welfare Secretarial (SUDS) Approval | COD | Municipal Health Department |  | EE&CC/NEPCO | July 2001
|  | D. Good Standing Tax Certificate | NTP | Seropédica Prefecture |  | ESA | December 2000
|  | E. Land Title (legal description of site, including boundaries description or similar description of site, as is customary in Brazilian land descriptions) | NTP | Land Title Registry |  | ESA | December 2000
|  | F. Project Completion Certificate (HABITE-SE) | COD | Seropédica Prefecture |  | EE&CC/NEPCO | July 2001
|  | G. Stack Heights and Lighting | NTP | COMAR |  | ESA | April 2001
|  | H. Approval of ICMS Deferral | NTP | State Government |  | ESA | April 2001
|  | I. Approval of Import under Grupo Eletrogêneo Regime | NTP | Secretaria de Receita Federal (SRF) |  | ESA | March 2001
|  | J. Heavy Load Transportation | NTP | Nova Dutra |  | EE&CC/NEPCO | January 2001
|  | K. Heavy Load Transportation | NTP | DNER |  | EE&CC/NEPCO | January 2001
5. Water Licenses
|  | A. Water Quantity | NTP | SERLA | August 3 2000 | ESA | April 2001
|  | B. Construction Water | LNTP | SERLA |  | ESA | December 2000