## EOL New Countries
|  | ENRONONLINE WORLDWIDE PRESENCE |  |  |  |  | as of: | 2026-07-29
Notes:
THE AMERICAS
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 | Canada |  | 1 | Argentina | Enron Argentina | M. Taylor | 2000-10-01 | 08/15 Draft of legal Documents later this week. 8/31 Draft has not been forthcoming. 09/07 Pending!
2 | United States |  | 2 | Bermuda |  | M. Taylor | to be determined | 08/15 No date yet. Mark Taylor is checking and will get back to us. 8/31 M. Taylor will get ETA. Brent is working on.
3 | Mexico |  | 3 | Brazil | Enron Brazil | M. Taylor | to be determined | 08/15 No date yet. 8/31 No update.
|  |  | 4 | Chile | MG | M. Taylor | 2000-09-01 | 08/15 More info Wed. 8/31 May need an agent for service of process in the U.S. (Brent is checking)
|  |  | 5 | Colombia | Enron Coal / MG | M. Taylor | 2000-09-01 | 08/15 Mark Taylor is restarting process. 8/31 M. Taylor to obtain ETA. Brent working on.
|  |  | 6 | Peru | MG | M. Taylor | 2000-09-01 | 08/15 More info Wed. 8/31 May need an agent for service of process in the U.S. (Brent is checking)
AFRICA
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 |  |  | 1 | South Africa | Enron Coal | Edmund | to be determined | 08/15 No date yet. 8/22 Issue: South Africans can not make payments to non-residents without approval of Reserve Bank. Reserve Bank gives no approvals to South Africans in respect of commodity or derivative transactions with foreign counterparties.
ASIA / AUSTRALIA
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 | Australia |  | 1 | China | MG | Edmund | to be determined | 8/22 Commodity derivatives trading within China is not promoted unless it takes place on a domestic futures exchange.
2 | Japan |  | 2 | Hong Kong | MG | Edmund | to be determined | 8/15 Initial and follow up advice received. Further clarification still needed.
3 | Singapore |  | 3 | Israel | Seafreight | Edmund | to be determined | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 Advise outstanding: due at end of August.
|  |  | 4 | South Korea | ? | ? | to be determined | 8/15 Need to confirm status. 8/31 Matt Lee will update.
EUROPE
# | Available at: |  |  | In the works: | Business Unit | Responsibility | Scheduled for: | Comments:
1 | Austria |  | 1 | Greece | Seafreight | Edmund | 2000-09-01 | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 There are significant restrictions on trading in gas and power. In addition, only companies possessing a license issued by the Ministry of Development can trade oil. No License needed only permission from Capital Mkt.. Committee.
2 | Belgium |  | 2 | Russia | MG | Edmund | to be determined | 8/15 Initial and follow up advice received. Further clarification still needed. 8/22 Issues; A) Risk of non-deliverable transactions not unforeseeable. B) Payments in foreign currency might require case-by-case consent from Central Bank. C) Every trade with a Russian counterparty needs to be documented in writing.
3 | Croatia |  | 3 | Turkey | Seafreight | Edmund | 2000-09-01 | 8/15 Initial outside legal responses received. 8/22 For enforceability a hard copy of an umbrella agreement should be signed. Follow up advice awaited!!!
4 | Czech Republic
5 | Denmark
6 | Finland
7 | France
8 | Germany
9 | Ireland
10 | Italy
11 | Netherlands
12 | Norway
13 | Poland
14 | Portugal
10 | Romania
16 | Slovenia
17 | Spain
18 | Sweden
19 | Switzerland
20 | United Kingdom

## EOL New Products
|  | ENRONONLINE NEW PRODUCTS STATUS |  |  |  | as of: | 2026-07-29
Note: Due to the Launch of Phase II all new products types and auctions development has been postponed.
TRANSACTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Responsibility | Status as of 9/07/00 | Status as of 9/14/00 | Scheduled for | Comments
1 | Advertising Blocks (Nielsen Ratings) | Advertisement Market | US | EBS | Dale Neuner | Pending | Pending | TBD | 08/23 EBS is reviewing legal issues. 09/07 Met with S. Barth (EBS) to discuss. They will work on defining the products and then get back to us.
2 | AUS and JPN Weather | Weather Options | US | Weather | Dale Neuner | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II . 8/29 To be launched this week. 09/07 Launched yesterday.
3 | Brent | Brent/Dubai Spread | London | Crudes | Anna / Arfan | Draft | Draft | TBD | 08/23 On hold due to Phase II
4 | Coal | Physical Options | London | Coal | Imelda / Lara | Draft | Draft | 2000-09-01 | 09/08 Reviewing.
5 | Gas | PHY Fwd | Argentina | Enron Argentina | Dale Neuner | In Test | In Test | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit
6 | Gas | Fin Options | US | Gas | Dale Neuner | Pending | Pending | TBD | 08/23 On hold due to Phase II
7 | Gas | Fin Spread | US | Gas | Dale Neuner | Draft | Draft | TBD | 08/23 Product for internal use only to hedge between Nymex and HeHub. 9/14 products will bridge similar to other basis products
8 | Gas | Transportation | US | EPG | Savita Puthigai | Draft | Draft | 2000-10-01 | 08/23 Working on descriptions and GTC. 8/31 Product Descriptions and Legal being reviewed. "Chinese Wall" type concerns being reviewed by Legal. 9/07 Reviewing issues related to GPG and ENA information (comply with regulation) 9/14 need to segregate marketing affiliates using Chinese Walls- Preparing list of Proprietary system issues; may include HPL products
9 | Gasoil | Daily Average x2 | London | Global Liquids | Arfan / Anna | Reviewing | Reviewing | TBD | 09/08 Reviewing language.
10 | Gasoil | SG East-West Fuel Oil Swap Diff. | London | Global Liquids | Marie / Anna | Reviewing | Reviewing | 2000-10-01 | 09/08 Reviewing language.
11 | Gasoil | SG East-West Swap Differential | London | Global Liquids | Marie / Anna | Reviewing | Reviewing | 2000-10-01 | 09/08 Reviewing language.
12 | Isobutane | Fin Swap | US | Petchems | Dale Neuner | Draft | Draft | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval
13 | Isobutane | Phy FOB | US | Petchems | Dale Neuner | Draft | Draft | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval
14 | E/P Mix | Phy FOB | US | Petchems | Dale Neuner | N/A | Draft | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval
15 | E/P Mix | Fin Swap | US | Petchems | Dale Neuner | N/A | Draft | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval
16 | Isobutane | Phy Index | US | Petchems | Dale Neuner | Draft | Cancelled | N/A | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 cancelled
17 | Marine Bunkers | Marine Bunkers | London | Oil | Caroline/ Anna | Draft | Draft | 2000-09-01 | 08/23 On hold due to Phase II 09/07 On hold.
18 | Metals | Fin x3 (lead etc) | London | MG | Lara/Imelda | Draft | Draft | TBD | 09/08 On Draft.
19 | Metals | Phys x5 Copper | London | MG | Diana | Draft | Draft | TBD | 09/08 On Draft.
20 | Metals | LME x4 | London | MG | Lara/Arfan | Draft | Draft | 2000-09-01 | 08/23 On hold due to Phase II 09/07 On Draft.
21 | Metals | Metals LME x5 | London | MG | Lara/Arfan | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II 09/07 Done!
22 | Nat-Gasoline | Phy Index | US | Petchems | Dale Neuner | Draft | Draft | TBD | 08/31 Working on initial draft.
23 | Paper | Phy Paper OCC Ex-works | US | Pulp and Paper | Dale Neuner | Reviewing | Reviewing | TBD | 08/23 Desk is working on logistics and legal issues.
24 | Power | FIN Swap | Argentina | Enron Argentina | Dale Neuner | In Test | In Test | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit
25 | Power | PHY Fwd | Argentina | Enron Argentina | Dale Neuner | In Test | In Test | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit
26 | Power | German Power Options | Germany | Power | Anna / Imelda | Draft | Draft | TBD | 08/23 On hold due to Phase II . Legal reviewing.
27 | Power | East Cinergy Peak Splits | US | Power | Dale Neuner | Test | Active | 2000-09-01 | 09/07 Testing products. 9/14 Done
28 | Propane | Phy Index Purity | US | Petchems | Dale Neuner | Draft | Draft | TBD | 08/31 Working on initial draft. 09/06 Draft in progress.
29 | Sea Freight | Physical | London | Oil | Anna/Amita | Draft | Draft | 2000-09-01 | 09/08 On hold due to Phase II. Legal reviewing.
30 | Singapore FX | Singapore FX | London | FX desk | Anna | On hold | On hold | TBD | 08/23 On hold by request of commercial group
31 | Tanker Freight | Tanker Freight | London | Oil | Caroline/ Anna | Draft | Draft | 2000-09-01 | 09/08 On hold due to Phase II. Legal reviewing.
AUCTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Responsibility | Status as of 9/07/00 | Status as of 9/14/00 | Scheduled for | Comments
1 | Coal | Coal Auction | US | Coal | John Massey | Text in Draft | Text in Draft | TBD | 8/21 Coal group working on text draft
2 | Gas | Transportation Cap. | US | FGT | Steve Hotte | Text in Draft | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II.
3 | Gas | Transportation Cap. | US | NGPL | Steve Hotte | Text in Draft | Text in Draft | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II.
4 | Power | Capacity Generation | US | Power Desk | David Portz | Text in Draft | Text in Draft | TBD | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II.
5
6
7
8
9
10