## Matrix
LV Cogeneration II L.L.C.
PROJECT CONTROL MATRIX - DATA ROOM INDEX
2000-09-14
DOCUMENT INCLUDED IN TRANSMITTAL
FILE | DOCUMENT REQUIRED FOR CLOSING | ACTUAL
NO. | FINAL DOCUMENT AVAILABLE
DOCUMENTATION SUBSTANTIALLY COMPLETE
1 | HOST & SITE DEVELOPMENT
1.1.2 | LEGAL DESCRIPTION
1.1.6 | CITY OF NORTH LAS VEGAS ZONING MAP | 2000-06-01
1.2.8.1 | LETTER TO JORDAN RE RELOCATION OF BRUCE STREET, LANDSCAPING | 2000-07-11
1.3.1 | GEOTECH REPORT - RTP ENVIRONMENTAL DUE DILIGENCE REPORT FOR LVCLP | 1999-06-01
1.3.1.1 | LOCATION OF SUBSURFACE LOCATIONS FOR LVCLP | 1992-08-31
1.4 | ALTA SURVEY OF THE SITE
1.5.1 | OPTION TO LEASE AGREEMENT
1.5.2 | GROUND LEASE
1.5.3 | ASSESSOR'S PARCELS FOR CONSTRUCTION LAYDOWN | NO DATE
2 | PROJECT ECONOMICS
2.3.1 | TASKING LETTER REV 0 TRI-MONT, RTP | 1999-10-19
2.3.2 | TASKING LETTER REV 1 TRI-MONT | 2000-03-06
2.3.3 | TASKING LETTER REV 2 RTP | 2000-04-19
2.3.4 | TASKING LETTER REV 3 PGE | 2000-04-19
2.3.5 | TASKING LETTER REV 4 TRI-MONT | 2000-04-19
2.3.6 | TASKING LETTER REV 5 TRI-MONT | 2000-05-02
2.3.8 | TASKING LETTER REV 6 DDR | 2000-06-13
2.3.9 | TASKING LETTER REV 7 EE&CC | 2000-06-22
2.3.10 | TASKING LETTER REV 8 MFG
2.10.1 | TRI-MONT CONSULTING SERVICES AGREEMENT - EPC/DBS DOCUMENT | 2000-04-01
2.10.2 | VTN NEVADA - SURVEY COST PROPOSAL | 2000-04-13
2.10.3 | PROPERTY SPECIALISTS CONSULTING AGREEMENT | 2000-06-30
3 | SCHEDULES & ADMINISTRATIVE
4 | DEVELOPMENT OF BUSINESS STRUCTURE
4.2.1 | LOY CLARK PIPELINE | 2000-05-26
4.7 | FORMATION OF LVCII LLC | 2000-03-23
4.8.1 | CONFIDENTIALITY AGREEMENT - LOY CLARK PIPELINE | 2000-06-02
4.9 | BUSINESS LICENSE FOR LVCLP | 2000-08-10
5 | ENERGY PURCHASE AGREEMENTS
5.5.1.1 | LETTER AGREEMENT FOR INTERCONNECTION STUDY | 2000-06-28
5.5.1.2 | DATA REQUEST TO NEVADA POWER FOR GENERATOR INTERCONNECTION AND TRANSIENT DATA REQUIREMENTS | 2000-04-21
5.5.1.3 | NPC TRANSMISSION MASTER PLAN | 2000-06-07
5.5.1.4 | NPC DESIGN STANDARD FOR PARALLEL GENERATION 1 MVA OR LARGER | 2000-06-13
5.5.2 | LETTER TO NPC REQUESTING TRANSMISSION STUDY | 2000-03-02
5.5.4.1 | APPLICATION FOR LONG TERM FIRM TRANSMISSION SERVICE | 2000-08-14
6 | PERMITS
6.1.8 | APPLICATION FOR AUTHORITY TO CONSTRUCT CERTIFICATE | 2000-03-27
6.1.9.1 | APCD LETTER - MODIFICATION #3 NOTICE OF INCOMPLETE | 2000-04-18
6.1.9.1.1 | RESPONSE TO APCD LETTER (6.1.9.1) | 2000-05-05
6.1.9.2 | EPA LETTER RE SCONOX | 3/24/00 3/23/98
6.1.14 | NEVADA STATE LAW ON AIR PERMITTING - BUREAU OF AIR QUALITY | 2000-07-05
6.1.15 | DRAFT AUTHORITY TO CONSTRUCT #A-329 MODIFICATION #3
6.1.15.1 | TECHNICAL SUPPORT DOCUMENT FOR AUTHORITY TO CONSTRUCT #A-329 MOD #3
6.2.13 | LETTER TO CITY OF NORTH LAS VEGAS RE BRUCE STREET WALL AND CANAL | 2000-07-16
6.3.1 | UEPA PERMIT REQUIREMENTS LETTER FROM MCDONALD CARANO WILSON MCCUNE ET AL | 2000-08-30
6.4.2.2 | WATER QUALITY STANDARDS FOR SALINITY OF COLORADO RIVER SYSTEM | 2000-03-27
6.4.5 | DRAFT APPLICATION FOR DISCHARGE PERMIT MODIFICATION AND SALINITY CONTROL PLAN
6.4.6 | LETTER FROM CITY OF NORTH LAS VEGAS RE 3000 TDS WILL BE ACCEPTABLE AND CITY OF LAS VEGAS INDICATING DISCHARGE VOLUME IS ACCEPTABLE | 6/19/2000 6/16/00
6.4.6.1 | LETTER FROM CITY OF NORTH LAS VEGAS RE 3000 TDS WILL BE ACCEPTABLE AND CITY OF LAS VEGAS INDICATING DISCHARGE VOLUME IS ACCEPTABLE | 2000-07-15
6.4.6.2 | LETTER FROM CITY OF NORTH LAS VEGAS TO CITY OF LAS VEGAS RE TDS LEVELS | 2000-06-05
6.4.6.3 | LETTER FORM CITY OF NORTH LAS VEGAS INDICATING A FORMAL DISCHARGE PERMIT APPLICATION IS REQUIRED | 2000-08-08
6.5.2 | SUBMIT EXEMPTION LETTER CONFIRMING STORMWATER CONSTRUCTION PERMIT IS NOT REQUIRED | 2000-04-11
6.5.3 | LETTER FROM STATE OF NEVADA INDICATING STORMWATER PERMIT WILL NOT BE REQUIRED | 2000-06-08
6.7.2 | ACID RAIN APPLICATION (INCLUDES COVER LETTER TO EPA, CERTIFICATE OF REPRESENTATION, DRAFT PHASE II PERMIT APPLICATION) | 2000-08-18
6.10.1 | FAA FORM 7460-1 NOTICE OF PROPOSED CONSTRUCTION OR ALTERATION | 2000-06-30
6.10.2 | NOTICE THAT FAA RECEIVED NOTICE OF EXPANSION OF POWER PLANT | 2000-07-26
6.10.3 | FAA DETERMINATION OF NO HAZARD TO AIR NAVIGATION | 2000-08-09
7 | FUEL AND COMMODITIES CONTRACTS
7.3.1 | BYPASS GAS LINE COST ESTIMATE PREPARED BY TRI-MONT | 2000-04-14
7.3.2 | SOUTHWEST GAS LETTER RE SYSTEM PLANNING STUDY | 2000-04-10
7.3.3 | SOUTHWEST GAS PROPOSED CONTRACT RATE STRUCTURE | 2000-06-30
7.7.1 | SPECIFICATIONS OF LEAVITT WELL, MOTOR AND PUMP
7.7.1.1 | CITY OF NORTH LAS VEGAS LETTER RE TDS LEVELS, WATER AND WELL INFORMATION WITH ALTERNATE WATER SUPPLY LINE PLAN & PROFILE DRAWING | 2000-06-06
7.7.1.2 | CERTIFICATE OF ANALYSIS OF WATER SAMPLES TAKEN AT LVCLP | 2000-04-03
7.7.1.3 | WATER RATES - BILLINGS, DEPOSITS, REFUNDS FROM CITY OF NORTH LAS VEGAS | 1996-07-01
8 | OPERATIONS & MAINTENANCE
9 | EPC CONTRACT
9.1.1 | EPC DESIGN BASIS SCOPE/RFP | 2000-06-09
9.1.3.1.1 | DELTA HUDSON LETTER INDICATING THEY WILL NOT PROVIDE AN EPC PROPOSAL | 2000-07-06
9.1.3.1.2 | HARRIS GROUP LETTER INDICATING THEY WILL NOT PROVIDE AN EPC PROPOSAL | 2000-07-18
9.1.3.1.3 | POWER ENGINEERS LETTER INDICATING THEY WILL BID | 2000-06-30
9.1.4.1.3 | LAUREN ENGINEERS AND CONSTRUCTORS NOT TO EXCEED PRICE GUARANTEE | 2000-08-14
9.1.4.1.4 | LAUREN LETTER WITH ATTACHED MEMORANDUM OF UNDERSTANDING BETWEEN JOINT TEAM OF LAUREN AND SAULSBURY INDUSTRIES AND POWER ENGINEERS, DRAFT LIMITED NOTICE TO PROCEED AND HARTFORD FIRE INSURANCE LETTER TO PROVIDE BONDING | 2000-08-17
9.1.4.2 | LAUREN EXPERIENCE & QUALIFICATIONS | 2000-07-10
9.1.4.3 | INWEST GROUP LETTER INDICATING LAUREN AND SAULSBURY CAN PROVIDE PERFORMANCE AND PAYMENT BONDS THROUGH HARTFORD FIRE INSURANCE | 2000-08-16
9.1.5.1 | EPC ADDENDUM NO 1 | 2000-07-14
9.1.5.2 | EPC ADDENDUM NO 2 | 2000-07-27
9.1.7 | LIMITED NOTICE TO PROCEED PURSUANT TO RFP DATED 6/9/00 | 2000-09-07
10 | INSURANCE - CONSTRUCTION
11 | INSURANCE - OPERATIONS
12 | PROJECT PARTICIPANTS
13 | FINANCING ACTIVITIES
14 | TECHNICAL/OPERATIONAL REPORTS
14.1.1 | TRI-MONT FEASIBILITY STUDY & PROPOSED SITE PLAN FOR OPT 5 | 2000-03-24
14.1.2.1 | 75 DEGREE HEAT BALANCE3 AT 30 PPM NOX ENGINE EMISSIONS | 2000-08-31
14.1.2.2 | 75 DEGREE HEAT BALANCE AT 42 PPM NOX ENGINE EMISSIONS | 2000-08-31
14.1.8.6 | MONTHLY NET POWER OUTPUT AND FUEL CONSUMPTION ESTIMATES | 2000-06-21
14.1.17 | STEADY STATE ANALYSIS OF LAS VEGAS COGEN CAPACITY INCREASE | 1999-06-10
14.2.2 | TECH ENVIRONMENTAL PROPOSAL FOR NOISE STUDY | 2000-05-11
14.2.3 | ENVIRONMENTAL NOISE ANALYSIS BY MFG, INC | 2000-08-04
14.3 | EQUIPMENT LIST FOR LVCLP-UNITED ENGINEERS & CONSTRUCTORS | 1993-12-08
14.3.1 | VALVE LIST FOR LVCLP- UNITED ENGINEERS & CONSTRUCTORS | 1993-07-27
14.3.2 | TRAP LIST FOR LVCLP - UNITED ENGINEERS & CONSTRUCTORS | 1993-04-26
14.3.3 | STRAINER LIST FOR LVCLP - UNITED ENGINEERS & CONTRUCTORS | 1993-07-26
14.3.4 | PIPING LINE LIST FOR LVCLP-UNITED ENGINEERS & CONSTRUCTORS | 1993-09-17
14.3.5 | TAGGING AND NUMBERING SYSTEM | 2000-05-22
14.4 | GREENHOUSE PACKAGE BOILERS STUDY BY TRI-MONT | 1997-01-22
15 | PROMOTION
16 | CORRESPONDENCE
16.1.1 | RTP RECORD OF CONVERSATION | ONGOING
16.2.2 | TRI-MONT INLET CHILLING CONSIDERATIONS | 2000-04-12
16.2.3 | TRI-MONT REVISED CHILLER STUDY | 2000-04-17
16.2.4 | TRI-MONT AUXILIARY POWER DEMANDS | 2000-04-12
16.2.5 | DRAINAGE CALCULATIONS | 2000-05-22
16.2.6 | CHILLER STUDY, ABSORPTION VS MECHANICAL | 2000-05-24
16.2.8 | PRELIMINARY SCONOX VS SCR COMPARISON | 2000-05-03
16.2.9 | REVISED SCONOX VS SCR COMPARISON | 2000-05-04
16.2.10 | HEAT BALANCE | 2000-05-05
16.2.11 | NOTICE OF CONTENTS OF ADDENDUM 1 | 2000-07-21
16.2.12 | QF CAPABILITY OF UNIT 1 PROPOSAL FOR A SINGLE LARGE HOT WATER TANK | 2000-07-25
16.2.13 | MISC CORRESPONDENCE | ONGOING
16.2.14 | ONE-LINE DIAGRAM DETAILING REVISIONS TO 13.8 Kv CIRCUIT BREAKERS | 2000-06-16
16.3.2 | REQUEST FOR COURTNEY & NYE TO REVIEW CONDENSOR CALCULATION | 2000-04-27
16.3.6 | LVC II AIR PERMIT APPLICATION DEEMED COMPLETE LETTER FROM CLARK | 2000-06-13
16.8.3 | CONFIRMATION OF THE FUEL GAS PRESSURE REQUIRED FOR LM6000 SPRINT | 2000-05-30
16.8.4 | CHILLER OPTION PACKAGE DESCRIPTION FROM DAVE MARTIN AT S&S ENERGY PRODUCTS | 2000-06-20
16.11.1 | LETTER FROM LESLIE LONG RE EXPANSION ISSUES - TDS LEVELS, WASTEWATER COLEECTION SYSTEM CAPACITY, LEAVITT WELL WATER USE | 2000-05-17
16.18.1 | CITY OF NORTH LAS VEGAS PLANNING COMMISSION AGENDA FOR 8/23/00 MEETING | 2000-08-13
17 | CONSTRUCTION