## Sheet1
Enron Transportation Services
System Outage Request/Notification
[6 empty] | Submittal Date: ____ | 2002-01-11
|  |  |  | Planned: |  | Late: XX | Unplanned:
| Region/Location: |  | Transwestern Station 4
| Reported By: |  | Robert Stearns |  |  |  |  | New: | x | Revised
| Telephone No: |  | 928-871-4266 or3038 |  |  | If a Revision Enter outage ID#
or the Original Est. Start Date
| FAX No: |  | 928-871-5784
| Starting Date: |  | 2002-01-15 | Time: | 08:00 | Completion Date: |  | 2002-01-15 | Time: | 16:00
| Descripition of Work: |  |  | Shut unit 402 down to inspect crosshead for posible damage and to adjust all lifters. This has a priority 2 from the engine analysis report.
Facilities Affected
| Compressor Station: |  | Station 4 (Transwestern Pipeline) |  |  |  |  | Estimated Volume: |  | 250-400 mcf
|  | Units: | Unit 402 |  |  |  |  | Horse Power: |  | 4000 hp
Services Affected
| Mainline: |  | na |  |  |  |  | Aprox. Mile Post: |  | na
| Branchline/Transmission: |  | na |  |  |  | Reduced Operation Pressure: |  |  | na
|  | TBS: | [5 empty] | Farmtap: |  | na
| Comments: |  | Priority 2 If condition is not corrected ASAP damage to equipment and loss of production will occur.
| All Outages Fax Or E:mail To (Jerry Graves) |  |  |  | fax# (713)-345-3478 Houston
| Facility Planning (Outage Coordinator) |  |  |  |  | fax# (402)-3987041 Omaha
For Unplanned Outages Add these Burst FAX Numbers ( Project Link):
( For unplanned outages in the Holcomb, Liberal, Mullinville & Amarillo Regions Only)
| Oneok - Tulsa |  | Delaine Kruth |  |  | (918) 732-1355 |  | ET&S Gas Control (Houston): |  |  | 7138539155
| Oneok - Bushton |  | Alan Siemer |  |  | (316) 562-4373 |  | ET&S Gary Spraggins: |  |  | 7136468000
| Exxon-Mobil-Liberal |  | Ulysses |  |  | (316) 356-7580
[8 empty] | Anadarko: |  |  | 3166294505
| OXY-Liberal |  | Jay Muse |  |  | (316) 624-7014
| ETS - Liberal Operatons |  |  |  |  | (316) 626-2251