## Key Dates (3) (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
KEY DATES
| 1999 |  | 1998
| September 10 | Friday |  | Discuss revised game plan with Causey - focus on 3rd qtr and reorganization delays
Review draft of 2000 Budget straw man with Investor Relations
Receive outstanding Corporate cost centers
| September 13 | Monday |  | Receive International regional break-out
| September 15 | Wednesday |  | Review Summary of Corporate Cost Centers with Causey (3:00 p.m.)
|  |  | September 16 | Preliminary Service Group Costs Distributed to Business Units
| September 20 | Monday |  | Review Summary of Corporate Cost Centers with Skilling & Sutton
Review 2000 Budget straw man with Skilling & Sutton
| September 21 - 23 | Tues - Thurs | Last week of Sept | Meet with Corporate Cost Centers to plan presentation to Skilling & Sutton
| September 22 | Wednesday |  | Targets distributed to Business Units
| September 27 | Monday |  | Staff budget reviews with Management
| October 15 | Friday | October 16 | Operating & Strategic Plan due to Corporate Financial Planning
| November 1 - 9 | Mon - Tues | November 10, 11 & 17 | Executive Review of Business Units
| November 19 | Friday | November 13 & 19 | Plan Revisions Due to Corporate Financial Planning
| November 24 | Wednesday | November 20 | Board Book Information to Corporate Financial Planning
| November 30 | Tuesday | November 23 | Draft of Board Book Given to Causey & Skilling for Approval
| December 6 | Monday | November 30 | Complete & Mail Books to Board Members
| December 14 | Tuesday | December 8 | Presentation to the Board
2026-07-29 06:49
'file:///tmp/in/input.xls'#$Key Dates (3)

## Key Dates 2001
ENRON CORP
2002 - 2004 OPERATING & STRATEGIC PLAN
KEY DATES
2001
| August 6 * | Preliminary Corporate Groups Budgets due to Corp Financial Planning
| June 12 | Send out request for plan headcount
| June 22 | Headcount due to Corporate Financial Planning
| June 28 | Headcount submitted to Benefits & Risk Mgmt (Infor. returned to Corp. - July 13)
| July 18 | Corp. receives EPSC charges & total est. ENW charges for Corp. Depts.
| July 20 | Guidelines & files distributed to Corporate cost center owners
| August 13 | Corporate cost centers due to Corporate Financial Planning
| August 20-31 | Budget review meetings for Corporate cost centers
| September 14 *** | Distribute preliminary assessments to business units (all senders)
| October 1 | Estimated targets distributed to business units
| October 1*** | Final assessments distributed to business units (all senders)
| October 5*** | Distributed plan format to business units (this will be the Adaytum model; this date may change)
| October 19*** | Operating & Strategic Plan due to Corporate Financial Planning
| October 26 | Presentation Pages for Lay / Skilling Review to Corporate Financial Planning
| October 29 - November 9 | Executive Review of Business Units
| November 14*** | Plan Revisions Due to Corporate Financial Planning
| November 14 | Board Book Information to Corporate Financial Planning
| November 27 | Draft of Board Book Given to Causey & Skilling for Approval
| December 4 | Complete & Mail Books to Board Members
| December 11 | Presentation to the Board
*** Although the process of submitting data to Corporate may change due to the Adaytum implementation, these
will still be the anticipated due dates for these items. As Adyatum development progresses, Corporate will provide any
information regarding how these items will be handled.

## reviews (2) (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
BUDGET REVIEWS TO BE SCHEDULED
Group | Responsible Party | Estimated Duration | Date Scheduled
Corporate Staff Groups - Oct 1
Legal | Jim Derrick | 1/2 hour | Sept. 27 | 0.5
RAC | Rick Buy | 1/2 hour | Sept. 27 | 0.5
Accounting | Rick Causey | 1/2 hour | Sept. 27 | 0.5
Investor Relations | Mark Koenig | 1/2 hour | Sept. 27 | 0.5
Other Staff Functions | Steve Kean | 1 hour | Sept. 27 | 1
Government Affairs
Public Affairs
Enron Property
Corporate Development | Mark Metts | 1/2 hour | Sept. 27 | 0.5
HR & Community Relations | Cindy Olson | 1/2 hour | Sept. 27 | 0.5
Total Time Needed |  | 4 hours |  | 4
Global Functions - To be scheduled
Risk Management | Greg Whalley | 1/2 hour | Pending | 0.5
Finance | Andy Fastow | 1/2 hour | Pending | 0.5
Asset Operations | Kurt Huneke | 1/2 hour | Pending | 0.5
Engineering & Construction | Larry Izzo | 1/2 hour | Pending | 0.5
Technology | Mike McConnell | 1/2 hour | Pending | 0.5
Global E&P | Jeff Sherrick | 1/2 hour | Pending | 0.5
Total Time Needed |  | 3 hours |  | 3
Business Units - November 1 - 12
North America | Kevin Hannon\Cliff Baxter | 2 hours | Pending | 2
Europe | Mark Frevert | 2 hours | Pending | 2
Asia/Africa | Rebecca McDonald | 1 hour | Pending | 1
Caribbean/Middle East | David Haug | 1 hour | Pending | 1
India | Sanjay Bhatnagar | 1 hour | Pending | 1
South America | Jim Bannantine | 1 hour | Pending | 1
Gas Pipeline Group | Stan Horton | 1 hour | Pending | 1
Portland General Group | Peggy Fowler | 1 hour | Pending | 1
Enron Energy Services | Lou Pai \ Tom White | 2 hours | Pending | 2
Azurix | Rebecca Mark | 1 hour | Pending | 1
Enron Communications | Ken Rice \ Joe Hirko | 2 hours | Pending | 2
Enron Economic Development | Gene Humphrey | 1/2 hour | Pending | 0.5
Total Time Needed |  | 15 1/2 hours |  | 15.5

## bullet points (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
Targets
Income Targets
Set Net Income & Pre-tax targets
Other Objectives
Return on Investment
Cash Return on Capital Deployed
Pre-Tax Earnings on Capital Deployed
After-Tax Earnings on Capital Deployed
Funds Flow - no targets
Quarter vs Full Year targets
Quarter percentage growth same as total year percentage growth
Presentations
Free form as in prior years
Standard Format
1st Page
Pre-Tax Earnings, Net Income
Capital Deployed Ratios, Total Expenses
Headcount
Prior Year Information & Quarterly Information
Global Functions - presentations
Key Dates
Summary
Budget Review Schedule - Time Allotment
Plan for 2001 and 2002
Amount of Emphasis
Targets for 2001 and 2002
Work with Corporate Group

## Key Dates (2) (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
BUDGET REVEIWS TO BE SCHEDULED
Corporate Groups - August 13 - 25
| Corporate Group | Responsible Party | Estimated Duration | Date Scheduled
| Corporate Devlopment | Cliff Baxter | 1 hour
| Enron Capital Mgmt | Andy Fastow | 2 hours
| RAC | Rick Buy | 2 hours
| Legal | Jim Derrick | 1 1/2 hours
| Corporate Affairs | Cindy Olsen | 1 1/2 hours
| Steve Kean | Government Affairs | 2 hours
| Investor Relations | Mark Koenig | 1/2 hour
| CAIO | Rick Causey
| Corporate Accounting | Bob Butts | 1/2 hour
| Tax | Bob Hermann | 1/2 hour
| Information Services | Phillipe Bibi | 2 hours
| Enron Property Services | Bill Donavan | 2 hours
| Compensation & Benefits | Rocky Jones | 2 hours
| Total Time Needed |  | 17 1/2 hours
Business Units - November 1- 12
| ECT - North America | Ken Rice | 3 hours
| ECT - Europe | Mark Frevert | 3 hours
| Enron International | Joe Sutton | 3 hours
| Gas Pipelines Group | Stan Horton | 3 hours
| Portland General Group | Peggy Fowler | 2 hours
| Enron Oil & Gas | Mark Papa | 2 hours
| Enron Energy Services | Lou Pai | 3 hours
| Azurix | Rebecca Mark | 2 hours
| Enron Communications | Joe Hirko | 2 hours
| Enron Renewable Energy Corp | Tom White | 2 hours
| Enron Economic Development | Gene Humphrey | 1 hour
| Total Time Needed |  | 26 hours