## overall
ENRON GLOBAL ASSETS AND SERVICES
2002 - 2004 Plan Review
Overview Agenda
Date | Review | Location
EGAS Due Date
July 23 | Operating projects guidelines and formats sent
August 21 | Cost centers guidelines and format sent.
August 31 | Support cost centers due back to Agatha Tran
September 5 | Allocation % on commercial cost centers due back to Agatha
September 6 | Consolidated support cost centers sent to regions
September 8 | Payroll-related total commercial cost centers allocation given to regions
September 10 - 19 | Plan review with Jim Hughes - including cost centers (separate calendar sent) | Houston
September 17 | Tentative date - Corp charges review with J.Hughes - coordinating with Corp
September 20 | Plan due to Agatha - corp format
September 25 | Plan due to Agatha - EGAS format*
September 26 | Total EGAS Plan to Jim Hughes
October 2 or 3 | EGAS plan meeting with Stan Horton (12 - 6pm for Oct 2 / 9:00am - 12pm for Oct 3)
October 16 | Presentation pages for Lay meeting to Jim Hughes/Stan Horton
November 14 | Presentation pages for board book to Jim Hughes/Stan Horton
Other Due Date
September 14 | Corp Charges Sent to Business Units
September 14 | Earnings Target Distributed from Enron Corp
October 4 | Plan due to Enron Corp
October 18 | Presentation Pages for Executive Review due to Corp
November 8 | Lay Plan Review With Stan Horton (1:00pm - 5:00pm, EGAS is 1:00pm - 3:00pm)
November 12 | Plan Revision Due to Corp
November 19 | Board book presentations due to Corp
December 11 | Plan Presentation to the Board
*EGAS format is the old "Hannon" format where we show 100% project at the top and Enron's level of IBIT and NI on the bottom. This will be part of the
package given to Jim but will not be used for consolidations purposes.
'file:///tmp/in/input.xls'#$overall