## Expands
ENRON NORTH AMERICA |  |  |  | 2026-07-29 07:08 |  | expands2
PIPELINE EXPANSION UPDATE
Project
[5 empty] | Daily | Start |  | ECT |  |  | Term | Cost of
| Pipeline |  | Project | Path | Quantity | Date | Probability | Position | Docket | Pricing | Years | Project | Miles | HP
Northeast:
| Iroquois |  |  | Waddington to S. Comack | 35000 | 1996-11-01 | Done | 15000 | NA |  | 10
| National Fuel |  |  | Niagara to Leidy | 25000 | 1997-11-01 | Done | 25000 | CP96-671 |  | 10 | 10600000 |  | 1300
| Tennessee |  | Niagara Expansion | National Fuel Compressor Expansion | 21344 | 1997-11-01 | Done |  | CP96-721 |  |  | 51620
| Transco |  | Pocono Expansion Project | Leidy to Northhampton County, PA | 35000 | 1997-11-01 | Done |  | CP97-328 |  | 15 | 9800000
| Vermont Gas Systems |  |  | Import at Highgate Springs, Vermont | 52000 | 1997-11-01 | Done |  | CP97-324
| Transco |  | Seaboard 97 (or so) | Leidy to New York City | 115000 | 1997-11-01 | Dead | 30000 | CP96-545 |  | 15-21 | 117700000
| Dominion |  | Market Value Project | Lebanon to Leidy and CNG Citygates | 400000 | 1998-11-01 | Dead
| Iroquois |  | Athens | Waddington to Brookfield | 30160 | 1998-11-01 | Done |  | CP96-687 |  | 10 | 22000000 |  | 9500
| National Fuel |  | Son of Seaboard | Niagara to Leidy | 100000 | 1998-11-01 | Dead
| Tennessee |  | DOMAC Expansion | DOMAC Everett Plant to Saugus, Mass | 90000 | 1998-11-01 | Done |  | CP96-194 |  |  | 25900000 | 8
| Texas Eastern |  | Spectrum Related | Lebanon Lateral Expansion | 302290 | 1998-11-01 | Done |  | CP98-336 |  |  | 31000000 |  | 17070 | (Gas City and Glen Karn)
| Portland/Maritimes |  | Joint Line Application |  |  | 1999-02-01 | Done |  | CP97-238 |  |  | CP96-178 ???
| Algonquin |  | EMI Dighton, MA Plant | Delivery off mainline to Dighton Plant | 33000 | 1999-03-01 | Done |  | CP98-99 |  |  | 4662000 | 1.5 | 900
| Portland Natural Gas Transmission |  | Granite State PL replacement | TCPL to Tennessee at Haverhill, Mass. | 178000 | 1999-03-01 | Done | 30000 | CP96-248 |  | 15-20 | 270000000 | 243
| Algonquin LNG |  | Providence, RI tie to Algonquin | Northeast City Gates (currently 100,000) | 150000 | 1999-11-01 | Done |  | CP99-113 |  |  | 10705000
| Duke Energy |  | Spectrum | Chicago to New Jersey | 500000 | 1999-11-01 | Dead |  | CP97-626
| National Fuel |  | Grandson of Seaboard | Niagara to Leidy | 400000 | 1999-11-01 | Dead
| National Fuel |  | Ellisburg compression | Ellisburg to Leidy, PA | 60919 | 1999-11-01 | Done |  | CP99-160 |  |  | 223600 |  | 1245
| Portland Natural Gas Transmission |  | TQM Link | TQM from Sable Island to Dracut, Mass | 350000 | 1999-11-01 | Dead |  | CP96-249
| Tatham Offshore (Leviathon) |  | North Atlantic Pipeline Project | Hibernia/Sable Island to New England | 250000 | 1999-11-01 | Dead |  | CP98-29/30/31/32
| Tennessee |  | Ellisburg Extension (me too) | Niagara to Leidy | 250000 | 1999-11-01 | Dead
| Tennessee |  | Eastern Express | Chicago to Leidy | 500000 | 1999-11-01 | Dead
| Maritimes & Northeast |  | Sable Island Phase I | Wells, Maine to Dracut, MA (flows backwards) | 60000 | 1999-12-01 | Done |  | CP96-178 |  |  | 103726000
| Maritimes & Northeast |  | Sable Island Phase II | Sable Offshore Energy Int. to Dracut, Mass. | 360000 | 1999-12-01 | Done |  | CP96-809 |  |  | 79217000 | 454 | 31160
| Algonquin |  | EMI Tiverton Plant | Compressor Upgrades & mainline work | 46000 | 2000-06-01 | Done |  | CP99-46 |  |  | 13949960 | 15.98 | 900
| Texas Eastern |  | Duke Vermillion Lateral | Midwestern PL to the plant (Cayuga) | 200000 | 2000-06-01 | High |  | CP 00-67 |  |  | 13000000 | 14
| Maine Natural Gas |  | Westbrook Lateral | MN&E to the Calpine Westbrook Plant | 100000 | 2000-07-01 | High
| Maritimes & Northeast |  | Bangor Gas | Orrington, ME | 50000 | 2000-07-01 | Done |  | CP00-77 |  |  |  | 8.3 | 0
| Algonquin |  | Lake Road Plant | Mainline (Putnam Co) to Killingly CT Plant | 146000 | 2000-08-01 | Done |  | CP99-271 |  |  | 4700000 | 1.8 | 0
| Tennessee |  | Honeoye Storage Expansion | 1.8 Bcf increase in working gas | 15000 | 2000-08-01 | Low |  | CP00-93 |  |  | 3000000
| Maritimes & Northeast |  | Gorham Lateral | Mainline to Gorham, ME Plant | 165000 | 2000-09-01 | Done |  | CP98-724 |  |  | 2000000 | 1
| TETCO |  | AES Ironwood Plant Lateral | Lateral in TETCO M3 (PA) | 120000 | 2000-09-01 | Done | 20 yr | CP99-621 |  |  | 5700000 | 3.6 | 0
| Algonquin |  | ANP Bellingham Lateral | Mainline (Norfolk Co, MA) to Bellingham Plant | 110000 | 2000-10-01 | Done |  | CP98-100 |  |  | 4593000 | 1.1 | 0
| Continental States Peaking Svs |  | El Paso/Tennessee/MCN | Maryland/Delaware LNG 2.0 Bcf MSQ | 200000 | 2000-11-01 | Dead |  |  |  |  | 45000000
| Granite State |  | Wells LNG | Portland/Northern Utilities 2.0 Bcf MSQ |  | 2000-11-01 | Dead |  | CP96-610 |  | 20 | 44221000
| Iroquois/Tennessee |  | EPEM/PDC Milford Plant | Waddington to Milford/Tenn Zone 6 Delivery | 35000 | 2000-11-01 | High
| Maritimes & Northeast |  | Veazie Lateral | Eddington, ME to Veazie (Casco Bay Plant) | 105000 | 2000-11-01 | Done |  | CP98-797 |  |  | 6000000 | 1 | 0
| National Fuel |  | AM-60 Pipeline Replacement | Lamont, PA to Roystone, PA | 30000 | 2000-11-01 | Done |  |  |  |  | 11400000 | 12.9 | 360
| TETCO |  | Independence/ML Substitute | ANR/Muncie to Linden, NJ | 663000 | 2000-11-01 | Low
| TETCO |  | Excelsior | New Jersey to New York | 500000 | 2000-11-01 | Dead
| Texas Eastern/NGPL |  | Enhanced Spectrum | Chicago Alliance to M3 | 55000 | 2000-11-01 | High |  |  | 0.46
| Maritimes & Northeast |  | Halifax Lateral | NS Power Tufts Cove Plant | 166000 | 2000-11-01 | Done | [5 empty] | 63
| NGPL |  | New York | Chicago to New York |  | 2000-12-01 | Dead
| Maritimes & Northeast |  | St John Lateral | JDI & NB Power Bayside Power Station | 105002 | 2000-12-01 | Done |  | CP98-799 |  |  | 6000002 | 3
| Maine Natural Gas |  | Brunswick Lateral | MN&E to Brunswick and Topsham | 50000 | 2001-08-01 | High |  |  |  |  | 10000000 | 18
| Tennessee |  | Stagecoach Lateral | Central New York - Tennessee Line 300 | 500000 | 2001-08-01 | High | FEIS rcvd | CP 00-65 |  | 10 | 81271600 | 23.7 | 13400
| Algonquin |  | Sithe Energy Lateral | Lateral from Canton, MA to Plant (Fore River) | 140000 | 2001-09-01 | High |  | CP 00-34 | AFT-CL | 20 | 32021000 | 7.4 | 0
| Maritimes & Northeast |  | Four Rivers Plant |  |  | 2001-09-01 | Med
| Tennessee |  | Concord Lateral/AES Londonderry | Dracut to Londonderry, NH 20" replacement | 130000 | 2001-11-01 | Done |  | CP 00-48 |  | 20 | 34513000 | 19.3 | 0
| Dominion/Tennessee |  | Atlantic Advantage Project | Chicago/Niagara to the Northeast | 750000 | 2001-11-01 | Dead
| Duke Energy/Williams/Iroquois |  | Lighthouse Pipeline | Long Island to Milford, CT | 350000 | 2001-11-01 | Dead |  |  |  |  | 240000000
| Iroquois |  | Vermont Extension | EDC Bennington & Rutland Plants | 250000 | 2001-11-01 | Dead |  |  |  |  | 105000000 | 70
| Tennessee |  | Eastern Express 2000 | Dracut to New England | 173000 | 2001-01-01 | Done |  | CP99-262 | rolled in |  | 28143432 | 0 | 13300
| Tennessee |  | CanEast | Niagara/Gulf Coast to Leidy via CNG lease | 280000 | 2002-11-01 | High
| Transco |  | MarketLink Phase I | Leidy to New York City | 166000 | 2001-11-01 | Done |  | CP98-540 |  |  | 123300000 | 60.6 | 30000
| TETCO |  | Phildelphia Lateral Expansion | Liberty Plants (Columbia and PG&E) | 84000 | 2002-01-01 | High |  | CP00-404 |  | 14.5 |  | 1 | 4000
| DOMAC |  | Sithe Mystic Plant Expansion | 4 submerged combustion vaporization units | 280000 | 2002-05-01 | High |  | CP00-447
| Algonquin |  | HubLine/M&NE Extension | Beverly, MA (MNE) to Weymouth, MA | 300500 | 2002-11-01 | Med |  | CP01-5 |  |  | 114048000 | 34.8 | 0
| Columbia Gas/CMS/MCN/Westcoast |  | Millennium | Chicago to New York City | 650000 | 2002-11-01 | Low |  | CP98-150 |  |  | 678000000 | 443
| Iroquois |  | Eastchester Bay Marine Ext Proj | Waddington to Eastchester (ConEd) | 230000 | 2002-11-01 | High | None | CP00-232 | rolled in | 10-30 | 173918000 | 30.3 | 58300
| Transco |  | Trenton Woodbury Loop Expansion | Station 210 to Zone 6 | 100000 | 2002-11-01 | Low
| Iroquois |  | Eastchester Bay Marine II | Waddington to Eastchester (ConEd) | 200000 | 2004-11-01 | Low
| Tennessee |  | New England Expansion | Replace crossover Dracut to Burlington, MA | 120000 | 2002-11-01 | Low |  |  |  |  | 37225000 | 12
| Texas Eastern |  | Texas Eastern Incremental Market | ELA/Gas City to M3 | 1300000 | 2002-11-01 | Low
| Maritimes & Northeast |  | Phase III | expand and add Beverly MA as Delivery Point | 360000 | 2003-11-01 | Med |  | CP01-4 |  |  | 265000000 | 25.1 | 0
| TCPL/St. Clair Pipeline |  | Lake Erie Crossing Pipeline | 7 shippers | 650000 | 2002-11-01 | Med |  |  |  |  | 106000000 | 60
| Transco |  | MarketLink Phase II | Leidy to New York City | 130000 | 2002-11-01 | Done |  | CP98-540 |  |  | 119600000
| Transco/ANR/National Fuel |  | Independence Pipeline | Chicago to Leidy | 946500 | 2002-11-01 | Med |  | CP97-315/320/321 |  |  | 629600000 | 400 | 60000
| Duke Energy/Williams/Keyspan |  | Cross Bay Pipeline | Transco/TETCO in NJ to JFK Airport | 125000 | 2002-12-01 | Low |  | CP00-412-414 |  |  | 59500000 | 33.7 | 16000
| Duke Energy/Keyspan |  | Islander East | Connecticut across Long Island Sound | 250000 | 2003-11-01 | Low | [5 empty] | 40
| Tennessee |  | Connecticut - Long Island Project | Dracut to Long Island | 450000 | 2003-11-01 | Low
| Transco |  | MarketLink Phase III | Leidy to New York City | 432000 | 2004-11-01 | Med |  | CP98-540
| MHP |  | Tioga Storage Facility (PA) | 5.0 Bcf working gas capacity | 1500000 | 2004 | High
Southeast:
| Transco |  | Southeast Mainline Exp I | Stn 85 to Stn 150 NC | 35000 | 1994-11-01 | Done |  | CP94-68
| Transco |  | Southeast Mainline Exp II | Stn 85 to Stn 150 NC | 115000 | 1995-11-01 | Done |  | CP94-109
| Southern |  | North System | North System to Chattanooga | 25000 | 1996-11-01 | Done |  | CP94-682
| Transco |  | Southeast Mainline Exp III | Stn 85 to Stn 150 NC | 50000 | 1996-11-01 | Done |  | CP94-109
| East Tennessee |  | System Wide | Knoxville Area | 31902 | 1997-11-01 | Done |  | CP96-696 |  | 3-10 | 12915473
| South Carolina Pipeline |  | New compressor - Blacksburg | Increase Transco takeaway | 75000 | 1997-11-01 | Done |  | Non-Jurisdictional |  |  | 10000000
| Southern |  | Zone 3 Markets | MS/AL Loops - Wren/Savannah Line | 45880 | 1997-11-01 | Done |  | CP96-541 |  | 10 | 36043000 | 28 | 10640
| Transco |  | SunBelt | 100 Stn 65 to Stn 85, 146 Stn 85 to Stn 145 NC | 145666 | 1997-11-01 | Done |  | CP96-16 |  | 20 | 85000000 | 15 | 30000
| Transco |  | Maiden Lateral | Expansion to Piedmont | 69000 | 1997-12-01 | Done |  | CP97-193 |  |  | 13200000 | 18
| East Tennessee |  | Virginia Expansion Project | Greenbriar, TN to Chilhowie & Roanoke, VA | 10300 | 1998-11-01 | Done | Roanoke Gas | CP98-40 |  | 20 | 8600000 | 10
| Southern |  | Zone 2 and 3 Markets | MS/AL Loops | 64911 | 1998-11-01 | Done |  | CP97-526 |  | 12 | 52179005
| Transco |  | Cherokee Expansion | Stn 85 to Stn 130 Madison Co., GA | 87070 | 1998-11-01 | Done |  | CP97-331 |  | 15 | 68000000 | 15 | 23000
| Southern |  | Zone 2 Markets | Alabama Power | 34925 | 1998-12-01 | Done |  | CP97-526 | Increm | 12 | 52179005
| Pine Needle LNG |  | Transco/Piedmont | North Carolina Peaking 4 Bcf MSQ | 400000 | 1999-11-01 | Done |  | CP96-52 |  | 20 | 107000000
| Transco/PSNC/Piedmont/NCNG |  | Cardinal Extension Co. | Stn 160 Rockingham, NC to Burlington, NC | 140000 | 1999-11-01 | Done |  | Non-Jurisdictional |  |  | 98300000 | 67
| Southern |  | North Alabama PL Exp | N. Alabama to Huntsville (Alatenn Bypass) | 76350 | 2000-01-01 | Done |  | CP96-153 |  |  | 66800000 | 118 | 6300
| ANR |  | LS Power Batesville lateral | Panola, MS to Tennessee 20" | 235000 | 2000-06-01 | Done |  | CP98-801 |  |  |  | 15
| Tennessee |  | LS Power Batesville lateral | Panola, MS to Tennessee | 216000 | 2000-06-01 | Done |  | CP98-770 |  |  |  | 3
| Transco |  | Cumberland Pipeline | Walton Co., GA to Chattanooga, TN | 450000 | 2000-11-01 | Dead |  |  |  |  | 115000000 | 141
| Transco |  | Cumberland Pipeline II | Walton Co., GA to Chattanooga, TN | 220000 | 2000-11-01 | Dead
| Transco |  | SouthCoast | Stn 85 to Zone 4 points north of Atlanta, GA | 204999 | 2000-11-01 | Done | PD recvd | CP99-392 | Southern Co 40,000/d | 15 | 108000000 | 44 | 31500
| Columbia Gulf |  | Vicksburg Lateral to Entergy Plants | Mainline (Richland Parish, LA) to Baxter Wilson Plant | 285000 | 2001-05-01 | Done |  | CP01-28 |  |  | 20148000 | 36.83 | 0
| Florida Gas Transmission |  | Phase IV | Central and South Central Florida | 272000 | 2001-05-01 | High | PD recvd | CP99-94 |  | DEIS | 351000000 | 205 | 48570
| Trunkline LNG |  | Lake Charles LNG regasification | No increase to terminal, just regasification | 300000 | 2001-05-01 | Med |  |  |  |  | 1155000
| Bay Gas |  | Mobile County Expansion |  |  | 2001-06-01 | Med | [5 empty] | 18
| CP&L |  | Iredell-Richmond Pipeline | Transco Stn 150 (Sundance) to CP&L Richmond Co | 200000 | 2001-06-01 | Med |  |  |  |  | 100000000 | 82
| Petal Gas Storage |  | Hattiesburg Storage Lateral | Hattiesburg,MS to Destin, Koch, Sonat & Transco | 700000 | 2001-06-01 | Done |  | CP00-59 |  |  |  | 5.5 | 35000
| Reliant Energy Gas Transmission |  | Pine Bluff Plant Lateral (Skygen) | Jefferson Co, AR (Line AC) | 40000 | 2001-06-01 | High | Skygen | CP00-137 |  | 10 | 1500000 | 2
| Southern Natural Gas |  | Wrens Compression Upgrade | Improve flow on Wrens/Savannah Line |  | 2001-10-01 | Done |  | CP00-231 |  |  | 5151438 |  | 3500
| ANR |  | Mountaintop | Brownsville Compressor to Altanta, GA | 500000 | 2001-11-01 | Low
| East Tennessee |  | Rocky Top Expansion | Greenbriar, TN to Chilhowie & Roanoke, VA | 35068 | 2001-11-01 | Done |  | CP00-51 |  | 10 | 18129000 | 28.73 | 0
| MCN/Columbia Gulf |  | Volunteer Pipeline | Chicago (via Midw) to Atlanta | 250000 | 2001-11-01 | Low |  |  |  |  | 160000000
| South Georgia |  | Holy Trinity Looping | SoNat to South Georgia gates | 17000 | 2001-11-01 | High |  | CP01-95 |  |  | 5969100 | 7.1 | 0
| Southern Natural Gas |  | AL/GA Expansion |  | 17000 | 2001-11-01 | Med |  | CP01-35 |  |  | 6000000 | 7
| Southern/AGL |  | Etowah LNG | Polk County, Georgia 3 Bcf | 450000 | 2001-11-01 | Med |  | CP98-363 |  | 20
| Southern LNG |  | Elba Island LNG Terminal | 4 Bcf Capacity | 330000 | 2002-01-01 | High | PD recvd | CP99-579 |  |  | 26200000
| Florida Gas Transmission |  | Phase V | Plant Smith and Sanford Plant | 428000 | 2002-04-01 | High |  | CP00-40 |  |  | 466000000 | 191 | 125215
| Panda |  | Trans-Union Interstate Pipeline | Claibourne Parish, LA to Arkansas Plant | 400000 | 2002-04-01 | Done |  | CP00-47 |  |  | 41000000 | 41.7
| Southern/CP&L |  | Palmetto Interstate Pipeline | SoNat system expansion and extension from Aiken, SC to Robeson CO, NC (NCNG) | 250000 | 2002-04-01 | Dead |  |  |  |  | 450000000 | 175
| Transco |  | Sundance Pipeline | Station 65 to North Carolina (CP&L) | 236383 | 2002-04-01 | Done | Inc Rate | CP00-165 | FERC approved | 15 | 134674037 | 421 | 41225
| Transco |  | Cove Point LNG | add fifth tank and pipeline facilities | 1000000 | 2003-09-01 | Med |  |  |  |  | 103000000
| Southern Natural Gas |  | South System Expansion | Phase I Loop from MS to GA/Phase II Loop from MS toAL | 335800 | 2002-06-01 | Done |  | CP00-233 |  |  | 140736540 | 67.3 | 53890
| Transco/Duke (Formerly Coastal) |  | Gulfstream | Mobile, AL to West Palm Beach, FL | 1130000 | 2002-06-01 | High | FEIS | CP00-6 | FERC approved |  | 1600000000 | 744
| East Tennessee |  | Patriot Extension | Virginia to North Carolina (Transco) | 200000 | 2002-11-01 | Low |  |  |  |  | 215000000 | 95
| FGT/El Paso |  | Cypress | Elba Island LNG to FGT Jacksonville | 310000 | 2003-04-01 | Med |  |  |  |  | 232000000 | 160 | 0
| Transco/Duke |  | Buccaneer Pipeline | Station 82 to north of Tampa Bay | 900000 | 2003-04-01 | Dead |  | CP00-14 |  |  | 1455173425 | 673.88 | 75000
| Florida Gas Transmission |  | Phase VI | Bayside Plant | 175000 | 2003-05-01 | Med
| Transco |  | Momentum Expansion Project | Station 65 to Station 165 Virginia excl So VA lateral | 475000 | 2003-05-01 | Med | Inc Rates |  |  | 175
| Scana |  | Carolinas Pipeline | South Carolina (Elba) to North Carolina (Pembroke) | 250000 | 2003-11-01 | Low |  |  |  |  | 1780000000
| Dominion |  | Greenbriar Pipeline | Cornwell to Rockingham, NC | 600000 | 2005-06-01 | Low |  |  |  |  | 400000000 | 200 | 31000
| East Tennessee |  | Murray Generating (Duke) | Hamilton Co., TN to Murray Co., GA | 170000 | 2002-02-01 | High |  | CP01-80 |  |  |  | 27 | 10950
Texas/OK to Louisiana:
| Sabine |  |  | HPL to Henry | 30000 | 1996-12-01 | Done
| Delhi |  | East Texas Cotton Valley | Pinnacle Reef Gathering Capacity | 275000 | 1997-04-01 | Done |  | Non-Jurisdictional
| Valero |  | Texas Expansion I | Bethel - Pinnacle Reef to Carthage Hub | 250000 | 1997-07-01 | Done |  | Non-Jurisdictional |  |  | 11700000
| Southern |  | N. Louisiana | Texas to Louisiana |  | 1997-11-01 | Dead
| Ozark |  |  | Oklahoma to Louisiana | 185000 | 1997-11-01 | Dead
| Trunkline |  |  | Katy to Henry | 250000 | 1997-11-01 | Dead
| Florida Gas Transmission |  |  | Texas to Louisiana |  | 1997-11-01 | Dead
| NGPL |  | Louisiana Line Expansion | Compression | 63000 | 1997-11-01 | Dead |  | CP96-720 |  | 7 | 4300000
| NGPL |  |  | Arkoma to Henry | 125000 | 1997-12-01 | Dead
| Valero |  | Texas Expansion II | Bethel - Pinnacle Reef to Carthage Hub | 200000 | 1998-06-01 | Dead |  | Non-Jurisdictional
| Noram |  | North Louisiana Expansion | Carthage to Perryville Hub | 170000 | 1998-11-01 | Done | UPRC 50/Amoco 15 | CP97-724 |  | 10/5 | 32200000
| Koch Gateway |  | East Texas | Carthage to Perryville | 250000 | 1998-11-01 | Dead |  |  |  |  | 31000000
| ANR |  | Katy Project | Katy to Eunice | 200000 | 1999-11-01 | Dead
Onshore Louisiana/Texas:
| Southern Natural Gas |  | TOCA Expansion |  |  |  | Done |  | CP95-500
| Southern Natural Gas | 1 | Lease of Capacity by Destin | Destin delivery into SoNat to TETCO Cranfield | 200000 | 1998-09-01 | Order disallowed roll-in |  | CP96-655 |  | 20
| Koch Gateway Pipeline |  | Venice Expansion | Venice to Koch Mainline | 615000 | 1997-11-01 | Done |  | CP96-572 |  |  | 20500000
| Venice Gathering System LLC |  | Venice Expansion |  | 328000 | 1998-11-01 | Done |  | CP97-533/534 |  |  | 40000000 | 52
| Texas Gas Transmission |  | Carthage Expansion | Haughton Comp Stn to Bossier Parish, LA | 105000 | 1998-11-01 | Done | UPRC | CP97-656 |  | 10 | 5980000 |  | 4600
| Mid Louisiana |  | Baton Rouge Expansion | Transco Station 61 to Baton Rouge | 60000 | 1998-10-01 | Low
| Columbia Gulf |  | Onshore Louisiana | Eastern Legs to Rayne (3 phases) | 400000 | 1998-11-01 | Dead
| Columbia Gulf |  | Mainline 99 | Rayne to Leach (3 compression upgrades) | 315000 | 1999-12-01 | Done | 27%LDC/63%Mktg/10%Indust |  |  |  | 38000000
|  |  |  | (270,000 11/99 & 45,000 11/2000) |  |  |  |  | CP98-596 | rolled in
| Reliant |  | SWEPCO Wilkes Plt Extension |  | 100000 | 2000-06-01 | Done | [5 empty] | 18
| Trunkline |  | Centennial Project | 720 miles of 26" line (chicago to gulf) | -255000 | 2001-12-01 | Low |  | CP00-114 |  |  | -10200000
|  |  | Liquids line conversion | Longville, LA to Bourbon, IL
| Gulf States Pipeline |  | Panda El Dorado Plant | Expansion from the Sharon La tie-in to TGP |  | 2002-06-01 | Med
| Tennessee |  | Panda El Dorado Plant | Interconnect |  | 2002-06-01 | Med
| Trans-Union Interstate Pipeline |  | Panda El Dorado Plant | Gulf States Pipeline to the El Dorado Plant | 430000 | 2002-06-01 | Med | [5 empty] | 42
| Trunkline LNG |  | Lake Charles Terminal | Increase sendout from 0.7 to 1.0 Bcf | 300000 | 2001-05-01 | Med |  |  |  |  | 2250000
Deep Water Louisiana:
| Stingray Pipeline Company |  | Garden Banks 72/VER Blocks | GB 72 to Stingray at VER 362 lateral | 100000 | 1995-11-01 | Done |  | CP96-91 |  |  | 9000000 | 15
| Mississippi Canyon Gath System |  | Shell (Mars, Ursa, Mensa) | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 600000 | 1996-09-01 | Done |  | CP96-159 |  |  | 75000000 | 45
| Garden Banks Pipeline |  | Shell/Hess (Ench/Auger/Bladpate) | GB 128A (Enchilada) to SMI 76 (BlueW/TRCO) | 600000 | 1997-04-01 | Done |  | CP96-679 |  |  | 108000000 | 50
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | GC 65 (Bullwinkle) to Ship Shoal 207 (Nautilus) | 300000 | 1997-12-15 | Done |  | CP96-796
| Nautilus Pipeline |  | Shell | SS 207 to South Bend, LA (Troika) to ANR | 600000 | 1997-12-15 | Done |  | CP96-790/791/792 |  |  | 121000000 | 101
| Discovery Gas Transmission |  | Texaco/MAPCO/British Borneo (Hardy/Allegheny/Morpeth) | ST 200, GI 115 & EB 873 to Larose, LA | 600000 | 1998-01-01 | Done |  | CP96-712 |  |  | 300000000 | 147
| Dauphin Island Gath System |  | Phase I | Main Pass 225 to AST 73 | 200000 | 1998-04-01 | Done |  | CP97-301 |  |  | 54000000 | 63
| Trunkline |  | SS Block 139 Compression | SS 139 to Patterson (upstream of constraints) | 500000 | 1998-05-01 | Done |  | CP97-105 |  |  | 52217940 |  | 28950
| Transco |  | Mobile Bay Extension | Main Pass 261 to Mobile Bay 822 to Stn 82 | 350000 | 1998-08-01 | Done | WESCO | CP97-92 |  | 15 | 120200000 | 77 | 30000 | Totally in-service on Nov. 9
| Transco |  | Mobile Bay Expansion | Station 85 | 128137 | 1998-08-01 | Done |  | CP97-93
| Destin Pipeline Svs Company |  | Shell/Amoco | MP/VK to Pascagoula Area (VK 915 Marlin) | 1000000 | 1998-09-01 | Done |  | CP96-655 |  |  | 308000000 | 210 | 26400
| Dauphin Island Gath System |  | Phase II | Alabama State Tract 73 to Transco/Colden, AL | 300000 | 1998-10-01 | Done |  | CP98-6 |  |  | 19000000 | 13
| Tennessee/Leviathon |  | Viosca Knoll Expansion | Looping of existing VK Line (Bi-flow) | 250000 | 1998-11-01 | Done
| Transco |  | Mobile Bay Expansion II | Station 85 | 135711 | 1998-11-01 | Done |  | CP97-94
| Transco |  | Genesis Field | Green Canyon 205 to Transco Ship Shoal | 72000 | 1999-02-01 | Done |  | Non-Jurisdictional
| Mississippi Canyon Gath System II |  | Compression upgrades | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 200000 | 1999-07-01 | Done |  |  |  |  | 216000
| Transco |  | SE Louisiana Crossover | Garden Banks PL @ SMI 76 to Station 50 | 264020 | 1999-09-01 | Done | at risk | CP99-76 |  | Hess | 80000000 | 53
| Transco |  | SE Louisiana Crossover | SMI 76 to VER 67 offshore | 141970 | 1999-09-01 | Done | at risk | CP99-76
| Destin Pipeline Svs Company |  | Shell/Amoco | New Lateral MP 283 to MP 279 (Gemini) | 111675 | 1999-11-01 | Done | Mobil & Phillips | CP98-512 |  |  | 7200000 | 31
| El Paso Field Services |  | Diana Line | East Breaks 945/6 to HIOS @ EB 165 | 500000 | 1999-11-01 | Med
| Green Canyon Gathering System |  | Tennessee/National Fuel | EB, GC & MC to Lafourche Parish, LA | 515000 | 1999-11-01 | Low |  | CP96-557 |  |  | 200000000 | 133
| Koch |  | Grand Isles Extension |  | 300000 | 1999-11-01 | Dead | [5 empty] | 5
| Tennessee |  | Express 500 | 500 Line Expansion from offshore LA |  | 1999-11-01 | Low
| Columbia Gulf |  | Sun Star (SP & WD to GI) | 2 new 24" laterals and one 30" mainline | 660000 | 1999-12-01 | Low | [5 empty] | 56
| Texas Eastern Transmission |  | Lease of Capacity by DIGP | Main Pass 164 to Venice Plant | 100000 | 2000-01-01 | Done | 15 | CP99-18 |  |  |  | 10
| ANR/Leviathan/NGPL |  | East Breaks Gathering | Alaminos Canyon 25 to HIOS HI A-573 (Diana/Hoover) | 400000 | 2000-07-01 | Done |  |  |  |  | 90000000 | 85
| Tennessee |  | Texas Deepwater link Project | HIOS WC 167 to WC 180 (Tennessee) | 400000 | 2000-11-01 | Med | Vastar | CP00-441 |  |  | 14500000 | 17.5
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | ST 292 to GI 116 (Anadarko/Hickory) | 300000 | 2001-03-01 | High | [5 empty] | 22
| Canyon Express |  | Total/Fina/Elf | Aconcaqua/KingsPeak/CandemHills to EMP 261 | 500000 | 2001-05-01 | Med
| Williams |  | Kerr McGee Boomvang/Nansen | connects to CTGS | 300000 | 2001-11-01 | Med |  |  |  |  | 200000000 | 55
| Leviathan/Tejas |  | Nemo Gathering | Brutus (GC 158) to Manta Ray | 150000 | 2001-12-01 | Med | [5 empty] | 24
| ANR |  | Conch Project | EI 63 to Patterson | 461000 | on hold | FERC ordered at risk |  | CP97-71 |  |  | 51200000 | 37 | 461
| Chandeleur Pipe Line |  | Chevron | Venice Plant to Destin @ Pascagoula | 41000 |  | Low |  | CP01-81
Mexico:
| Valero |  | Reynosa | McAllen, TX to Reynosa, Mexico | 400000 |  | Done |  | Non-Jurisdictional
| El Paso |  | Douglas Extension | Extension from Douglas to Mexico Border | 78000 |  | Done | Grupo Mex | CP98-359 |  |  | 600000 | 1
| El Paso |  | Samalayucca II (Phase I) | Waco Station to PEMEX Juarez (Guars) | 72000 | 1998-06-01 | Done | PEMEX | CP93-252 |  |  | 18200000 | 20
| El Paso |  | Samalayucca II (Phase II) | Waco Station to PEMEX Juarez (Guars) | 100000 | 1998-10-01 | Done | Samal..
| Tenneco |  | Donna Lateral | Extension to Reynosa | 220000 | 1999-10-01 | Done |  | CP98-28 |  |  | 15000000 | 10
| Tenneco |  | Mexicali | California to Baja California |  |  | Dead | replaced by Sempra
| Sempra Energy International |  | Rosarito Power Plt/Vecinos | Riverside Co., CA to Tijuana | 500000 | 1999-12-01 | Done | Sempra | CP94-207 |  |  | 35000000 | 23
| El Paso |  | PEMEX | Waco Station to PEMEX Juarez (Guars) | 40000 | 2000-01-01 | Done
| TCPL |  | Merida III Power Plant | Ciudad Pemex, Tabasco to Campeche/Merida | 370000 | 2000-06-01 | Done
| Coral Mexico |  | New PEMEX Line/Border Crossing | Kleburg County to Hildago Co., TX | 300000 | 2000-11-01 | Done |  | CP99-564 |  |  | 30000000 | 104
| Midcon Texas |  | Roma Crossing | Bob West Field to Mexican Border | 275000 | 2000-12-01 | Med |  | CP96-770
| Midcon Texas |  | Monterey Pipeline Project | Cuidad Mier to Monterey | 275000 | 2000-12-01 | Med |  | CP96-583 |  |  | 520000 | 92
| El Paso |  | Willcox Lateral | Extension from Willcox to Douglas (Border) | 130000 | 2001-09-01 | High |  | CP99-322 |  |  | 30000000 | 56
| El Paso |  | Yuma Extension | Yuma to Baja California (Mexicali) | 300000 | 2002-01-01 | Med |  |  |  |  | 143000000 | 94
| Sempra/PG&E/Proxima Gas SA |  | North Baja Pipeline/Ehrenberg Exp | El Paso Ehrenberg to Baja California | 500000 | 2002-09-01 | Med |  | CP01-22 |  |  | 146000000 | 212
West:
| Transwestern |  |  | San Juan Lateral | 255000 | 1996-12-01 | Done | 8000 | CP96-10 |  |  | 14600000
| Transwestern |  |  | Thoreau to East | 107000 | 1996-12-01 | Done | 8000
| El Paso |  | Havasu | San Juan to East | 184140 | 1997-05-01 | Done | 16495 | CP96-321 |  |  | 19564419
| El Paso |  | Bondad Compressor Expansion | Ignacio to Blanco Station | 116500 | 1999-01-01 | Dead | 100000 | CP98-149 |  |  | 3600000 |  | 5160
| AEC |  | Wild Goose Storage | PG&E/Scramento Area | 14.0 Bcf | 1999-04-01 | Done |  | Non-Jurisdictional
| Transwestern |  | San Juan Junior | Ignacio to Blanco | 200000 | 1998-04-01 | Dead | 45000 | CP97-516 |  |  | 21000000 |  | 22000
| Transwestern |  | San Juan Junior | Blanco to Thoreau | 130000 | 1998-04-01 | Dead | 45000 | CP97-517
| Pacific Gas Transmission |  | Kingsgate to Malin | Duke, Montana Power, El Paso, POCO, Avista | 57000 | 1998-11-01 | Done |  | CP98-167 |  | 3-15 | 6000000
| Northwest Pipeline |  | Columbia River Gorge Expansion | Stanfield to Sumas | 50000 | 1999-11-01 | Done | DETM | CP98-554 |  |  | 18570000 |  | 10870
| Questar |  | Southern Trails | San Juan to Long Beach | 120000 | 2001-10-01 | Med |  | CP99-163 |  |  | 155000000 | 705
| Kern River |  | Long Beach Extension | Bakersfield to Long Beach | 300000 | 2001-11-01 | Low
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 300000 | 2001-11-01 | on hold
| Transwestern |  | Gallup Expansion | Thoreau to California Border | 140000 | 2000-05-01 | Done |  | CP99-552 |  |  | 11600000 |  | 10000
| Northwest Pipeline |  | Jackson Prairie Expansion | Storage Field Expansion of 3.2 Bcf | 300000 | 1999-11-01 | Done |  | CP98-250 |  |  | 30192000 |  | 6960
| Northwest Pipeline |  | Jackson Prairie Expansion II | Displacement expansion for system operations | 175000 | 2003 | Med |  | CP98-251 |  |  | 100000000 |  | 6961
| Northwest Natural Gas |  | Mist Expansion Phase III | Storage Field Expansion of 2 Bcf | 45000 | [6 empty] | 122000000 | eight year plan
| Northwest Natural Gas |  | Mist Expansion Phases IV | Storage Field Expansion of 14 Bcf |  | 2002-11-01 | Low |  |  |  |  | 58000000 | 32
| Northwest Natural Gas |  | Mist Expansion Phases V | Storage Field Expansion of 14 Bcf |  | 2004-11-01 | Low | [5 empty] | 20
| Sumas Energy 2 |  | NWPL bypass | Westcoast Energy to 720 MW CC Plant | 140000 | 2003-11-01 | Med |  | CP99-320 |  |  |  | 4.5
| Williams/BC Hydro |  | Gerogia Straight Crossing | Sumas to Vancouver Island | 100000 | 2002-11-01 | Med | NEB Filed |  |  |  | 120000000 | 85
| El Paso |  | Line 2000 - oil line conversion | Midland to Bakersfield (mostly replacement) | 0 | 2002-01-01 | High
| Northwest Pipeline |  | Displacement Expansion | Ignacio to Stanfield Corridor | 175000 | 2003-10-01 | High |  |  |  |  | 81000000
| Westcoast/Cascade/Puget Sound |  | Orca Gas Pipeline | Sumas to Puget Sound |  | 2004 | [6 empty] | 140
| Western Hub Partners |  | LODI Storage | Connects to PG&E | 12.0 Bcf | 2001 | [5 empty] | 80000000 | 35
| Western Hub Partners |  | Wheeler Ridege Storage |  | 12.0 Bcf | 2004
| Westcoast |  | Orca Natural Gas Pipeline | Sumas to Washington areas | 430000 | 2004-11-01 | On Hold |  |  |  |  | 195000000 | 140 | 22000
| PG&E/Avista |  | Jackson Prairie Expansion | Storage Field Expansion of 5.0 Bcf |  | 2003-10-01 | Med
| PG&E/Avista |  | Stanfield Storage | Stanfield, OR 15.0 Bcf working gas |  | 2003-11-01 | Med
| Kern River |  | Early CA Expansions Project | Opal to Bakersfield | 135000 | 2001-07-01 | High |  |  |  |  | 81000000 |  | 3 comps
| Kern River |  | California Expansion Project | Opal to Bakersfield (some EOC) | 124500 | 2002-05-01 | High |  | CP01-31 |  |  | 80000000 |  | 3 comps
| Northwest Pipeline |  | Puget Sound Plant Lateral | Snohonmish County, WA | 133000 | 2002-08-01 | High |  | CP01-49 |  |  | 17200000 | 9
| Northwest Pipeline |  | Grants Pass Lateral Expansion |  | 50000 | 2002-11-01 | Med
| PGT |  | Kingsgate to Malin | Kingsgate to Malin | 200000 | 2002-11-01 | High | [5 empty] | 21 | 5 comps
| PGT |  | Kingsgate to Malin | Kingsgate to Malin | 300000 | 2003-11-01 | Med
| Tuscarora |  | Sierra Pacific Power | Lemmon Valley, NV Plant | 75000 | 2002-12-01 | Med |  |  |  |  | 10200000 | 16.4
| Transwestern |  | Red Rock Expansion Project | could be as much as 600,000/d | 150000 | 2002-06-01 | Med
| Kern River |  | Kern River Expansion II | Opal to Bakersfield (mostly EOC) | 900000 | 2003-05-01 | High
| El Paso |  | RedHawk/Arlington Valley Lateral | Lateral to the Duke and Pinnacle Plants | 620000 | 2002-06-01 | High |  | CP01-90 |  |  | 7700000 | 6.7
Rockies:
| CIG |  | Parachute Creek lateral | Uinta Lateral to Parachute | 37000 | 1996-09-27 | Done
| TransColorado |  | Phase I | Rio Blanco, CO to EP Blanco | 75000 | 1996-12-01 | Done |  | CP90-1777 |  |  | 14100000
| CIG |  | Wind River | Lateral Expansion | 68000 | 1997-08-01 | Done |  | CP96-289 |  |  | 10844200 |  | 10566
| KNE |  | Pony Express | Wind River Basin to Kansas City | 135000 | 1997-08-01 | Done |  | CP96-477
| Questar |  | Phase I | Clay Basin Storage to Kanda | 59000 | 1997-08-01 | Done - at risk |  | CP96-820
| Trailblazer |  |  | Tomahawk to NGPL | 104500 | 1997-08-01 | Done |  | CP96-506 |  | 10 | 11663000 |  | 5200
| WIC |  |  | Kanda to Tomohawk | 192000 | 1997-08-01 | Done |  | CP96-288 |  |  | 39933100 |  | 28612
| Williams Natural Gas |  | Rawlins-Hesston | Wyoming (Wamsutter) to Kansas | 30000 | 1997-11-01 | Done |  | CP97-7 |  |  | 9300000
| KNE |  | Pony Express | Dull Knife to Kansas City | 120000 | 1997-12-01 | Done |  | CP96-477 |  |  | 154000000 | 804
| Questar |  | Clay Basin Expansion | Increase by 4.0 Bcf (by adding cushion gas) | 88000 | 1998-05-01 | Done |  | CP96-820 |  |  | 18000000 | 41 | 110
| Questar |  | Phase II | Clay Basin Storage to Kanda | 25000 | 1998-08-01 | Done - at risk |  | CP96-820 |  |  | 18000000 | 41 | 110
| CIG |  | Campo Lateral | Pickwick Lateral to Campo Station | 107000 | 1998-09-01 | Done |  | CP97-769
| CIG/PSCO |  | Front Range Pipeline | Cheyenne Compressor to Ft. St. Vrain | 269000 | 1998-11-01 | Done |  | CP98- |  |  | 25000000 | 53
| CIG/WIC |  | Powder River Lateral | Compression at Laramie & Cheyenne | 49000 | 1998-11-01 | Done |  | CP98-128 |  | 10 | 15000000 |  | 7380
| TransColorado |  | Phase II | Rio Blanco, CO to EP Blanco | 45000 | 1999-02-01 | Done |  | CP90-1777
| TransColorado |  | KN/Questar | NW Colorado to Red Cedar Lateral | 300000 | 1999-03-01 | Done |  | CP90-1777 |  |  | 170900000 | 295
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering | Gillette, WY to Glenrock, WY | 434000 | 1999-09-01 | Done |  |  |  |  | 43000000 | 106
| CIG |  | Wind River II | Lateral Expansion to NWPL/Kern (westward) | 100000 | 1999-10-01 | Dead
| KNE |  | Wyoming Pipeline Project | Wind & Powder River/Big Horn to Rockport | 450000 | 1999-10-01 | Dead |  |  |  |  | 110000000
| KN/Devon |  | Thunder Creek Gas Gathering | Gillette, WY to Glenrock, WY | 450000 | 1999-11-01 | Done |  |  |  |  | 100000000 | 126
| CIG |  | Medicine Bow Lateral | Glenrock to Rockport | 368000 | 1999-12-01 | Done | WGR/CMS/ECT/MCN/Devon |  |  |  | 78200000 | 150
| CMS/ENA/NBPL |  | Bighorn Gas Gathering LLC |  | 250000 | 1999-12-01 | Done
| Questar |  | Fidlar Compressor Station | Expands southern part of system | 58850 | 2000-06-01 | Done |  | CP00-41 |  |  | 3325000 |  | 4829
| CIG (WIC) |  | Medicine Bow Lateral II | Glenrock to Rockport | 120000 | 2000-08-01 | Done | WGR/CMS/ECT/MCN/Devon | CP99-624 |  |  | 12100000 | 6
| Burlington Resources/ECT |  | Lost Creek Gathering | Madden Field, WY to Wamsutter Plant | 275000 | 2000-10-01 | Done |  |  |  |  | 69500000 | 124
| Questar |  | Southern System Expansion | Southern System to Clay Basin/Kanda | 280000 | 2000-10-01 | Dead
| Questar |  | Wyoming Pipeline Project | Wyoming to Kanda (Pinedale Area Porduction) | 300000 | 2000-10-01 | Low
| Questar |  | Opal Connection | Seven miles to connect to Opal | 100000 | 2000-10-01 | Low
| CIG |  | Picketwire Lateral |  | 33000 | 2000-11-01 | Done
| Northwest Pipelne |  | Silver Gem Lateral | Filer, Idaho to Wells, Nevada | 90000 | 2000-11-01 | Dead
| CIG |  | Nixon Plant Lateral | CIG's Watkins Station to Colorado Springs | 85000 | 2000-12-02 | High
| Questar/CIG |  | Southern System Expansion | Price, UT to Kern in Salt Lake City Area | 272000 | 2001-06-01 | High |  |  |  | 10 | 80850915 | 75.6 | 9336
| CIG |  | Raton Basin Lateral Expansion | Morton Co, KS to Texas Co, OK | 85000 | 2001-10-01 | High |  | CP00-452 |  |  |  | 48
| CIG |  | Fort Morgan Storage Del Increase | Cheyenne Comp to Watkins Comp (Adams Co) | 100000 | 2001-11-01 | High |  | CP01-01
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering II | Gillette, WY to Glenrock, WY | 200000 | 2001-10-01 | Done |  |  |  |  | 27000000
| Paiute Pipeline |  | System Expansion | Wells, Nevada to Paiute @ Elko, Nevada | 90000 | 2001-11-01 | Dead | replaced
| Questar |  | Mainline 104 Expansion |  | 272000 | 2001-11-01 | Med | PD Recvd | CP00-68 |  |  | 80800000 | 75 | 9336
| Totem Storage |  | CIG/PSCO connected storage facility' | 9 Bcf MSQ | 250000 | 2001-11-01 | Low
| CIG |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 180000 | 2001-12-01 | Dead | replaced
| CIG (WIC) |  | Medicine Bow Lateral III | Glenrock to Rockport | 675000 | 2001-12-01 | High |  |  |  |  | 168000000 | 155 | 14340
| El Paso |  | Dumas Gas Transmission | Raton Basin to EPNG/NNG Dumas |  | 2002-04-01 | Med | [5 empty] | 185
| Trailblazer |  | Expansion/Extension | Glenrock to Gage | 300000 | 2002-07-01 | High |  |  |  |  | 58500000 | 149 | 44800
| CIG |  | Valley Line Expansion | Adams Co, CO to Nixon Lateral | 232000 | 2002-12-01 | High |  | CP01-45 |  |  | 72000000 | 119 | 4470
| CIG/Piaute Pipeline |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 250000 | 2003-01-01 | Low | [5 empty] | 400
| CIG |  | COCO Pipeline | Cheyenne Hub to Midcontinent PLs | 500000 | 2003-10-01 | Low
| Northern Border |  | Bison Pipeline | Gillete, WY to McCabe, MT | 500000 | 2003-11-01 | Med |  |  |  |  | 225000000 | 325
| CMS/Pennaco Energy |  | Powder River Lateral Feeder | Montana to Gillette, WY
| KN |  | Pathfinder Pipeline | Glenrock to Rockport
| Questar/Montana Power |  | Clear Creek Storage | 4 Bcf with 50,000/d Inj. | 35000 |  | High |  |  |  |  | 3300000
Michigan:
| Great Lakes |  | River Crossing Security | Zone 3 - Under the St. Clair River | 50000 | 1996-11-01 | Done |  | CP96-26 |  | 2 | 3900000
| Great Lakes |  | Security Loop I | Looping in Lower Michigan | 5000 | 1996-11-01 | Done |  | CP95-375 |  |  | 17400000 | 14 | 14800
| Great Lakes |  | Security Loop II | Looping in Delta and Mackinac Counties, MI | 5000 | 1998-11-01 | Done |  | CP96-297 |  |  | 44300000 | 25
| Great Lakes |  | Security Loop III | Looping in Delta and Mackinac Counties, MI | 0 | 1999-11-01 | Done |  | CP98-143 |  |  | 11000000 | 14
| CMS |  | Little Bear PL | Michigan Production | 75000 | 1996-08-01 | Done |  | Non-Jurisdictional |  |  | 13600000
| ANR |  | Link Pipeline | Michigan to Consumers of Toronto | 150000 | 1996-11-01 | Done |  | CP93-564
| ANR |  | Michigan Leg South Looping | Bridgman to Sandwich Compressors | 135000 | 1997-06-01 | Done |  | CP96-641 |  |  | 18000000 | 12
| Great Lakes |  |  | Emerson to St. Clair | 126000 | 1998-11-01 | Done | 30000 | CP96-647 |  |  | 149000000 | 72 | 14800
| Great Lakes |  | 300 Expansion | Emerson to St. Clair | 304000 | 2000-11-01 | Dead |  | CP98-309 |  |  | 620000000
| Great Lakes |  | Nexus 98/99 | Emerson to St. Clair | 2000000 | 1999-11-01 | Dead
Midcontinent:
| Viking |  |  | Emerson to NNG | 20000 | 1996-11-01 | Done |  | CP96-32 |  |  | 8400000
| TransOk |  | Trident Ambrose Plant | Cushing to Blackwell, OK | 300000 | 1997-04-01 | Done |  | Non-Jurisdictional |  |  | 35000000
| TransOk |  |  | Bradley to Atoka, OK (Texoma) | 300000 | 1997-07-01 | Dead |  | Non-Jurisdictional |  |  | 40000000
| Viking |  |  | Emerson to NNG | 61300 | 1997-11-01 | Done |  | CP97-93 |  |  | 27900000
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 244000 | 1997-11-01 | Done |  | CP97-25 |  |  | 102000000 | 50 | 41000
| PEPL |  | Tuscola to Illinois | Replaced by Spectrum Project | 150000 | 1997-11-01 | Dead
| Williams Natural Gas |  | SW Missouri Expansion | waiting on Missouri Comm approval | 15610 | 1999-05-01 | Done |  | CP96-726 |  | 20 |  | 12.5
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 32000 | 1998-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 31000 | 1999-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 21000 | 2000-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | East Leg 2000 | Replaced with Ill/WI Express | 450000 | 2000-11-01 | replaced
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 20000 | 2001-11-01 | Done |  | CP97-25
| Williams Natural Gas |  | St, Louis Access | Conversion of 200 mile petroleum pipeline | 28000 | 1998-10-01 | Done
| Northern Natural Gas |  | NNG Zone E/F Koch | NNG Market Area Expansion (Rosemount) | 20000 | 1998-11-01 | Done - At Risk |  | CP98-132 |  |  | 9400000
| Viking |  |  | Minnesota Looping | 28000 | 1999-11-01 | Done |  | CP98-761 |  |  | 21300000 | 45
| Viking |  | 2001 Expansion | Emerson to Marshfield |  | 2001-11-01 | Low |  |  |  |  | 3900000 | 5.6
| Viking |  | Hallock Looping | Emerson to Hallock Compressor | 0 | 2001-11-01 | High |  | CP0-61 |  |  | 3200000 | 5.6
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 650000 | 2001-11-01 | Dead
| Williams Natural Gas |  | Ottowa Compressor Station | Compression Upgrades/Additions | 44200 | 2001-06-01 | Done |  | CP00-82 |  |  | 9700000 | 1.5
| Williams Natural Gas |  | Blackwell-Cotton Valley Pipeline | Compression Upgrades/Additions | 55000 | 2001-07-01 | High | [5 empty] | 37
| Williams Natural Gas |  | Western Farmers | Cheyenne Hub to Hugoton | 540000 | 2003-11-01 | Low | [5 empty] | 400 | 13000
| MRT |  | New St. Louis Lateral | Horseshoe Lake IL, to NGPL @ Clinton Co., IL | 230000 | 2002-06-01 | Low
| ANR |  | Badger Generating Lateral (PG&E) | Kenosha Co, WI | 210000 | 2003-05-01 | High |  | CP01-79 |  |  | 19500000 | 9.5
Canada:
| TCPL |  | Conventional 96 | Alberta to Ontario/Export | 150000 | 1996-11-01 | Done | 15000 |  |  |  | 489000
| NovaGas Clearinghouse |  | Pesh Creek Pipeline | British Columbia to Alberta | 60000 | 1997-05-01 | Done |  |  |  |  | 2900000
| Alberta Pipeline Project |  | CU Gas Ltd, Amoco & Shell Can. | Central Alberta to Carbon Hub to Empress | 1200000 | 1998-11-01 | Dead |  |  |  |  | 326868598.8233
| Alberta Pipeline Project |  | Phase II | Kaybob region extension | 1000000 | 1999-11-01 | Dead |  |  |  |  | 326868598.8233
| TCPL |  | Conventional 97 | Alberta to Ontario/Export | 286700 | 1997-11-01 | Done | 20000 |  |  |  | 900000000
| Penn West Petroleum, Ltd. |  | Wildboy Project | Wildboy Field (Fort Nelson, BC) to NOVA | 10000 | 1999-11-01 | Done |  |  |  |  | 15000000 | 40
| Foothills |  | NBPL Expansion | Nova to NBPL | 698900 | 1998-12-01 | Done | 15000 |  |  |  | 125000000 | 71 | 51000
| TCPL |  | Nexus 98 | Alberta to Ontario/Export | 2000000 | 1998-11-01 | Dead |  |  |  |  | 1190000000
| TCPL |  | Conventional 98 | 58.5 Domestic/397.4 Export | 455900 | 1998-11-01 | Done | 33539 |  |  |  | 877600000
| Nova |  | NBPL Expansion | Alberta to Foothills | 500000 | 1998-12-01 | Done | 15000 |  |  |  | 365400000
| Union Gas |  |  | System-wide |  | 1998-11-01 | Dead
| TCPL |  | Nexus 99 | Alberta to Ontario/Export | 938000 | 1999-11-01 | Dead
| TCPL |  | Conventional 99 | 108.0 Expansion/44.0 turnback | 108000 | 1999-11-01 | Done |  |  |  |  | 404500000
| TransQuebec & Martimies PL |  | TQM Extension | Lachenaie, PQ to East Hereford, NH | 194000 | 1998-11-01 | Done |  |  |  |  | 175000000 | 135
| TCPL |  | TransVoyageur Transmission | Empress, Alberta to Emerson, Manitoba | 2000000 | 1999-11-01 | Dead
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 212200 | 1998-11-01 | Dead |  |  |  |  | 1000000000
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 285000 | 1999-11-01 | Dead |  |  |  |  | 1000000000
| Sable Offshore Energy Project |  | Maritimes and Northeast feed | Nova Scotia/New Brunswick to US | 400000 | 1999-12-01 | Done
| BC Gas |  | Alberta Southern Crossing | Alberta to BC interior | 105000 | 2000-11-01 | High | PG&E and BC Hydro |  |  |  | 376000000 | 194
| TCPL/ANG Pipeline |  | Kootenay Pacific Pipeline | Yahk, BC to Vancouver/Sumas | 550000 | 2000-11-01 | Dead |  |  |  |  | 530000000
| Westcoast |  | Sunshine Coast Regional Dist | MSQ | 3000000 | 2000-05-01 | Dead |  |  |  |  | 87000000
| Crowsnest Pipeline |  | CU Gas Ltd and Shell Canada | Waterton Plant to ANG station 4 (BC) | 150000 | 1998-11-01 | Dead
| TCPL/Westcoast/CGT/MCN |  | Canadian Millenium | Dawn to Lake Erie | 700000 | 2002-11-01 | on hold |  |  |  |  | 700000000
| Westcoast |  | Howe Sound LNG | MSQ | 3000000 | 2001-11-01 | Low |  |  |  |  | 72000000
| Palliser |  | Settlement reached with Nova | Nightingale, AB to Empress | 1200000 |  | Dead
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Suffield, Alberta to TCPL/Burstall, Sask | 200000 | 1998-12-01 | Done | NEB approval 8/98 |  |  |  | 26200000
| ANG/BC Pipeline |  | BC Pipeline (Southern Crossing) | Cranbrook to Kingsgate to Oliver | 100000 | 2000-12-01 | Done |  |  |  |  | 379000000 | 200
| Westcoast |  | West Liard - NWT Pipeline | West Liard valley to Northern BC (Alliance) | 50000 | 2000-05-01 | Done
| Maritimes & Northeast |  | New Brunswick to Quebec lateral | M&NE mainline to Edmundston, NB | 184000 | 2004-11-01 | Med |  |  |  |  | 179000000
| Gaz Metropolitain/Enbridge |  | Trans-Quebec & Maritimes | Edmundston, NB to Quebec City (Riviere-du-Loup) | 184000 | 2004-11-01 | Med | [5 empty] | 164
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Burstall, Sask to SW Alberta
| Aiken Creek Storage |  | Unocal Canada | Increase working capacity to 80 Bcf |  | 2001-08-01 | High | [6 empty] | 18500
| TCPL/Westcoast |  | Canadian Arctic Pipeline | Mackenzie Delta/Canadian Arctic to AB/BC | 4000000 |  | Low |  |  |  |  | 6000000000
| BC Hydro/PG&E Trading |  | Southern Crossing Pipeline | Cranbrook to Kingsgate to Oliver | 275000 |  | Med
| Ricks Nova Scotia |  | Ladyfern Pipeline | NE BC to Nova's Owl Lake South Station | 30000 | 2001-03-01 | High | NEB approval 1/01 |  |  |  | 3000000 | 7.5
| Nova/ANG |  | PGT Expansion | A/BC to Kingsgate | 216000 | 2002-11-01 | High
Alaska:
| TransAlaska Natural Gas Systems |  | Arco/BP/Exxon/Phillips/Mobil/Hess/Unocal | Prudhoe Bay delevelopment (LNG) | 15000 |  | Low
| ANGTS |  | TCE/Westcoast | Alaskan Highway to Boundry Link | 2500000 | 2007-11-01 | Low |  |  |  |  | 6000000000 | 1700
| Arctic Resources (ARC) |  | Native Organizations (Hoagland's) | North Slope to Mackenzie to Alta | 1500000 | 2007-11-01 | Low |  |  |  |  | 5300000000 | 1200
| Enbridge Consortium |  | Mackenzie Delta | Mackenzie to Fort Saskatchewan | 1200000 | 2007-11-01 | Low |  |  |  |  | 2850000000 | 1250
Chicago:
| NGPL |  |  | Gage to Chicago |  | 1997-11-01 | Dead
| NGPL |  | Chicago | Harper to Chicago | 110000 | 1998-11-01 | Done | 10000 | CP96-27 |  |  | 24000000 | 5 | 9000
| Northern Border |  | Expansion | Monchy to Harper | 700463 | 1998-12-01 | Done | 55000 | CP95-194 |  |  | 457900000
| Northern Border |  | Extension | Harper to Chicago | 663050 | 1998-12-01 | Done | 45000 | CP95-194 |  |  | 338900000 | 793 | 293000
| ANR |  | Wisconsin Loop Expansion Proj | 11.7 miles of 30" looping from Joliet to WI | 116000 | 1999-03-01 | Done |  | CP97-765 |  |  | 24000000 | 11
| Viking, TCPL & NICOR |  | Viking Voyaguer | Marshfield, WI to Minn, ND, Wisc and Chicago | 1400000 | 1999-11-01 | Dead |  | CP98-60/62/64/65 |  |  | 1200000000 | 773
| ANR |  | Wisconsin Loop Expansion I | Comp. additions at Woodstock | 109000 | 2000-11-01 | Done |  | CP99-241 |  |  | 23800000 | 0 | 20000
| CMS |  | TriState Pipeline | Chicago to Dawn | 650000 | 2000-11-01 | Dead |  | CP99-63 |  |  | 361000000 | 226
| NGPL |  | Hub America | Chicago to Lebanon/TETCO M3 | 100000 | 2000-11-01 | High |  |  | rolled-in
| Alliance |  | Fort St John, BC to Chicago | Canadian Side | 1325000 | 2000-12-01 | Done |  |  |  |  | 1600000000 | 1445
| Alliance |  | Fort St John, BC to Chicago | US Side |  | 2000-12-01 | Done |  | CP97-168 |  |  | 1400000000 | 887 | 320000
| Alliance |  | Chicago Portion | Aux Sable Liquids Plant |  | 2000-12-01 | Done |  |  |  |  | 365000000
| Enbridge/MCN/Westcoast |  | Vector | Chicago to Dawn (with NIPSCO/Crossroads) | 700000 | 2000-12-01 | Done |  | CP98-131 |  | 10 | 443000000 | 270 | 60000
| TETCO |  | PSI Wabash Power Lateral | Midwestern Int at Vigo County, Ind | 215000 | 2001-04-01 | High |  |  |  |  | 8000000 | 9
| ANR |  | Wisconsin Loop Expansion II | Comp. additions at Janesville/Weyauwega | 85000 | 2001-11-01 | Done |  | CP99-341 |  |  |  | 3 | 3000
| Crossroads |  | NBPL connection | 25 mile expansion to NGPL/NBPL | 485000 | 2001-11-01 | Low |  |  |  |  | 35000000 | 25
| Enbridge/MCN/Westcoast |  | Vector Expansion | Compression | 300000 | 2001-11-01 | Med |  |  |  | 3
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 650000 | 2001-11-01 | Dead
| Midwestern |  | PL Reversal | Chicago to Tennessee | 500000 | 2001-11-01 | on hold
| Northern Border |  | Chicago Extension | Chicago to NIPSCO | 198300 | 2001-11-01 | High |  | CP99-21 |  |  | 93000000 | 34 | 30500
| KN Energy/NICOR |  | Horizon | Chicago | 380000 | 2002-04-01 | Med | PD recd | CP00-129 |  | 10 | 75000000 | 28.5 | 8900
| Peoples/Coastal |  | Whitecap Energy - Land | ANR @ Crete, IL to Southeastern WI | 1500000 | 2002-04-01 | Low | 30000 |  |  |  | 334000000 | 21
| NGPL |  | St Louis Lateral |  | 300000 | 2002-06-01 | Med | 311 fac. |  |  |  | 35000000 | 47
| ANR |  | Supply Link | Sandwich Compressor to Defiance | 750000 | 2002-11-01 | Low |  | CP97-319 |  |  | 124800000 | 73 | 15000
| ANR |  | Wisconsin Loop Expansion III | Chicago to Wisconsin, IL and MN | 100000 | 2002-11-01 | Med | 30000
| CMS/WICOR/Viking |  | Guardian Pipeline | Chicago to Wisconsin | 750000 | 2002-11-01 | Done |  | CP00-36 | FEIS/PD/Cert rcvd |  | 224000000 | 147 | 24000
| Peoples/Coastal |  | Whitecap Energy - Lake | ANR @ Crete, IL to Southeastern WI | 1500000 | 2003-11-01 | Low | [5 empty] | 90
Appalachian:
| ANR |  | Replaced by Independence | Chicago to Lebanon | 250000 |  | Dead
| Columbia Gas |  | Storage | Storage Withdrawal | 210000 | 1997-11-01 | Done |  | CP96-213 |  | 15 | 270000000 | 42 | 45699
|  |  |  | Transport increase | 42500 | 1997-11-01 | Done
| Columbia Gas |  | Storage | Storage Withdrawal | 126000 | 1998-11-01 | Done |  | CP96-213 |  | 15
|  |  |  | Transport increase | 25500 | 1998-11-01 | Done
| Columbia Gas |  | Storage | Storage Withdrawal | 80000 | 1999-11-01 | Done |  | CP96-213 |  | 15
|  |  |  | Transport increase | 17000 | 1999-11-01 | Done
| Columbia Gas/TETCO |  |  | Capacity Lease | 141500 | 1997-11-01 | Done |  | CP96-559 |  | 17 | 63200000
| TETCO/Dominion |  | WinterNet | Oakford Storage to CNG (Phased) | 64000 | 1997-11-01 | Dead |  | CP96-606 |  | 24 | 18589000
| TETCO/Dominion |  | SS-E | Oakford Storage to CNG 4.6 Bcf | 70000 |  |  |  | CP96-607 |  | 25 | 18589001
| Dominion |  |  | Transport increase | 102820 | 1997-11-01 | Done |  | CP96-492 |  |  | 55929000 | 36 | 13600
| NE Hub Partners |  | Tioga Storage | Pennsylvania 6.0 Bcf | 500000 | 1999-11-01 | High
| Dominion |  | Bath Petroleum | Storage Withdrawal | 168320 | 1999-11-01 | Dead |  | CP96-492
| Dominion |  | Capstone Project | South Webster to Northern CNG Gates (Tenn replacement) | 0 | 2001-11-01 | High |  | CP00-64 |  |  | 63502000 | 13 | 20250
| Dominion |  | Leidy Transportation Project | North Points (Empirer/Tenn/Iroquois) to Liedy | 300000 | 2001-11-01 | High
| Dominion |  | High Deliverability Storage | Salt Like Firm Storage (12 cycles) |  | 2002-11-01 | Low
Note on B161: ECT: Trunkline, Marathon Ashland Petroleum and TEPPCO Partners LP
Note on B420: ECT: one third ownership each
Note on D109: julie gomez: Uses Tennessee 500 line capacity
Note on D118: ECT: The LNG will come from output from the planned second and third trains of Atlantic LNG project in Trinidad and Tobago.
Note on D211: Julie Gomez: Serves 620 MW Presidente Juarez power plant
Note on D378: ECT: Producers include Chevron Canada, Canadian Forest, Ranger, Purcell, Anderson Exploration and Talisman
Note on E61: jgomez: 19,100 via National Fuel lease from Niagara, the rest is from the Gulf Coast.
Note on E70: jgomez: 19,100 via National Fuel lease from Niagara, the rest is from the Gulf Coast.
Note on E118: ECT: Can take delivery of 80 Bcf annually, or 220,000 M/d fo LNG starting mid 2002
Note on E122: ECT: Southern Company's capacity is in the name of Georgia Power for the Wansley Plant
Note on E131: ECT: Scana would extend the system 300 miles to the proposed ethanol facilities and power plants in Onslow, Greene and Martin Counties, NC
Note on E217: ECT: To serve the existing 150MW Hermosillo Plant and a proposed 225MW expansion plant. The 12 mile east branch line will cross the border near Douglas and serve the proposed 225MW El Fresnal/Nogales plant.
Note on E219: Julie Gomez: Will interconnect with Sempra'a Rosarito Pipelien south of Tijuana
Note on E235: ECT: Includes 50,000/d of capacity from Blanco to Thoreau
Note on E242: ECT: The Canadian portion of the project would originate on the international border in Boundry Pass, Strait of Georgia and interconnect with the existing Centra transmission system at a point south of Duncan, BC. The Canadian portion would be about 31 miles long with about 23 miles offshore and eight miles onshore. The 16" pipe would move 100,000 M/d and be in service 11/2002
Note on E420: ECT: Proposed to connect to Alliance, NBPL, NGPL, Midwestern and Joliet Hub
Note on F20: jgomez: Dighton Power Assoc 33,000/d from Mendon to Dighton Plant
Note on F22: jgomez: Shippers include: Boston Gas 35000/d, ConEd 20000/d and ProvGas 95000/d.
Note on F25: jgomez: Shippers include: Aquila 16819/d, El Paso Energy 20000/d and FP&L 19100/d
Note on F32: jgomez: Tiverton Power Accos 46000/d Brookfield to Plant
Note on F36: jgomez: Lake Road Generating 146000/d from mainline to plant
Note on F40: jgomez: ANP Bellingham Energy 110,000/d Mainline Int to Plant
Note on F44: jgomez: Casco Bay 105000/d from Ediington to Veazie Plant
Note on F45: jgomez: National Fuel Distribution 30,000/d from Lamont to Roystone
Note on F53: Julie Gomez: Could be expanded to 1.0 Bcf/d. NJ Natural controls Shipper is eCorp.
Note on F54: jgomez: Sithe Power Marketing 140000/d lateral only
Note on F60: jgomez: Shippers inlcude: ANP 50000/dand El Paso Gas Svs 123000/d
Note on F62: Julie Gomez: Willaims 100,000/d, ConEd 30,000/d,Aquila 25,000/d, ConEd Energy 10,000/d and St Lawrence Cement 1,000/d
Note on F65: Shippers inlcude: Sithe 70,000/d, Southern Kendall 35,000/d Southern Connecticut 20,000 Prov Gas 500/d Mass Water Resource Auth 25,000/d and TETCO 80,000/d
Note on F67: jgomez: Shippers include: Keyspan Ravenswood 60000/d, Mirant Corp 60,000/d, Astoria Generating (Orion) 60,000, VEPCO 20,000/d and ConEd 30000.
Note on F72: jgomez: Capacity will be 760,000/d in the US and 930,000/d in Canada
Note on F74: jgomez: Virginia Power 100,000/d and PPL 30,000/d
Note on F75: ECT: DirectLink (an affiliate) has contracted for 500,000/d. Dynegy has contracted for 350,000/d.
Note on F76: Julie Gomez: 125,000 is incremental capacity and the remaining 489,628 would be leased back to Transco.
Note on F103: ECT: Southern Company 40,000/d, Visy Paper 4500/d and AGL 61160/d Santee Cooper 80,000/d, Sylacaugh Utilities Board 4000/d, MGAG 14,439/d
Note on F104: jgomez: Shippers Include: Entergy Miss 200000/d and Warren Power 85000/d.
Note on F109: julie gomez: Southern Co bought 7Bcf of storage at Petal and can deliver to Transco, SoNat, Koch and Deston
Note on F113: julie gomez: UCG 27,500, Citizens, APG Industries and City of Pulaski
Note on F115: jgomez: Shippers inlcude: CE Minerals 782/d, City of Lenox 12/d, Coral Energy 6646/d, Interconn 6646/d, Milwhite 80/d, MGAG 1270/d and P&G Paper 1564/d.
Note on F116: jgomez: Shippers include Coral 6,646/d Interconn 6646/d, P&G Paper 1,564/d MGAG 1270/d CE Mineral 782/d milwhite 80/d and City of Lenox 12/d.
Note on F117: jgomez: AGL signed up for 200,000/d for 20 years.
Note on F118: ECT: 675,000 Peak Day Deliverability
Note on F119: ECT: FPL 101142/d. Southern 60937/d, TECO 180,000/d, JEA 14000/d, Tallahassee 2677/d, Peoples 1504/d, US Agri-Chem 115/d
Note on F122: ECT: Southern Company 140000/d and CP&L 75000/d
Note on F124: ECT: 15 year contracts with Southern Co 284,050 South Carolina PL Corp 50,000 LaGrange, GA 1,750 Phase I of 88,150 will start June 1, 2002
Note on F242: ECT: BC Hydro has sined up for 97,000/d of capacity Connects two 250MW plants on Shawnigan Lake (81,000/d) and the local LDC Centra Gas
Note on F244: ECT: PITCO's 60% of Max DQ
Note on F246: ECT: 400,000/d MDIQ 500,000/d MDWQ
Note on F255: jgomez: 170,000 /d to Newport for 52 years and 30,000/d to Calpine for 30+ years
Note on F260: jgomez: RedHawk 410,000/d Duke 210.000/d
Note on F276: ECT: WGR anchored
Note on F287: jgomez: 171,000 capacity for the public
Note on F295: julie gomez: Primero Gas Marketing and El Paso Energy Raton LLC
Note on F299: jgomez: Shippers include CIG Resources 150,000/d, Questar Gas 100,000/d and 40,000 Texaco
Note on F304: jgomez: Shippers include: Western Gas 57,500/d, ENA 41,000/d, CMS 100,000/d, Barrett 70,000/d, Devon Energy 33,000/d and Pennaco 22,500/d.
Note on F305: jgomez: Shippers include Front Range Power 85,000/d, PSCO 178,000/d
Note on F338: ECT: LaClede subscribed
Note on F344: ECT: MEP Pleasant Hill Generating Unit (600MW) and Tyson Foods
Note on F345: ECT: Empire District Electric Company State Line Plant in Jasper Co, MO 500 MW (CC)
Note on F377: ECT: Volume in question: 250,000/d or 600,000/d ??
Note on F401: ECT: 59,000/d contracted to three shippers and an additional 25,000/d as of 11/1/01
Note on F415: ECT: Nicor is 300,000/d
Note on F418: Julie Gomez: DirectLink 507,000/d (contract not allowed by FERC), Dynegy 303,900/d, Cogentrix 101,300/d, Gleason 80,000/d and Duke 50,700/d
Note on F420: ECT: WICOR is 650,000/d
Note on G243: jgomez: Will take 6 to 9 months after FERC ruling to get this in service
Note on M53: Julie Gomez: ecorp Marketing (an affiliate of Central New York) has 400,000/d on the lateral and 90,000/d on Tennessee's 300 line
Note on M56: ECT: AES signed for 20 year 10 month contract at a negotiated rate of $.0425 plus fuel
Note on O408: julie gomez: PSI (Cynergi) will reimburse Midw for $6.3 mil
Note on P108: ECT: 30" pipeline

## By Pipe
ENRON NORTH AMERICA |  |  |  | 2026-07-29 07:08 |  | expands2
PIPELINE EXPANSION UPDATE
Project
[5 empty] | Daily | Start |  | ECT |  |  | Term | Cost of
| Pipeline |  | Project | Path | Quantity | Date | Probability | Position | Docket | Pricing | Years | Project | Miles | HP
| AEC |  | Wild Goose Storage | PG&E/Scramento Area | 14.0 Bcf | 1999-04-01 | Done |  | Non-Jurisdictional
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Suffield, Alberta to TCPL/Burstall, Sask | 200000 | 1998-12-01 | Done | NEB approval 8/98 |  |  |  | 26200000
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Burstall, Sask to SW Alberta
| Aiken Creek Storage |  | Unocal Canada | Increase working capacity to 80 Bcf |  | 2001-08-01 | High | [6 empty] | 18500
| Alberta Pipeline Project |  | CU Gas Ltd, Amoco & Shell Can. | Central Alberta to Carbon Hub to Empress | 1200000 | 1998-11-01 | Dead |  |  |  |  | 326868598.8233
| Alberta Pipeline Project |  | Phase II | Kaybob region extension | 1000000 | 1999-11-01 | Dead |  |  |  |  | 326868598.8233
| Algonquin |  | EMI Dighton, MA Plant | Delivery off mainline to Dighton Plant | 33000 | 1999-03-01 | Done |  | CP98-99 |  |  | 4662000 | 1.5 | 900
| Algonquin |  | EMI Tiverton Plant | Compressor Upgrades & mainline work | 46000 | 2000-06-01 | Done |  | CP99-46 |  |  | 13949960 | 15.98 | 900
| Algonquin |  | Lake Road Plant | Mainline (Putnam Co) to Killingly CT Plant | 146000 | 2000-08-01 | Done |  | CP99-271 |  |  | 4700000 | 1.8 | 0
| Algonquin |  | ANP Bellingham Lateral | Mainline (Norfolk Co, MA) to Bellingham Plant | 110000 | 2000-10-01 | Done |  | CP98-100 |  |  | 4593000 | 1.1 | 0
| Algonquin |  | Sithe Energy Lateral | Lateral from Canton, MA to Plant (Fore River) | 140000 | 2001-09-01 | High |  | CP 00-34 | AFT-CL | 20 | 32021000 | 7.4 | 0
| Algonquin |  | HubLine | Beverly, MA (MNE) to Weymouth, MA | 300500 | 2002-11-01 | Med |  | CP01-5 |  |  | 114048000 | 34.8 | 0
| Algonquin LNG |  | Providence, RI tie to Algonquin | Northeast City Gates (currently 100,000) | 150000 | 1999-11-01 | Done |  | CP99-113 |  |  | 10705000
| Alliance |  | Fort St John, BC to Chicago | Canadian Side | 1325000 | 2000-12-01 | Done |  |  |  |  | 1600000000 | 1445
| Alliance |  | Fort St John, BC to Chicago | US Side |  | 2000-12-01 | Done |  | CP97-168 |  |  | 1400000000 | 887 | 320000
| Alliance |  | Chicago Portion | Aux Sable Liquids Plant |  | 2000-12-01 | Done |  |  |  |  | 365000000
| ANG/BC Pipeline |  | BC Pipeline (Southern Crossing) | Cranbrook to Kingsgate to Oliver | 250000 | 2000-12-01 | Done |  |  |  |  | 379000000 | 200
| ANGTS |  | TCE/Westcoast | Alaskan Highway to Boundry Link | 2500000 | 2007-11-01 | Low |  |  |  |  | 6000000000 | 1700
| ANR |  | Link Pipeline | Michigan to Consumers of Toronto | 150000 | 1996-11-01 | Done |  | CP93-564
| ANR |  | Michigan Leg South Looping | Bridgman to Sandwich Compressors | 135000 | 1997-06-01 | Done |  | CP96-641 |  |  | 18000000 | 12
| ANR |  | Katy Project | Katy to Eunice | 200000 | 1999-11-01 | Dead
| ANR |  | LS Power Batesville lateral | Panola, MS to Tennessee 20" | 235000 | 2000-06-01 | Done |  | CP98-801 |  |  |  | 15
| ANR |  | Mountaintop | Brownsville Compressor to Altanta, GA | 500000 | 2001-11-01 | Low
| ANR |  | Supply Link | Sandwich Compressor to Defiance | 750000 | 2002-11-01 | Low |  | CP97-319 |  |  | 124800000 | 73 | 15000
| ANR |  | Conch Project | EI 63 to Patterson | 461000 | on hold | FERC ordered at risk |  | CP97-71 |  |  | 51200000 | 37 | 461
| ANR |  | Replaced by Independence | Chicago to Lebanon | 250000 |  | Dead
| ANR |  | Wisconsin Loop Expansion Proj | 11.7 miles of 30" looping from Joliet to WI | 116000 | 1999-03-01 | Done |  | CP97-765 |  |  | 24000000 | 11
| ANR |  | Wisconsin Loop Expansion I | Comp. additions at Woodstock | 109000 | 2000-11-01 | Done |  | CP99-241 |  |  | 23800000 | 0 | 20000
| ANR |  | Wisconsin Loop Expansion II | Comp. additions at Janesville/Weyauwega | 85000 | 2001-11-01 | Done |  | CP99-341 |  |  |  | 3 | 3000
| ANR |  | Wisconsin Loop Expansion III | Chicago to Wisconsin, IL and MN | 100000 | 2002-11-01 | Med | 30000
| ANR/Leviathan/NGPL |  | East Breaks Gathering | Alaminos Canyon 25 to HIOS HI A-573 (Diana/Hoover) | 400000 | 2000-07-01 | Done |  |  |  |  | 90000000 | 85
| Arctic Resources (ARC) |  | Native Organizations (Hoagland's) | North Slope to Mackenzie to Alta | 1500000 | 2007-11-01 | Low |  |  |  |  | 5300000000 | 1200
| Bay Gas |  | Mobile County Expansion |  |  | 2001-06-01 | Med | [5 empty] | 18
| BC Gas |  | Alberta Southern Crossing | Alberta to BC interior | 105000 | 2000-11-01 | High | PG&E and BC Hydro |  |  |  | 376000000 | 194
| BC Hydro/PG&E Trading |  | Southern Crossing Pipeline | Cranbrook to Kingsgate to Oliver | 275000 | 275000 | Med
| Burlington Resources/ECT |  | Lost Creek Gathering | Madden Field, WY to Wamsutter Plant | 275000 | 2000-10-01 | Done |  |  |  |  | 69500000 | 124
| Canyon Express |  | Total/Fina/Elf | Aconcaqua/KingsPeak/CandemHills to EMP 261 | 500000 | 2001-05-01 | Med
| Chandeleur Pipe Line |  | Chevron | Venice Plant to Destin @ Pascagoula | 50000 |  | Low
| CIG |  | Parachute Creek lateral | Uinta Lateral to Parachute | 37000 | 1996-09-27 | Done
| CIG |  | Wind River | Lateral Expansion | 68000 | 1997-08-01 | Done |  | CP96-289 |  |  | 10844200 |  | 10566
| CIG |  | Campo Lateral | Pickwick Lateral to Campo Station | 107000 | 1998-09-01 | Done |  | CP97-769
| CIG |  | Wind River II | Lateral Expansion to NWPL/Kern (westward) | 100000 | 1999-10-01 | Dead
| CIG |  | Medicine Bow Lateral | Glenrock to Rockport | 368000 | 1999-12-01 | Done | WGR/CMS/ECT/MCN/Devon |  |  |  | 78200000 | 150
| CIG |  | Pickerwire Lateral |  | 33000 | 2000-11-01 | Done
| CIG |  | Nixon Plant Lateral | CIG's Watkins Station to Colorado Springs | 85000 | 2000-12-02 | High
| CIG |  | Raton Basin Lateral Expansion | Morton Co, KS to Texas Co, OK | 85000 | 2001-10-01 | High |  | CP00-452 |  |  |  | 48
| CIG |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 180000 | 2001-12-01 | Dead | replaced
| CIG |  | Valley Line Expansion | Adams Co, CO to Nixon Lateral | 232000 | 2002-12-01 | High |  | CP01-45 |  |  | 72000000 | 85 | 4470
| CIG |  | COCO Pipeline | Cheyenne Hub to Midcontinent PLs | 500000 | 2003-10-01 | Low
| CIG (WIC) |  | Medicine Bow Lateral II | Glenrock to Rockport | 120000 | 2000-08-01 | Done | WGR/CMS/ECT/MCN/Devon | CP99-624 |  |  | 12100000 | 6
| CIG (WIC) |  | Medicine Bow Lateral III | Glenrock to Rockport | 675000 | 2001-12-01 | High |  |  |  |  | 168000000 | 155 | 14340
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering | Gillette, WY to Glenrock, WY | 434000 | 1999-09-01 | Done |  |  |  |  | 43000000 | 106
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering II | Gillette, WY to Glenrock, WY | 200000 | 2001-10-01 | Done |  |  |  |  | 27000000
| CIG/Piaute Pipeline |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 250000 | 2003-01-01 | Low | [5 empty] | 400
| CIG/PSCO |  | Front Range Pipeline | Cheyenne Compressor to Ft. St. Vrain | 269000 | 1998-11-01 | Done |  | CP98- |  |  | 25000000 | 53
| CIG/WIC |  | Powder River Lateral | Compression at Laramie & Cheyenne | 49000 | 1998-11-01 | Done |  | CP98-128 |  | 10 | 15000000 |  | 7380
| CMS |  | Little Bear PL | Michigan Production | 75000 | 1996-08-01 | Done |  | Non-Jurisdictional |  |  | 13600000
| CMS |  | TriState Pipeline | Chicago to Dawn | 650000 | 2000-11-01 | Dead |  | CP99-63 |  |  | 361000000 | 226
| CMS/ENA/NBPL |  | Bighorn Gas Gathering LLC |  | 250000 | 1999-12-01 | Done
| CMS/Pennaco Energy |  | Powder River Lateral Feeder | Montana to Gillette, WY
| CMS/WICOR/Viking |  | Guardian Pipeline | Chicago to Wisconsin | 750000 | 2002-11-01 | High | PD recd | CP00-36 | FEIS recd |  | 224000000 | 147 | 24000
| Columbia Gas |  | Storage | Storage Withdrawal | 210000 | 1997-11-01 | Done |  | CP96-213 |  | 15 | 270000000 | 42 | 45699
| Columbia Gas |  | Storage | Storage Withdrawal | 126000 | 1998-11-01 | Done |  | CP96-213 |  | 15
| Columbia Gas |  | Storage | Storage Withdrawal | 80000 | 1999-11-01 | Done |  | CP96-213 |  | 15
| Columbia Gas/CMS/MCN/Westcoast |  | Millennium | Chicago to New York City | 650000 | 2002-11-01 | Low |  | CP98-150 |  |  | 678000000 | 443
| Columbia Gas/TETCO |  |  | Capacity Lease | 141500 | 1997-11-01 | Done |  | CP96-559 |  | 17 | 63200000
| Columbia Gulf |  | Onshore Louisiana | Eastern Legs to Rayne (3 phases) | 400000 | 1998-11-01 | Dead
| Columbia Gulf |  | Mainline 99 | Rayne to Leach (3 compression upgrades) | 315000 | 1999-12-01 | Done | 27%LDC/63%Mktg/10%Indust |  |  |  | 38000000
| Columbia Gulf |  | Sun Star (SP & WD to GI) | 2 new 24" laterals and one 30" mainline | 660000 | 1999-12-01 | Low | [5 empty] | 56
| Columbia Gulf |  | Baxter Wilson & Warren Power | Warren Co., MS | 285000 | 2001-05-01 | High
| Columbia Gulf |  | Vicksburg Lateral to Entergy Plants | Mainline (Richland Parish, LA) to Baxter Wilson Plant | 285000 | 2001-05-01 | High |  | CP01-28 |  |  | 20148000 | 36.83 | 0
| Continental States Peaking Svs |  | El Paso/Tennessee/MCN | Maryland/Delaware LNG 2.0 Bcf MSQ | 200000 | 2000-11-01 | Dead |  |  |  |  | 45000000
| Coral Mexico |  | New PEMEX Line/Border Crossing | Kleburg County to Hildago Co., TX | 300000 | 2000-11-01 | Done |  | CP99-564 |  |  | 30000000 | 104
| CP&L |  | Iredell-Richmond Pipeline | Transco Stn 150 (Sundance) to CP&L Richmond Co | 200000 | 2001-06-01 | Med |  |  |  |  | 100000000 | 82
| Crossroads |  | NBPL connection | 25 mile expansion to NGPL/NBPL | 485000 | 2001-11-01 | Low |  |  |  |  | 35000000 | 25
| Crowsnest Pipeline |  | CU Gas Ltd and Shell Canada | Waterton Plant to ANG station 4 (BC) | 150000 | 1998-11-01 | Dead
| Dauphin Island Gath System |  | Phase I | Main Pass 225 to AST 73 | 200000 | 1998-04-01 | Done |  | CP97-301 |  |  | 54000000 | 63
| Dauphin Island Gath System |  | Phase II | Alabama State Tract 73 to Transco/Colden, AL | 300000 | 1998-10-01 | Done |  | CP98-6 |  |  | 19000000 | 13
| Delhi |  | East Texas Cotton Valley | Pinnacle Reef Gathering Capacity | 275000 | 1997-04-01 | Done |  | Non-Jurisdictional
| Destin Pipeline Svs Company |  | Shell/Amoco | MP/VK to Pascagoula Area (VK 915 Marlin) | 1000000 | 1998-09-01 | Done |  | CP96-655 |  |  | 308000000 | 210 | 26400
| Destin Pipeline Svs Company |  | Shell/Amoco | New Lateral MP 283 to MP 279 (Gemini) | 111675 | 1999-11-01 | Done | Mobil & Phillips | CP98-512 |  |  | 7200000 | 31
| Discovery Gas Transmission |  | Texaco/MAPCO/British Borneo (Hardy/Allegheny/Morpeth) | ST 200, GI 115 & EB 873 to Larose, LA | 600000 | 1998-01-01 | Done |  | CP96-712 |  |  | 300000000 | 147
| DOMAC |  | Sithe Mystic Plant Expansion | 4 submerged combustion vaporization units | 280000 | 2002-05-01 | High |  | CP00-447
| Dominion |  |  | Transport increase | 102820 | 1997-11-01 | Done |  | CP96-492 |  |  | 55929000 | 36 | 13600
| Dominion |  | Market Value Project | Lebanon to Leidy and CNG Citygates | 400000 | 1998-11-01 | Dead
| Dominion |  | Bath Petroleum | Storage Withdrawal | 168320 | 1999-11-01 | Dead |  | CP96-492
| Dominion |  | Capstone Project | South Webster to Northern CNG Gates (Tenn replacement) | 0 | 2001-11-01 | High |  | CP00-64 |  |  | 63502000 | 13 | 20250
| Dominion |  | Leidy Transportation Project | North Points (Empirer/Tenn/Iroquois) to Liedy | 300000 | 2001-11-01 | High
| Dominion |  | High Deliverability Storage | Salt Like Firm Storage (12 cycles) |  | 2002-11-01 | Low
| Dominion |  | Greenbriar Pipeline | Cornwell to Rockingham, NC | 600000 | 2005-01-01 | Low |  |  |  |  | 400000000 | 200 | 31000
| Dominion |  | Greenbriar Pipeline | Cornwell to Rockingham, NC | 600000 | 2005-06-01 | Low |  |  |  |  | 400000000 | 200 | 31000
| Dominion/Tennessee |  | Atlantic Advantage Project | Chicago/Niagara to the Northeast | 750000 | 2001-11-01 | Dead
| Duke Energy |  | Spectrum | Chicago to New Jersey | 500000 | 1999-11-01 | Dead |  | CP97-626
| Duke Energy/Williams/Iroquois |  | Lighthouse Pipeline | Long Island to Milford, CT | 350000 | 2001-11-01 | Dead |  |  |  |  | 240000000
| Duke Energy/Williams/Keyspan |  | Cross Bay Pipeline | Transco/TETCO in NJ to JFK Airport | 125000 | 2002-12-01 | Low |  | CP00-412-414 |  |  | 59500000 | 33.7 | 16000
| East Tennessee |  | System Wide | Knoxville Area | 31902 | 1997-11-01 | Done |  | CP96-696 |  | 3-10 | 12915473
| East Tennessee |  | Virginia Expansion Project | Greenbriar, TN to Chilhowie & Roanoke, VA | 10300 | 1998-11-01 | Done | Roanoke Gas | CP98-40 |  | 20 | 8600000 | 10
| East Tennessee |  | Rocky Top Expansion | Greenbriar, TN to Chilhowie & Roanoke, VA | 35068 | 2001-11-01 | Done |  | CP00-51 |  | 10 | 18129000 | 28.73 | 0
| East Tennessee |  | Patriot Extension | Virginia to North Carolina (Transco) | 200000 | 2002-11-01 | Low |  |  |  |  | 215000000 | 95
| El Paso |  | Havasu | San Juan to East | 184140 | 1997-05-01 | Done | 16495 | CP96-321 |  |  | 19564419
| El Paso |  | Samalayucca II (Phase I) | Waco Station to PEMEX Juarez (Guars) | 72000 | 1998-06-01 | Done | PEMEX | CP93-252 |  |  | 18200000 | 20
| El Paso |  | Samalayucca II (Phase II) | Waco Station to PEMEX Juarez (Guars) | 100000 | 1998-10-01 | Done | Samal..
| El Paso |  | Bondad Compressor Expansion | Ignacio to Blanco Station | 116500 | 1999-01-01 | Dead | 100000 | CP98-149 |  |  | 3600000 |  | 5160
| El Paso |  | PEMEX | Waco Station to PEMEX Juarez (Guars) | 40000 | 2000-01-01 | Done
| El Paso |  | Willcox Lateral | Extension from Willcox to Douglas (Border) | 130000 | 2001-06-01 | High |  | CP99-322 |  |  | 30000000 | 56
| El Paso |  | Line 2000 - oil line conversion | Midland to Bakersfield (mostly replacement) | 300000 | 2001-10-01 | High
| El Paso |  | Yuma Extension | Yuma to Baja California (Mexicali) | 300000 | 2002-01-01 | Med |  |  |  |  | 143000000 | 94
| El Paso |  | Dumas Gas Transmission | Raton Basin to EPNG/NNG Dumas |  | 2002-04-01 | Med | [5 empty] | 185
| El Paso |  | Douglas Extension | Extension from Douglas to Mexico Border | 78000 |  | Done | Grupo Mex | CP98-359 |  |  | 600000 | 1
| El Paso Field Services |  | Diana Line | East Breaks 945/6 to HIOS @ EB 165 | 500000 | 1999-11-01 | Med
| Enbridge Consortium |  | Mackenzie Delta | Mackenzie to Fort Saskatchewan | 1200000 | 2007-11-01 | Low |  |  |  |  | 2850000000 | 1250
| Enbridge/MCN/Westcoast |  | Vector | Chicago to Dawn (with NIPSCO/Crossroads) | 700000 | 2000-12-01 | Done |  | CP98-131 |  | 10 | 443000000 | 270 | 60000
| Enbridge/MCN/Westcoast |  | Vector Expansion | Compression | 300000 | 2001-11-01 | Med |  |  |  | 3
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 650000 | 2001-11-01 | Dead
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 650000 | 2001-11-01 | Dead
| FGT/El Paso |  | Cypress | Elba Island LNG to FGT Jacksonville | 310000 | 2003-04-01 | Med |  |  |  |  | 232000000 | 160 | 0
| Florida Gas Transmission |  |  | Texas to Louisiana |  | 1997-11-01 | Dead
| Florida Gas Transmission |  | Phase IV | Central and South Central Florida | 272000 | 2001-05-01 | High | PD recvd | CP99-94 |  | DEIS | 351000000 | 205 | 48570
| Florida Gas Transmission |  | Phase V | Plant Smith and Sanford Plant | 428000 | 2002-04-01 | High |  | CP00-40 |  |  | 466000000 | 191 | 125215
| Florida Gas Transmission |  | Phase VI | Bayside Plant | 175000 | 2003-05-01 | Med
| Foothills |  | NBPL Expansion | Nova to NBPL | 698900 | 1998-12-01 | Done | 15000 |  |  |  | 125000000 | 71 | 51000
| Garden Banks Pipeline |  | Shell/Hess (Ench/Auger/Bladpate) | GB 128A (Enchilada) to SMI 76 (BlueW/TRCO) | 600000 | 1997-04-01 | Done |  | CP96-679 |  |  | 108000000 | 50
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 212200 | 1998-11-01 | Dead |  |  |  |  | 1000000000
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 285000 | 1999-11-01 | Dead |  |  |  |  | 1000000000
| Granite State |  | Wells LNG | Portland/Northern Utilities 2.0 Bcf MSQ |  | 2000-11-01 | Dead |  | CP96-610 |  | 20 | 44221000
| Great Lakes |  | River Crossing Security | Zone 3 - Under the St. Clair River | 50000 | 1996-11-01 | Done |  | CP96-26 |  | 2 | 3900000
| Great Lakes |  | Security Loop I | Looping in Lower Michigan | 5000 | 1996-11-01 | Done |  | CP95-375 |  |  | 17400000 | 14 | 14800
| Great Lakes |  | Security Loop II | Looping in Delta and Mackinac Counties, MI | 5000 | 1998-11-01 | Done |  | CP96-297 |  |  | 44300000 | 25
| Great Lakes |  |  | Emerson to St. Clair | 126000 | 1998-11-01 | Done | 30000 | CP96-647 |  |  | 149000000 | 72 | 14800
| Great Lakes |  | Security Loop III | Looping in Delta and Mackinac Counties, MI | 0 | 1999-11-01 | Done |  | CP98-143 |  |  | 11000000 | 14
| Great Lakes |  | Nexus 98/99 | Emerson to St. Clair | 2000000 | 1999-11-01 | Dead
| Great Lakes |  | 300 Expansion | Emerson to St. Clair | 304000 | 2000-11-01 | Dead |  | CP98-309 |  |  | 620000000
| Green Canyon Gathering System |  | Tennessee/National Fuel | EB, GC & MC to Lafourche Parish, LA | 515000 | 1999-11-01 | Low |  | CP96-557 |  |  | 200000000 | 133
| Gulf States Pipeline |  | Panda El Dorado Plant | Expansion from the Sharon La tie-in to TGP |  | 2002-06-01 | Med
| Iroquois |  |  | Waddington to S. Comack | 35000 | 1996-11-01 | Done | 15000 | NA |  | 10
| Iroquois |  | Athens | Waddington to Brookfield | 30160 | 1998-11-01 | Done |  | CP96-687 |  | 10 | 22000000 |  | 9500
| Iroquois |  | Vermont Extension | EDC Bennington & Rutland Plants | 250000 | 2001-11-01 | Dead |  |  |  |  | 105000000 | 70
| Iroquois |  | Eastchester Bay Marine Ext Proj | Waddington to Eastchester (ConEd) | 220000 | 2002-11-01 | Med | None | CP00-232 | rolled in | 10-30 | 173918000 | 30.3 | 58300
| Iroquois/Tennessee |  | EPEM/PDC Milford Plant | Waddington to Milford/Tenn Zone 6 Delivery | 35000 | 2000-11-01 | High
| Kern River |  | Long Beach Extension | Bakersfield to Long Beach | 300000 | 2001-11-01 | Low
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 300000 | 2001-11-01 | on hold
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 124500 | 2002-05-01 | Med |  |  |  |  | 80000000 |  | 3 comps
| KN |  | Pathfinder Pipeline | Glenrock to Rockport
| KN Energy/NICOR |  | Horizon | Chicago | 380000 | 2002-04-01 | Med | PD recd | CP00-129 |  | 10 | 75000000 | 28.5 | 8900
| KN/Devon |  | Thunder Creek Gas Gathering | Gillette, WY to Glenrock, WY | 450000 | 1999-11-01 | Done |  |  |  |  | 100000000 | 126
| KNE |  | Pony Express | Wind River Basin to Kansas City | 135000 | 1997-08-01 | Done |  | CP96-477
| KNE |  | Pony Express | Dull Knife to Kansas City | 120000 | 1997-12-01 | Done |  | CP96-477 |  |  | 154000000 | 804
| KNE |  | Wyoming Pipeline Project | Wind & Powder River/Big Horn to Rockport | 450000 | 1999-10-01 | Dead |  |  |  |  | 110000000
| Koch |  | Grand Isles Extension |  | 300000 | 1999-11-01 | Dead | [5 empty] | 5
| Koch Gateway |  | East Texas | Carthage to Perryville | 250000 | 1998-11-01 | Dead |  |  |  |  | 31000000
| Koch Gateway Pipeline |  | Venice Expansion | Venice to Koch Mainline | 615000 | 1997-11-01 | Done |  | CP96-572 |  |  | 20500000
| Leviathan/Tejas |  | Nemo Gathering | Brutus (GC 158) to Manta Ray | 150000 | 2001-12-01 | Med | [5 empty] | 24
| Maine Natural Gas |  | Westbrook Lateral | MN&E to the Calpine Westbrook Plant | 100000 | 2000-07-01 | High
| Maine Natural Gas |  | Brunswick Lateral | MN&E to Brunswick and Topsham | 50000 | 2001-08-01 | High |  |  |  |  | 10000000 | 18
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | GC 65 (Bullwinkle) to Ship Shoal 207 (Nautilus) | 300000 | 1997-12-15 | Done |  | CP96-796
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | ST 292 to GI 116 (Anadarko/Hickory) | 300000 | 2001-03-01 | High | [5 empty] | 22
| Maritimes & Northeast |  | Sable Island Phase I | Wells, Maine to Dracut, MA (flows backwards) | 60000 | 1999-12-01 | Done |  | CP96-178 |  |  | 103726000
| Maritimes & Northeast |  | Sable Island Phase II | Sable Offshore Energy Int. to Dracut, Mass. | 360000 | 1999-12-01 | Done |  | CP96-809 |  |  | 79217000 | 454 | 31160
| Maritimes & Northeast |  | Bangor Gas | Orrington, ME | 50000 | 2000-07-01 | Done |  | CP00-77 |  |  |  | 8.3 | 0
| Maritimes & Northeast |  | Gorham Lateral | Mainline to Gorham, ME Plant | 165000 | 2000-09-01 | Done |  | CP98-724 |  |  | 2000000 | 1
| Maritimes & Northeast |  | Veazie Lateral | Eddington, ME to Veazie (Casco Bay Plant) | 105000 | 2000-11-01 | Done |  | CP98-797 |  |  | 6000000 | 1 | 0
| Maritimes & Northeast |  | Halifax Lateral | NS Power Tufts Cove Plant | 166000 | 2000-12-01 | Done | [5 empty] | 63
| Maritimes & Northeast |  | St John Lateral | JDI & NB Power Bayside Power Station | 105002 | 2001-01-01 | High |  | CP98-799 |  |  | 6000002 | 3
| Maritimes & Northeast |  | Four Rivers Plant |  |  | 2001-09-01 | Med
| Maritimes & Northeast |  | Phase III | adds Beverly MA as another Delivery Point | 360000 | 2002-11-01 | Med |  | CP01-4 |  |  | 133995000 | 25.1 | 0
| Maritimes & Northeast |  | New Brunswick to Quebec lateral | Fredericton, NB to Quebec City (Riviere-du-Loup) | 300000 | 2003-11-01 | Low
| MCN/Columbia Gulf |  | Volunteer Pipeline | Chicago (via Midw) to Atlanta | 250000 | 2001-11-01 | Low |  |  |  |  | 160000000
| MHP |  | Tioga Storage Facility (PA) | 5.0 Bcf working gas capacity | 1500000 | 2004 | High
| Mid Louisiana |  | Baton Rouge Expansion | Transco Station 61 to Baton Rouge | 60000 | 1998-10-01 | Low
| Midcon Texas |  | Roma Crossing | Bob West Field to Mexican Border | 275000 | 2000-12-01 | Med |  | CP96-770
| Midcon Texas |  | Monterey Pipeline Project | Cuidad Mier to Monterey | 275000 | 2000-12-01 | Med |  | CP96-583 |  |  | 520000 | 92
| Midwestern |  | PL Reversal | Chicago to Tennessee | 500000 | 2001-11-01 | on hold
| Mississippi Canyon Gath System |  | Shell (Mars, Ursa, Mensa) | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 600000 | 1996-09-01 | Done |  | CP96-159 |  |  | 75000000 | 45
| Mississippi Canyon Gath System II |  | Compression upgrades | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 200000 | 1999-07-01 | Done |  |  |  |  | 216000
| National Fuel |  |  | Niagara to Leidy | 25000 | 1997-11-01 | Done | 25000 | CP96-671 |  | 10 | 10600000 |  | 1300
| National Fuel |  | Son of Seaboard | Niagara to Leidy | 100000 | 1998-11-01 | Dead
| National Fuel |  | Grandson of Seaboard | Niagara to Leidy | 400000 | 1999-11-01 | Dead
| National Fuel |  | Ellisburg compression | Ellisburg to Leidy, PA | 60919 | 1999-11-01 | Done |  | CP99-160 |  |  | 223600 |  | 1245
| National Fuel |  | AM-60 Pipeline Replacement | Lamont, PA to Roystone, PA | 30000 | 2000-11-01 | Done |  |  |  |  | 11400000 | 12.9 | 360
| Nautilus Pipeline |  | Shell | SS 207 to South Bend, LA (Troika) to ANR | 600000 | 1997-12-15 | Done |  | CP96-790/791/792 |  |  | 121000000 | 101
| NE Hub Partners |  | Tioga Storage | Pennsylvania 6.0 Bcf | 500000 | 1999-11-01 | High
| NGPL |  | Louisiana Line Expansion | Compression | 63000 | 1997-11-01 | Dead |  | CP96-720 |  | 7 | 4300000
| NGPL |  |  | Gage to Chicago |  | 1997-11-01 | Dead
| NGPL |  |  | Arkoma to Henry | 125000 | 1997-12-01 | Dead
| NGPL |  | Chicago | Harper to Chicago | 110000 | 1998-11-01 | Done | 10000 | CP96-27 |  |  | 24000000 | 5 | 9000
| NGPL |  | Hub America | Chicago to Lebanon/TETCO M3 | 100000 | 2000-11-01 | High |  |  | rolled-in
| NGPL |  | New York | Chicago to New York |  | 2000-12-01 | Dead
| NGPL |  | St Louis Lateral |  | 300000 | 2002-06-01 | Med | 311 fac. |  |  |  | 35000000 | 47
| Noram |  | North Louisiana Expansion | Carthage to Perryville Hub | 170000 | 1998-11-01 | Done | UPRC 50/Amoco 15 | CP97-724 |  | 10/5 | 32200000
| Northern Border |  | Expansion | Monchy to Harper | 700463 | 1998-12-01 | Done | 55000 | CP95-194 |  |  | 457900000
| Northern Border |  | Extension | Harper to Chicago | 663050 | 1998-12-01 | Done | 45000 | CP95-194 |  |  | 338900000 | 793 | 293000
| Northern Border |  | Chicago Extension | Chicago to NIPSCO | 198300 | 2001-11-01 | High |  | CP99-21 |  |  | 93000000 | 34 | 30500
| Northern Border |  | Bison Pipeline | Gillete, WY to McCabe, MT | 500000 | 2003-11-01 | Med |  |  |  |  | 225000000 | 325
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 244000 | 1997-11-01 | Done |  | CP97-25 |  |  | 102000000 | 50 | 41000
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 32000 | 1998-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | NNG Zone E/F Koch | NNG Market Area Expansion (Rosemount) | 20000 | 1998-11-01 | Done - At Risk |  | CP98-132 |  |  | 9400000
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 31000 | 1999-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 21000 | 2000-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | East Leg 2000 | Replaced with Ill/WI Express | 450000 | 2000-11-01 | replaced
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 20000 | 2001-11-01 | Done |  | CP97-25
| Northwest Natural Gas |  | Mist Expansion Phases IV | Storage Field Expansion of 14 Bcf |  | 2002-11-01 | Low |  |  |  |  | 58000000 | 32
| Northwest Natural Gas |  | Mist Expansion Phases V | Storage Field Expansion of 14 Bcf |  | 2004-11-01 | Low | [5 empty] | 20
| Northwest Natural Gas |  | Mist Expansion Phase III | Storage Field Expansion of 2 Bcf | 45000 | [6 empty] | 122000000 | eight year plan
| Northwest Pipeline |  | Columbia River Gorge Expansion | Stanfield to Sumas | 50000 | 1999-11-01 | Done | DETM | CP98-554 |  |  | 18570000 |  | 10870
| Northwest Pipeline |  | Jackson Prairie Expansion | Storage Field Expansion of 3.2 Bcf | 300000 | 1999-11-01 | Done |  | CP98-250 |  |  | 30192000 |  | 6960
| Northwest Pipeline |  | Puget Sound Plant Lateral | Snohonmish County, WA | 133000 | 2002-08-01 | High |  |  |  |  | 17200000
| Northwest Pipeline |  | Grants Pass Lateral Expansion |  | 50000 | 2002-11-01 | Med
| Northwest Pipeline |  | Displacement Expansion | Ignacio to Stanfield Corridor | 175000 | 2003-10-01 | High |  |  |  |  | 81000000
| Northwest Pipeline |  | Jackson Prairie Expansion II | Displacement expansion for system operations | 175000 | 2003 | Med |  | CP98-251 |  |  | 100000000 |  | 6961
| Northwest Pipelne |  | Silver Gem Lateral | Filer, Idaho to Wells, Nevada | 90000 | 2000-11-01 | Dead
| Nova |  | NBPL Expansion | Alberta to Foothills | 500000 | 1998-12-01 | Done | 15000 |  |  |  | 365400000
| NovaGas Clearinghouse |  | Pesh Creek Pipeline | British Columbia to Alberta | 60000 | 1997-05-01 | Done |  |  |  |  | 2900000
| Ozark |  |  | Oklahoma to Louisiana | 185000 | 1997-11-01 | Dead
| Pacific Gas Transmission |  | Kingsgate to Malin | Duke, Montana Power, El Paso, POCO, Avista | 57000 | 1998-11-01 | Done |  | CP98-167 |  | 3-15 | 6000000
| Paiute Pipeline |  | System Expansion | Wells, Nevada to Paiute @ Elko, Nevada | 90000 | 2001-11-01 | Dead | replaced
| Palliser |  | Settlement reached with Nova | Nightingale, AB to Empress | 1200000 |  | Dead
| Panda |  | Trans-Union Interstate Pipeline | Claibourne Parish, LA to Arkansas Plant | 400000 | 2002-04-01 | Done |  | CP00-47 |  |  | 41000000 | 41.7
| Penn West Petroleum, Ltd. |  | Wildboy Project | Wildboy Field (Fort Nelson, BC) to NOVA | 10000 | 1999-11-01 | Done |  |  |  |  | 15000000 | 40
| Peoples/Coastal |  | Whitecap Energy - Land | ANR @ Crete, IL to Southeastern WI | 1500000 | 2002-04-01 | Low | 30000 |  |  |  | 334000000 | 21
| Peoples/Coastal |  | Whitecap Energy - Lake | ANR @ Crete, IL to Southeastern WI | 1500000 | 2003-11-01 | Low | 30001 |  |  |  |  | 90
| PEPL |  | Tuscola to Illinois | Replaced by Spectrum Project | 150000 | 1997-11-01 | Dead
| Petal Gas Storage |  | Hattiesburg Storage Lateral | Hattiesburg,MS to Destin, Koch, Sonat & Transco | 700000 | 2001-06-01 | Done |  | CP00-59 |  |  |  | 5.5 | 35000
| PG&E/Avista |  | Jackson Prairie Expansion | Storage Field Expansion of 5.0 Bcf |  | 2003-10-01 | Med
| PG&E/Avista |  | Stanfield Storage | Stanfield, OR 15.0 Bcf working gas |  | 2003-11-01 | Med
| PGT |  | Kingsgate to Malin | Kingsgate to Malin | 200000 | 2002-11-01 | Med
| Pine Needle LNG |  | Transco/Piedmont | North Carolina Peaking 4 Bcf MSQ | 400000 | 1999-11-01 | Done |  | CP96-52 |  | 20 | 107000000
| Portland Natural Gas Transmission |  | Granite State PL replacement | TCPL to Tennessee at Haverhill, Mass. | 178000 | 1999-03-01 | Done | 30000 | CP96-248 |  | 15-20 | 270000000 | 243
| Portland Natural Gas Transmission |  | TQM Link | TQM from Sable Island to Dracut, Mass | 350000 | 1999-11-01 | Dead |  | CP96-249
| Portland/Maritimes |  | Joint Line Application |  |  | 1999-02-01 | Done |  | CP97-238 |  |  | CP96-178 ???
| Questar |  | Phase I | Clay Basin Storage to Kanda | 59000 | 1997-08-01 | Done - at risk |  | CP96-820
| Questar |  | Clay Basin Expansion | Increase by 4.0 Bcf (by adding cushion gas) | 88000 | 1998-05-01 | Done |  | CP96-820 |  |  | 18000000 | 41 | 110
| Questar |  | Phase II | Clay Basin Storage to Kanda | 25000 | 1998-08-01 | Done - at risk |  | CP96-820 |  |  | 18000000 | 41 | 110
| Questar |  | Fidlar Compressor Station | Expands southern part of system | 58850 | 2000-06-01 | Done |  | CP00-41 |  |  | 3325000 |  | 4829
| Questar |  | Southern System Expansion | Southern System to Clay Basin/Kanda | 280000 | 2000-10-01 | Dead
| Questar |  | Wyoming Pipeline Project | Wyoming to Kanda (Pinedale Area Porduction) | 300000 | 2000-10-01 | Low
| Questar |  | Opal Connection | Seven miles to connect to Opal | 100000 | 2000-10-01 | Low
| Questar |  | Southern Trails | San Juan to Long Beach | 120000 | 2001-10-01 | Med |  | CP99-163 |  |  | 155000000 | 705
| Questar |  | Mainline 104 Expansion |  | 272000 | 2001-11-01 | Med | PD Recvd | CP00-68 |  |  | 80800000 | 75 | 9336
| Questar/CIG |  | Southern System Expansion | Price, UT to Kern in Salt Lake City Area | 272000 | 2001-06-01 | High |  |  |  | 10 | 80850915 | 75.6 | 9336
| Questar/Montana Power |  | Clear Creek Storage | 4 Bcf with 50,000/d Inj. | 35000 |  | High |  |  |  |  | 3300000
| Reliant |  | SWEPCO Wilkes Plt Extension |  | 100000 | 2000-06-01 | Done | [5 empty] | 18
| Reliant Energy Gas Transmission |  | Pine Bluff Plant Lateral (Skygen) | Jefferson Co, AR (Line AC) | 40000 | 2001-06-01 | High | Skygen | CP00-137 |  | 10 | 1500000 | 2
| Ricks Nova Scotia |  | Ladyfern Pipeline | NE BC to Nova's Owl Lake South Station | 30000 | 2001-03-01 | High | NEB approval 1/01 |  |  |  | 3000000 | 7.5
| Sabine |  |  | HPL to Henry | 30000 | 1996-12-01 | Done
| Sable Offshore Energy Project |  | Maritimes and Northeast feed | Nova Scotia/New Brunswick to US | 400000 | 1999-12-01 | Done
| Scana |  | Carolinas Pipeline | South Carolina (Elba) to North Carolina (Pembroke) | 250000 | 2003-11-01 | Low |  |  |  |  | 1780000000
| Sempra Energy International |  | Rosarito Power Plt/Vecinos | Riverside Co., CA to Tijuana | 500000 | 1999-12-01 | Done | Sempra | CP94-207 |  |  | 35000000 | 23
| Sempra/PG&E/Proxima Gas SA |  | North Baja Pipeline/Ehrenberg Exp | El Paso Ehrenberg to Baja California | 500000 | 2002-09-01 | Med |  | CP01-22 |  |  | 146000000 | 212
| South Carolina Pipeline |  | New compressor - Blacksburg | Increase Transco takeaway | 75000 | 1997-11-01 | Done |  | Non-Jurisdictional |  |  | 10000000
| South Georgia |  | Holy Trinity Looping | SoNat to South Georgia gates | 17000 | 2001-11-01 | High |  | CP01-95 |  |  | 5969100 | 7.1 | 0
| Southern |  | North System | North System to Chattanooga | 25000 | 1996-11-01 | Done |  | CP94-682
| Southern |  | Zone 3 Markets | MS/AL Loops - Wren/Savannah Line | 45880 | 1997-11-01 | Done |  | CP96-541 |  | 10 | 36043000 | 28 | 10640
| Southern |  | N. Louisiana | Texas to Louisiana |  | 1997-11-01 | Dead
| Southern |  | Zone 2 and 3 Markets | MS/AL Loops | 64911 | 1998-11-01 | Done |  | CP97-526 |  | 12 | 52179005
| Southern |  | Zone 2 Markets | Alabama Power | 34925 | 1998-12-01 | Done |  | CP97-526 | Increm | 12 | 52179005
| Southern |  | North Alabama PL Exp | N. Alabama to Huntsville (Alatenn Bypass) | 76350 | 2000-01-01 | Done |  | CP96-153 |  |  | 66800000 | 118 | 6300
| Southern LNG |  | Elba Island LNG Terminal | 4 Bcf Capacity | 330000 | 2002-01-01 | High | PD recvd | CP99-579 |  |  | 26200000
| Southern Natural Gas | 1 | Lease of Capacity by Destin | Destin delivery into SoNat to TETCO Cranfield | 200000 | 1998-09-01 | Order disallowed roll-in |  | CP96-655 |  | 20
| Southern Natural Gas |  | Wrens Compression Upgrade | Improve flow on Wrens/Savannah Line |  | 2001-10-01 | Done |  | CP00-231 |  |  | 5151438 |  | 3500
| Southern Natural Gas |  | AL/GA Expansion |  | 17000 | 2001-11-01 | Med |  | CP01-35 |  |  | 6000000 | 7
| Southern Natural Gas |  | South System Expansion | Phase I Loop from MS to GA/Phase II Loop from MS toAL | 335800 | 2002-06-01 | High |  | CP00-233 |  |  | 140736540 | 67.3 | 53890
| Southern Natural Gas |  | TOCA Expansion |  |  |  | Done |  | CP95-500
| Southern/AGL |  | Etowah LNG | Polk County, Georgia 3 Bcf | 450000 | 2001-11-01 | Med |  | CP98-363 |  | 20
| Southern/CP&L |  | Palmetto Interstate Pipeline | SoNat system expansion and extension from Aiken, SC to Robeson CO, NC (NCNG) | 250000 | 2002-04-01 | Dead |  |  |  |  | 450000000 | 175
| Stingray Pipeline Company |  | Garden Banks 72/VER Blocks | GB 72 to Stingray at VER 362 lateral | 100000 | 1995-11-01 | Done |  | CP96-91 |  |  | 9000000 | 15
| Sumas Energy 2 |  | NWPL bypass | Westcoast Energy to 720 MW CC Plant | 140000 | 2003-11-01 | Med |  | CP99-320 |  |  |  | 4.5
| Tatham Offshore (Leviathon) |  | North Atlantic Pipeline Project | Hibernia/Sable Island to New England | 250000 | 1999-11-01 | Dead |  | CP98-29/30/31/32
| TCPL |  | Conventional 96 | Alberta to Ontario/Export | 150000 | 1996-11-01 | Done | 15000 |  |  |  | 489000
| TCPL |  | Conventional 97 | Alberta to Ontario/Export | 286700 | 1997-11-01 | Done | 20000 |  |  |  | 900000000
| TCPL |  | Nexus 98 | Alberta to Ontario/Export | 2000000 | 1998-11-01 | Dead |  |  |  |  | 1190000000
| TCPL |  | Conventional 98 | 58.5 Domestic/397.4 Export | 455900 | 1998-11-01 | Done | 33539 |  |  |  | 877600000
| TCPL |  | Nexus 99 | Alberta to Ontario/Export | 938000 | 1999-11-01 | Dead
| TCPL |  | Conventional 99 | 108.0 Expansion/44.0 turnback | 108000 | 1999-11-01 | Done |  |  |  |  | 404500000
| TCPL |  | TransVoyageur Transmission | Empress, Alberta to Emerson, Manitoba | 2000000 | 1999-11-01 | Dead
| TCPL |  | Merida III Power Plant | Ciudad Pemex, Tabasco to Campeche/Merida | 370000 | 2000-06-01 | Done
| TCPL/ANG Pipeline |  | Kootenay Pacific Pipeline | Yahk, BC to Vancouver/Sumas | 550000 | 2000-11-01 | Dead |  |  |  |  | 530000000
| TCPL/St. Clair Pipeline |  | Lake Erie Crossing Pipeline | 7 shippers | 650000 | 2002-11-01 | Med |  |  |  |  | 106000000 | 60
| TCPL/Westcoast |  | Canadian Arctic Pipeline | Mackenzie Delta/Canadian Arctic to AB/BC | 4000000 |  | Low |  |  |  |  | 6000000000
| TCPL/Westcoast/CGT/MCN |  | Canadian Millenium | Dawn to Lake Erie | 700000 | 2002-11-01 | on hold |  |  |  |  | 700000000
| Tenneco |  | Donna Lateral | Extension to Reynosa | 220000 | 1999-10-01 | Done |  | CP98-28 |  |  | 15000000 | 10
| Tenneco |  | Mexicali | California to Baja California |  |  | Dead | replaced by Sempra
| Tennessee |  | Niagara Expansion | National Fuel Compressor Expansion | 21344 | 1997-11-01 | Done |  | CP96-721 |  |  | 51620
| Tennessee |  | DOMAC Expansion | DOMAC Everett Plant to Saugus, Mass | 90000 | 1998-11-01 | Done |  | CP96-194 |  |  | 25900000 | 8
| Tennessee |  | Ellisburg Extension (me too) | Niagara to Leidy | 250000 | 1999-11-01 | Dead
| Tennessee |  | Eastern Express | Chicago to Leidy | 500000 | 1999-11-01 | Dead
| Tennessee |  | Express 500 | 500 Line Expansion from offshore LA |  | 1999-11-01 | Low
| Tennessee |  | LS Power Batesville lateral | Panola, MS to Tennessee | 216000 | 2000-06-01 | Done |  | CP98-770 |  |  |  | 3
| Tennessee |  | Honeoye Storage Expansion | 1.8 Bcf increase in working gas | 15000 | 2000-08-01 | Low |  | CP00-93 |  |  | 3000000
| Tennessee |  | Texas Deepwater link Project | HIOS WC 167 to WC 180 (Tennessee) | 400000 | 2000-11-01 | Med | Vastar | CP00-441 |  |  | 14500000 | 17.5
| Tennessee |  | Stagecoach Lateral | Central New York - Tennessee Line 300 | 500000 | 2001-08-01 | High | FEIS rcvd | CP 00-65 |  | 10 | 81271600 | 23.7 | 13400
| Tennessee |  | Concord Lateral/AES Loundonderry | Dracut to Loundonderry, NH 20" replacement | 130000 | 2001-10-01 | Done |  | CP 00-48 |  | 20 | 324563678 | 19.3 | 0
| Tennessee |  | Eastern Express 2001 | Dracut to New England | 288000 | 2001-11-01 | Done |  | CP99-262 | rolled in |  | 28143432 | 0 | 13320
| Tennessee |  | CanEast | Niagara/Gulf Coast to Leidy via CNG lease | 280000 | 2001-11-01 | High
| Tennessee |  | Panda El Dorado Plant | Interconnect |  | 2002-06-01 | Med
| Tennessee/Leviathon |  | Viosca Knoll Expansion | Looping of existing VK Line (Bi-flow) | 250000 | 1998-11-01 | Done
| TETCO |  | AES Ironwood Plant Lateral | Lateral in TETCO M3 (PA) | 120000 | 2000-09-01 | Done | 20 yr | CP99-621 |  |  | 5700000 | 3.6 | 0
| TETCO |  | Independence/ML Substitute | ANR/Muncie to Linden, NJ | 663000 | 2000-11-01 | Low
| TETCO |  | Excelsior | New Jersey to New York | 500000 | 2000-11-01 | Dead
| TETCO |  | PSI Wabash Power Lateral | Midwestern Int at Vigo County, Ind | 215000 | 2001-04-01 | High |  |  |  |  | 8000000 | 9
| TETCO |  | Phildelphia Lateral Expansion | Liberty Plants (Columbia and PG&E) | 84000 | 2002-01-01 | High |  | CP00-404 |  | 14.5 |  | 1 | 4000
| TETCO/Dominion |  | WinterNet | Oakford Storage to CNG (Phased) | 64000 | 1997-11-01 | Dead |  | CP96-606 |  | 24 | 18589000
| TETCO/Dominion |  | SS-E | Oakford Storage to CNG 4.6 Bcf | 70000 |  |  |  | CP96-607 |  | 25 | 18589001
| Texas Eastern |  | Spectrum Related | Lebanon Lateral Expansion | 302290 | 1998-11-01 | Done |  | CP98-336 |  |  | 31000000 |  | 17070 | (Gas City and Glen Karn)
| Texas Eastern |  | Duke Vermillion Lateral | Midwestern PL to the plant (Cayuga) | 200000 | 2000-06-01 | High |  | CP 00-67 |  |  | 13000000 | 14
| Texas Eastern Transmission |  | Lease of Capacity by DIGP | Main Pass 164 to Venice Plant | 100000 | 2000-01-01 | Done | 15 | CP99-18 |  |  |  | 10
| Texas Eastern/NGPL |  | Enhanced Spectrum | Chicago Alliance to M3 | 55000 | 2000-11-01 | High |  |  | 0.46
| Texas Gas Transmission |  | Carthage Expansion | Haughton Comp Stn to Bossier Parish, LA | 105000 | 1998-11-01 | Done | UPRC | CP97-656 |  | 10 | 5980000 |  | 4600
| Totem Storage |  | CIG/PSCO connected storage facility' | 9 Bcf MSQ | 250000 | 2001-11-01 | Low
| Trailblazer |  |  | Tomahawk to NGPL | 104500 | 1997-08-01 | Done |  | CP96-506 |  | 10 | 11663000 |  | 5200
| Trailblazer |  | Expansion/Extension | Glenrock to Gage | 300000 | 2002-07-01 | High |  |  |  |  | 58500000 | 149 | 44800
| TransAlaska Natural Gas Systems |  | Arco/BP/Exxon/Phillips/Mobil/Hess/Unocal | Prudhoe Bay delevelopment (LNG) | 15000 |  | Low
| Transco |  | Southeast Mainline Exp I | Stn 85 to Stn 150 NC | 35000 | 1994-11-01 | Done |  | CP94-68
| Transco |  | Southeast Mainline Exp II | Stn 85 to Stn 150 NC | 115000 | 1995-11-01 | Done |  | CP94-109
| Transco |  | Southeast Mainline Exp III | Stn 85 to Stn 150 NC | 50000 | 1996-11-01 | Done |  | CP94-109
| Transco |  | Pocono Expansion Project | Leidy to Northhampton County, PA | 35000 | 1997-11-01 | Done |  | CP97-328 |  | 15 | 9800000
| Transco |  | Seaboard 97 (or so) | Leidy to New York City | 115000 | 1997-11-01 | Dead | 30000 | CP96-545 |  | 15-21 | 117700000
| Transco |  | SunBelt | 100 Stn 65 to Stn 85, 146 Stn 85 to Stn 145 NC | 145666 | 1997-11-01 | Done |  | CP96-16 |  | 20 | 85000000 | 15 | 30000
| Transco |  | Maiden Lateral | Expansion to Piedmont | 69000 | 1997-12-01 | Done |  | CP97-193 |  |  | 13200000 | 18
| Transco |  | Mobile Bay Extension | Main Pass 261 to Mobile Bay 822 to Stn 82 | 350000 | 1998-08-01 | Done | WESCO | CP97-92 |  | 15 | 120200000 | 77 | 30000 | Totally in-service on Nov. 9
| Transco |  | Mobile Bay Expansion | Station 85 | 128137 | 1998-08-01 | Done |  | CP97-93
| Transco |  | Cherokee Expansion | Stn 85 to Stn 130 Madison Co., GA | 87070 | 1998-11-01 | Done |  | CP97-331 |  | 15 | 68000000 | 15 | 23000
| Transco |  | Mobile Bay Expansion II | Station 85 | 135711 | 1998-11-01 | Done |  | CP97-94
| Transco |  | Genesis Field | Green Canyon 205 to Transco Ship Shoal | 72000 | 1999-02-01 | Done |  | Non-Jurisdictional
| Transco |  | SE Louisiana Crossover | Garden Banks PL @ SMI 76 to Station 50 | 264020 | 1999-09-01 | Done | at risk | CP99-76 |  | Hess | 80000000 | 53
| Transco |  | SE Louisiana Crossover | SMI 76 to VER 67 offshore | 141970 | 1999-09-01 | Done | at risk | CP99-76
| Transco |  | Cumberland Pipeline | Walton Co., GA to Chattanooga, TN | 450000 | 2000-11-01 | Dead |  |  |  |  | 115000000 | 141
| Transco |  | Cumberland Pipeline II | Walton Co., GA to Chattanooga, TN | 220000 | 2000-11-01 | Dead
| Transco |  | SouthCoast | Stn 85 to Zone 4 points north of Atlanta, GA | 204999 | 2000-11-01 | Done | PD recvd | CP99-392 | Southern Co 40,000/d | 15 | 108000000 | 44 | 31500
| Transco |  | MarketLink Phase I | Leidy to New York City | 166000 | 2001-11-01 | Done |  | CP98-540 |  |  | 123300000 | 60.6 | 30000
| Transco |  | Sundance Pipeline | Station 65 to North Carolina (CP&L) | 236383 | 2002-04-01 | Med | PD recvd | CP00-165 | Incremental | 15 | 134674037 | 421 | 41225
| Transco |  | MarketLink Phase II | Leidy to New York City | 130000 | 2002-11-01 | Done |  | CP98-540 |  |  | 119600000
| Transco |  | Momentum Expansion Project | Station 65 to Station 165 Virginia excl So VA lateral | 475000 | 2003-05-01 | Med | Inc Rates |  |  | 175
| Transco |  | MarketLink Phase III | Leidy to New York City | 432000 | 2004-11-01 | Med |  | CP98-540
| Transco/ANR/National Fuel |  | Independence Pipeline | Chicago to Leidy | 946500 | 2002-11-01 | Med |  | CP97-315/320/321 |  |  | 629600000 | 400 | 60000
| Transco/Duke |  | Buccaneer Pipeline | Station 82 to north of Tampa Bay | 900000 | 2003-04-01 | Dead |  | CP00-14 |  |  | 1455173425 | 673.88 | 75000
| Transco/Duke (Formerly Coastal) |  | Gulfstream | Mobile, AL to West Palm Beach, FL | 1100000 | 2002-06-01 | Med |  | CP00-6 |  |  | 1600000000 | 744
| Transco/PSNC/Piedmont/NCNG |  | Cardinal Extension Co. | Stn 160 Rockingham, NC to Burlington, NC | 140000 | 1999-11-01 | Done |  | Non-Jurisdictional |  |  | 98300000 | 67
| TransColorado |  | Phase I | Rio Blanco, CO to EP Blanco | 75000 | 1996-12-01 | Done |  | CP90-1777 |  |  | 14100000
| TransColorado |  | Phase II | Rio Blanco, CO to EP Blanco | 45000 | 1999-02-01 | Done |  | CP90-1777
| TransColorado |  | KN/Questar | NW Colorado to Red Cedar Lateral | 300000 | 1999-03-01 | Done |  | CP90-1777 |  |  | 170900000 | 295
| TransOk |  | Trident Ambrose Plant | Cushing to Blackwell, OK | 300000 | 1997-04-01 | Done |  | Non-Jurisdictional |  |  | 35000000
| TransOk |  |  | Bradley to Atoka, OK (Texoma) | 300000 | 1997-07-01 | Dead |  | Non-Jurisdictional |  |  | 40000000
| TransQuebec & Martimies PL |  | TQM Extension | Lachenaie, PQ to East Hereford, NH | 194000 | 1998-11-01 | Done |  |  |  |  | 175000000 | 135
| Trans-Union Interstate Pipeline |  | Panda El Dorado Plant | Gulf States Pipeline to the El Dorado Plant | 430000 | 2002-06-01 | Med | [5 empty] | 42
| Transwestern |  |  | San Juan Lateral | 255000 | 1996-12-01 | Done | 8000 | CP96-10 |  |  | 14600000
| Transwestern |  |  | Thoreau to East | 107000 | 1996-12-01 | Done | 8000
| Transwestern |  | San Juan Junior | Ignacio to Blanco | 200000 | 1998-04-01 | Dead | 45000 | CP97-516 |  |  | 21000000 |  | 22000
| Transwestern |  | San Juan Junior | Blanco to Thoreau | 130000 | 1998-04-01 | Dead | 45000 | CP97-517
| Transwestern |  | Gallup Expansion | Thoreau to California Border | 140000 | 2000-05-01 | Done |  | CP99-552 |  |  | 11600000 |  | 10000
| Transwestern |  | San Juan to California | could be 100/d or 300/d | 610000 | 2002-11-01 | Low
| Trunkline |  |  | Katy to Henry | 250000 | 1997-11-01 | Dead
| Trunkline |  | SS Block 139 Compression | SS 139 to Patterson (upstream of constraints) | 500000 | 1998-05-01 | Done |  | CP97-105 |  |  | 52217940 |  | 28950
| Trunkline |  | Centennial Project | 720 miles of 26" line (chicago to gulf) | -255000 | 2001-12-01 | Low |  | CP00-114 |  |  | -10200000
| Trunkline LNG |  | Lake Charles LNG regasification | No increase to terminal, just regasification | 300000 | 2001-05-01 | Med |  |  |  |  | 1155000
| Trunkline LNG |  | Lake Charles Terminal | Increase sendout from 0.7 to 1.0 Bcf | 300000 | 2001-05-01 | Med |  |  |  |  | 2250000
| Tuscarora |  | Sierra Pacific Power | Lemmon Valley, NV Plant | 75000 | 2002-12-01 | Med |  |  |  |  | 10200000 | 16.4
| Union Gas |  |  | System-wide |  | 1998-11-01 | Dead
| Valero |  | Texas Expansion I | Bethel - Pinnacle Reef to Carthage Hub | 250000 | 1997-07-01 | Done |  | Non-Jurisdictional |  |  | 11700000
| Valero |  | Texas Expansion II | Bethel - Pinnacle Reef to Carthage Hub | 200000 | 1998-06-01 | Dead |  | Non-Jurisdictional
| Valero |  | Reynosa | McAllen, TX to Reynosa, Mexico | 400000 |  | Done |  | Non-Jurisdictional
| Venice Gathering System LLC |  | Venice Expansion |  | 328000 | 1998-11-01 | Done |  | CP97-533/534 |  |  | 40000000 | 52
| Vermont Gas Systems |  |  | Import at Highgate Springs, Vermont | 52000 | 1997-11-01 | Done |  | CP97-324
| Viking |  |  | Emerson to NNG | 20000 | 1996-11-01 | Done |  | CP96-32 |  |  | 8400000
| Viking |  |  | Emerson to NNG | 61300 | 1997-11-01 | Done |  | CP97-93 |  |  | 27900000
| Viking |  |  | Minnesota Looping | 28000 | 1999-11-01 | Done |  | CP98-761 |  |  | 21300000 | 45
| Viking |  | 2001 Expansion | Emerson to Marshfield |  | 2001-11-01 | Low |  | CP98-762 |  |  | 21300001 | 46
| Viking, TCPL & NICOR |  | Viking Voyaguer | Marshfield, WI to Minn, ND, Wisc and Chicago | 1400000 | 1999-11-01 | Dead |  | CP98-60/62/64/65 |  |  | 1200000000 | 773
| Westcoast |  | Sunshine Coast Regional Dist | MSQ | 3000000 | 2000-05-01 | Dead |  |  |  |  | 87000000
| Westcoast |  | West Liard - NWT Pipeline | West Liard valley to Northern BC (Alliance) | 50000 | 2000-05-01 | Done
| Westcoast |  | Howe Sound LNG | MSQ | 3000000 | 2001-11-01 | Low |  |  |  |  | 72000000
| Westcoast |  | Orca Natural Gas Pipeline | Sumas to Washington areas | 430000 | 2004-11-01 | On Hold |  |  |  |  | 195000000 | 140 | 22000
| Westcoast/Cascade/Puget Sound |  | Orca Gas Pipeline | Sumas to Puget Sound |  | 2004 | [6 empty] | 140
| Western Hub Partners |  | LODI Storage | Connects to PG&E | 12.0 Bcf | 2001 | [5 empty] | 80000000 | 35
| Western Hub Partners |  | Wheeler Ridege Storage |  | 12.0 Bcf | 2004
| WIC |  |  | Kanda to Tomohawk | 192000 | 1997-08-01 | Done |  | CP96-288 |  |  | 39933100 |  | 28612
| Williams |  | Kerr McGee Boomvang/Nansen | connects to CTGS | 300000 | 2001-11-01 | Med |  |  |  |  | 200000000 | 55
| Williams Natural Gas |  | Rawlins-Hesston | Wyoming (Wamsutter) to Kansas | 30000 | 1997-11-01 | Done |  | CP97-7 |  |  | 9300000
| Williams Natural Gas |  | St, Louis Access | Conversion of 200 mile petroleum pipeline | 28000 | 1998-10-01 | Done
| Williams Natural Gas |  | SW Missouri Expansion | waiting on Missouri Comm approval | 15610 | 1999-05-01 | Done |  | CP96-726 |  | 20 |  | 12.5
| Williams Natural Gas |  | Ottowa Compressor Station | Compression Upgrades/Additions | 44200 | 2001-06-01 | Done |  | CP00-82 |  |  | 9700000 | 1.5
| Williams Natural Gas |  | Blackwell-Cotton Valley Pipeline | Compression Upgrades/Additions | 55000 | 2001-07-01 | High | [5 empty] | 37
| Williams Natural Gas |  | Western Farmers | Cheyenne Hub to Hugoton | 540000 | 2003-11-01 | Low | [5 empty] | 400 | 13000
| Williams/BC Hydro |  | Gerogia Straight Crossing | Sumas to Vancouver Island | 100000 | 2002-11-01 | Med | NEB Filed |  |  |  | 120000000 | 85
Note on B67: ECT: one third ownership each
Note on B359: ECT: Trunkline, Marathon Ashland Petroleum and TEPPCO Partners LP
Note on D228: julie gomez: Uses Tennessee 500 line capacity
Note on D253: Julie Gomez: Serves 620 MW Presidente Juarez power plant
Note on D263: ECT: The LNG will come from output from the planned second and third trains of Atlantic LNG project in Trinidad and Tobago.
Note on D375: ECT: Producers include Chevron Canada, Canadian Forest, Ranger, Purcell, Anderson Exploration and Talisman
Note on E67: ECT: Proposed to connect to Alliance, NBPL, NGPL, Midwestern and Joliet Hub
Note on E111: ECT: To serve the existing 150MW Hermosillo Plant and a proposed 225MW expansion plant. The 12 mile east branch line will cross the border near Douglas and serve the proposed 225MW El Fresnal/Nogales plant.
Note on E252: ECT: Scana would extend the system 300 miles to the proposed ethanol facilities and power plants in Onslow, Greene and Martin Counties, NC
Note on E254: Julie Gomez: Will interconnect with Sempra'a Rosarito Pipelien south of Tijuana
Note on E263: ECT: Can take delivery of 80 Bcf annually, or 220,000 M/d fo LNG starting mid 2002
Note on E299: jgomez: 19,100 via National Fuel lease from Niagara, the rest is from the Gulf Coast.
Note on E336: ECT: Southern Company's capacity is in the name of Georgia Power for the Wansley Plant
Note on E355: ECT: Includes 50,000/d of capacity from Blanco to Thoreau
Note on E389: ECT: The Canadian portion of the project would originate on the international border in Boundry Pass, Strait of Georgia and interconnect with the existing Centra transmission system at a point south of Duncan, BC. The Canadian portion would be about 31 miles long with about 23 miles offshore and eight miles onshore. The 16" pipe would move 100,000 M/d and be in service 11/2002
Note on F13: jgomez: Dighton Power Assoc 33,000/d from Mendon to Dighton Plant
Note on F14: jgomez: Tiverton Power Accos 46000/d Brookfield to Plant
Note on F15: jgomez: Lake Road Generating 146000/d from mainline to plant
Note on F16: jgomez: ANP Bellingham Energy 110,000/d Mainline Int to Plant
Note on F17: jgomez: Sithe Power Marketing 140000/d lateral only
Note on F18: Shippers inlcude: Sithe 70,000/d, Southern Kendall 35,000/d Southern Connecticut 20,000 Prov Gas 500/d Mass Water Resource Auth 25,000/d and TETCO 80,000/d
Note on F19: jgomez: Shippers include: Boston Gas 35000/d, ConEd 20000/d and ProvGas 95000/d.
Note on F23: ECT: 600,000/d ??
Note on F30: Julie Gomez: DirectLink 507,000/d (contract not allowed by FERC), Dynegy 303,900/d, Cogentrix 101,300/d, Gleason 80,000/d and Duke 50,700/d
Note on F34: ECT: 59,000/d contracted to three shippers and an additional 25,000/d as of 11/1/01
Note on F42: jgomez: 171,000 capacity for the public
Note on F52: julie gomez: Primero Gas Marketing and El Paso Energy Raton LLC
Note on F54: jgomez: Shippers include Front Range Power 85,000/d, PSCO 178,000/d
Note on F62: ECT: WGR anchored
Note on F67: ECT: WICOR is 650,000/d
Note on F77: jgomez: Shippers Include: Entergy Miss 200000/d and Warren Power 85000/d.
Note on F101: Julie Gomez: 125,000 is incremental capacity and the remaining 489,628 would be leased back to Transco.
Note on F104: julie gomez: UCG 27,500, Citizens, APG Industries and City of Pulaski
Note on F125: ECT: FPL 101142/d. Southern 60937/d, TECO 180,000/d, JEA 14000/d, Tallahassee 2677/d, Peoples 1504/d, US Agri-Chem 115/d
Note on F144: jgomez: Shippers include: Keyspan Ravenswood 60000/d, Engage 90000/d, Riverbay Corp 11470/d, Astoria Generating (Orion) 200000 and ConEd 200000.
Note on F150: ECT: Nicor is 300,000/d
Note on F167: jgomez: Casco Bay 105000/d from Ediington to Veazie Plant
Note on F184: jgomez: Shippers include: Aquila 16819/d, El Paso Energy 20000/d and FP&L 19100/d
Note on F185: jgomez: National Fuel Distribution 30,000/d from Lamont to Roystone
Note on F214: ECT: PITCO's 60% of Max DQ
Note on F228: julie gomez: Southern Co bought 7Bcf of storage at Petal and can deliver to Transco, SoNat, Koch and Deston
Note on F244: jgomez: Shippers include CIG Resources 150,000/d, Questar Gas 100,000/d and 40,000 Texaco
Note on F256: jgomez: Shippers inlcude: CE Minerals 782/d, City of Lenox 12/d, Coral Energy 6646/d, Interconn 6646/d, Milwhite 80/d, MGAG 1270/d and P&G Paper 1564/d.
Note on F263: ECT: 540,000 Peak Day Deliverability
Note on F266: jgomez: Shippers include Coral 6,646/d Interconn 6646/d, P&G Paper 1,564/d MGAG 1270/d CE Mineral 782/d milwhite 80/d and City of Lenox 12/d.
Note on F267: ECT: 15 year contracts with Southern Co 284,050 South Carolina PL Corp 50,000 LaGrange, GA 1,750 Phase I of 88,150 will start June 1, 2002
Note on F269: jgomez: AGL signed up for 200,000/d for 20 years.
Note on F296: Julie Gomez: Could be expanded to 1.0 Bcf/d. NJ Natural controls Shipper is eCorp.
Note on F298: jgomez: Shippers inlcude: ANP 34000/dand El Paso Gas Svs 139000/d
Note on F316: jgomez: Shippers include: Western Gas 57,500/d, ENA 41,000/d, CMS 100,000/d, Barrett 70,000/d, Devon Energy 33,000/d and Pennaco 22,500/d.
Note on F334: ECT: Southern Company 40,000/d, Visy Paper 4500/d and AGL 61160/d Santee Cooper 80,000/d, Sylacaugh Utilities Board 4000/d, MGAG 14,439/d
Note on F335: Julie Gomez: Willaims 100,000/d, ConEd 30,000/d,Aquila 25,000/d, ConEd Energy 10,000/d and St Lawrence Cement 1,000/d
Note on F336: ECT: Southern Company 140000/d and CP&L 75000/d
Note on F337: jgomez: Virginia Power 100,000/d and PPL 30,000/d
Note on F340: ECT: DirectLink (an affiliate) has contracted for 500,000/d. Dynegy has contracted for 350,000/d.
Note on F379: ECT: 400,000/d MDIQ 500,000/d MDWQ
Note on F384: ECT: LaClede subscribed
Note on F386: ECT: MEP Pleasant Hill Generating Unit (600MW) and Tyson Foods
Note on F387: ECT: Empire District Electric Company State Line Plant in Jasper Co, MO 500 MW (CC)
Note on F389: ECT: BC Hydro has sined up for 97,000/d of capacity Connects two 250MW plants on Shawnigan Lake (81,000/d) and the local LDC Centra Gas
Note on M296: Julie Gomez: ecorp Marketing (an affiliate of Central New York) has 400,000/d on the lateral and 90,000/d on Tennessee's 300 line
Note on M297: ECT: AES signed for 20 year 10 month contract at a negotiated rate of $.0425 plus fuel
Note on O305: julie gomez: PSI (Cynergi) will reimburse Midw for $6.3 mil
Note on P80: ECT: 30" pipeline

## By Date
ENRON NORTH AMERICA |  |  |  | 2026-07-29 07:08 |  | expands2
PIPELINE EXPANSION UPDATE
Project
[5 empty] | Daily | Start |  | ECT |  |  | Term | Cost of
| Pipeline |  | Project | Path | Quantity | Date | Probability | Position | Docket | Pricing | Years | Project | Miles | HP
| Transco |  | Southeast Mainline Exp I | Stn 85 to Stn 150 NC | 35000 | 1994-11-01 | Done |  | CP94-68
| Stingray Pipeline Company |  | Garden Banks 72/VER Blocks | GB 72 to Stingray at VER 362 lateral | 100000 | 1995-11-01 | Done |  | CP96-91 |  |  | 9000000 | 15
| Transco |  | Southeast Mainline Exp II | Stn 85 to Stn 150 NC | 115000 | 1995-11-01 | Done |  | CP94-109
| CMS |  | Little Bear PL | Michigan Production | 75000 | 1996-08-01 | Done |  | Non-Jurisdictional |  |  | 13600000
| Mississippi Canyon Gath System |  | Shell (Mars, Ursa, Mensa) | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 600000 | 1996-09-01 | Done |  | CP96-159 |  |  | 75000000 | 45
| CIG |  | Parachute Creek lateral | Uinta Lateral to Parachute | 37000 | 1996-09-27 | Done
| ANR |  | Link Pipeline | Michigan to Consumers of Toronto | 150000 | 1996-11-01 | Done |  | CP93-564
| Great Lakes |  | River Crossing Security | Zone 3 - Under the St. Clair River | 50000 | 1996-11-01 | Done |  | CP96-26 |  | 2 | 3900000
| Great Lakes |  | Security Loop I | Looping in Lower Michigan | 5000 | 1996-11-01 | Done |  | CP95-375 |  |  | 17400000 | 14 | 14800
| Iroquois |  |  | Waddington to S. Comack | 35000 | 1996-11-01 | Done | 15000 | NA |  | 10
| Southern |  | North System | North System to Chattanooga | 25000 | 1996-11-01 | Done |  | CP94-682
| TCPL |  | Conventional 96 | Alberta to Ontario/Export | 150000 | 1996-11-01 | Done | 15000 |  |  |  | 489000
| Transco |  | Southeast Mainline Exp III | Stn 85 to Stn 150 NC | 50000 | 1996-11-01 | Done |  | CP94-109
| Viking |  |  | Emerson to NNG | 20000 | 1996-11-01 | Done |  | CP96-32 |  |  | 8400000
| Sabine |  |  | HPL to Henry | 30000 | 1996-12-01 | Done
| TransColorado |  | Phase I | Rio Blanco, CO to EP Blanco | 75000 | 1996-12-01 | Done |  | CP90-1777 |  |  | 14100000
| Transwestern |  |  | San Juan Lateral | 255000 | 1996-12-01 | Done | 8000 | CP96-10 |  |  | 14600000
| Transwestern |  |  | Thoreau to East | 107000 | 1996-12-01 | Done | 8000
| Delhi |  | East Texas Cotton Valley | Pinnacle Reef Gathering Capacity | 275000 | 1997-04-01 | Done |  | Non-Jurisdictional
| Garden Banks Pipeline |  | Shell/Hess (Ench/Auger/Bladpate) | GB 128A (Enchilada) to SMI 76 (BlueW/TRCO) | 600000 | 1997-04-01 | Done |  | CP96-679 |  |  | 108000000 | 50
| TransOk |  | Trident Ambrose Plant | Cushing to Blackwell, OK | 300000 | 1997-04-01 | Done |  | Non-Jurisdictional |  |  | 35000000
| El Paso |  | Havasu | San Juan to East | 184140 | 1997-05-01 | Done | 16495 | CP96-321 |  |  | 19564419
| ANR |  | Michigan Leg South Looping | Bridgman to Sandwich Compressors | 135000 | 1997-06-01 | Done |  | CP96-641 |  |  | 18000000 | 12
| TransOk |  |  | Bradley to Atoka, OK (Texoma) | 0 | 1997-07-01 | Dead |  | Non-Jurisdictional |  |  | 40000000
| Valero |  | Texas Expansion I | Bethel - Pinnacle Reef to Carthage Hub | 250000 | 1997-07-01 | Done |  | Non-Jurisdictional |  |  | 11700000
| CIG |  | Wind River | Lateral Expansion | 68000 | 1997-08-01 | Done |  | CP96-289 |  |  | 10844200 |  | 10566
| KNE |  | Pony Express | Wind River Basin to Kansas City | 135000 | 1997-08-01 | Done |  | CP96-477
| Questar |  | Phase I | Clay Basin Storage to Kanda | 59000 | 1997-08-01 | Done - at risk |  | CP96-820
| Trailblazer |  |  | Tomahawk to NGPL | 104500 | 1997-08-01 | Done |  | CP96-506 |  | 10 | 11663000 |  | 5200
| WIC |  |  | Kanda to Tomohawk | 192000 | 1997-08-01 | Done |  | CP96-288 |  |  | 39933100 |  | 28612
| Columbia Gas |  | Storage | Storage Withdrawal | 210000 | 1997-11-01 | Done |  | CP96-213 |  | 15 | 270000000 | 42 | 45699
| Columbia Gas/TETCO |  |  | Capacity Lease | 141500 | 1997-11-01 | Done |  | CP96-559 |  | 17 | 63200000
| Dominion |  |  | Transport increase | 102820 | 1997-11-01 | Done |  | CP96-492 |  |  | 55929000 | 36 | 13600
| East Tennessee |  | System Wide | Knoxville Area | 31902 | 1997-11-01 | Done |  | CP96-696 |  | 3-10 | 12915473
| Florida Gas Transmission |  |  | Texas to Louisiana |  | 1997-11-01 | Dead
| Koch Gateway Pipeline |  | Venice Expansion | Venice to Koch Mainline | 615000 | 1997-11-01 | Done |  | CP96-572 |  |  | 20500000
| National Fuel |  |  | Niagara to Leidy | 25000 | 1997-11-01 | Done | 25000 | CP96-671 |  | 10 | 10600000 |  | 1300
| NGPL |  | Louisiana Line Expansion | Compression | 0 | 1997-11-01 | Dead |  | CP96-720 |  | 7 | 4300000
| NGPL |  |  | Gage to Chicago |  | 1997-11-01 | Dead
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 244000 | 1997-11-01 | Done |  | CP97-25 |  |  | 102000000 | 50 | 41000
| Ozark |  |  | Oklahoma to Louisiana | 0 | 1997-11-01 | Dead
| PEPL |  | Tuscola to Illinois | Replaced by Spectrum Project | 0 | 1997-11-01 | Dead
| South Carolina Pipeline |  | New compressor - Blacksburg | Increase Transco takeaway | 75000 | 1997-11-01 | Done |  | Non-Jurisdictional |  |  | 10000000
| Southern |  | Zone 3 Markets | MS/AL Loops - Wren/Savannah Line | 45880 | 1997-11-01 | Done |  | CP96-541 |  | 10 | 36043000 | 28 | 10640
| Southern |  | N. Louisiana | Texas to Louisiana |  | 1997-11-01 | Dead
| TCPL |  | Conventional 97 | Alberta to Ontario/Export | 286700 | 1997-11-01 | Done | 20000 |  |  |  | 900000000
| Tennessee |  | Niagara Expansion | National Fuel Compressor Expansion | 21344 | 1997-11-01 | Done |  | CP96-721 |  |  | 51620
| TETCO/Dominion |  | WinterNet | Oakford Storage to CNG (Phased) | 0 | 1997-11-01 | Dead |  | CP96-606 |  | 24 | 18589000
| Transco |  | Pocono Expansion Project | Leidy to Northhampton County, PA | 35000 | 1997-11-01 | Done |  | CP97-328 |  | 15 | 9800000
| Transco |  | Seaboard 97 (or so) | Leidy to New York City | 0 | 1997-11-01 | Dead | 30000 | CP96-545 |  | 15-21 | 117700000
| Transco |  | SunBelt | 100 Stn 65 to Stn 85, 146 Stn 85 to Stn 145 NC | 145666 | 1997-11-01 | Done |  | CP96-16 |  | 20 | 85000000 | 15 | 30000
| Trunkline |  |  | Katy to Henry | 0 | 1997-11-01 | Dead
| Vermont Gas Systems |  |  | Import at Highgate Springs, Vermont | 52000 | 1997-11-01 | Done |  | CP97-324
| Viking |  |  | Emerson to NNG | 61300 | 1997-11-01 | Done |  | CP97-93 |  |  | 27900000
| Williams Natural Gas |  | Rawlins-Hesston | Wyoming (Wamsutter) to Kansas | 30000 | 1997-11-01 | Done |  | CP97-7 |  |  | 9300000
| KNE |  | Pony Express | Dull Knife to Kansas City | 120000 | 1997-12-01 | Done |  | CP96-477 |  |  | 154000000 | 804
| NGPL |  |  | Arkoma to Henry | 0 | 1997-12-01 | Dead
| Transco |  | Maiden Lateral | Expansion to Piedmont | 69000 | 1997-12-01 | Done |  | CP97-193 |  |  | 13200000 | 18
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | GC 65 (Bullwinkle) to Ship Shoal 207 (Nautilus) | 300000 | 1997-12-15 | Done |  | CP96-796
| Nautilus Pipeline |  | Shell | SS 207 to South Bend, LA (Troika) to ANR | 600000 | 1997-12-15 | Done |  | CP96-790/791/792 |  |  | 121000000 | 101
| Discovery Gas Transmission |  | Texaco/MAPCO/British Borneo (Hardy/Allegheny/Morpeth) | ST 200, GI 115 & EB 873 to Larose, LA | 600000 | 1998-01-01 | Done |  | CP96-712 |  |  | 300000000 | 147
| Dauphin Island Gath System |  | Phase I | Main Pass 225 to AST 73 | 200000 | 1998-04-01 | Done |  | CP97-301 |  |  | 54000000 | 63
| Transwestern |  | San Juan Junior | Ignacio to Blanco | 0 | 1998-04-01 | Dead | 45000 | CP97-516 |  |  | 21000000 |  | 22000
| Transwestern |  | San Juan Junior | Blanco to Thoreau | 0 | 1998-04-01 | Dead | 45000 | CP97-517
| Questar |  | Clay Basin Expansion | Increase by 4.0 Bcf (by adding cushion gas) | 88000 | 1998-05-01 | Done |  | CP96-820 |  |  | 18000000 | 41 | 110
| Trunkline |  | SS Block 139 Compression | SS 139 to Patterson (upstream of constraints) | 500000 | 1998-05-01 | Done |  | CP97-105 |  |  | 52217940 |  | 28950
| El Paso |  | Samalayucca II (Phase I) | Waco Station to PEMEX Juarez (Guars) | 72000 | 1998-06-01 | Done | PEMEX | CP93-252 |  |  | 18200000 | 20
| Valero |  | Texas Expansion II | Bethel - Pinnacle Reef to Carthage Hub | 0 | 1998-06-01 | Dead |  | Non-Jurisdictional
| Questar |  | Phase II | Clay Basin Storage to Kanda | 25000 | 1998-08-01 | Done - at risk |  | CP96-820 |  |  | 18000000 | 41 | 110
| Transco |  | Mobile Bay Extension | Main Pass 261 to Mobile Bay 822 to Stn 82 | 350000 | 1998-08-01 | Done | WESCO | CP97-92 |  | 15 | 120200000 | 77 | 30000 | Totally in-service on Nov. 9
| Transco |  | Mobile Bay Expansion | Station 85 | 128137 | 1998-08-01 | Done |  | CP97-93
| CIG |  | Campo Lateral | Pickwick Lateral to Campo Station | 107000 | 1998-09-01 | Done |  | CP97-769
| Destin Pipeline Svs Company |  | Shell/Amoco | MP/VK to Pascagoula Area (VK 915 Marlin) | 1000000 | 1998-09-01 | Done |  | CP96-655 |  |  | 308000000 | 210 | 26400
| Southern Natural Gas | 1 | Lease of Capacity by Destin | Destin delivery into SoNat to TETCO Cranfield | 200000 | 1998-09-01 | Order disallowed roll-in |  | CP96-655 |  | 20
| Dauphin Island Gath System |  | Phase II | Alabama State Tract 73 to Transco/Colden, AL | 300000 | 1998-10-01 | Done |  | CP98-6 |  |  | 19000000 | 13
| El Paso |  | Samalayucca II (Phase II) | Waco Station to PEMEX Juarez (Guars) | 100000 | 1998-10-01 | Done | Samal..
| Williams Natural Gas |  | St, Louis Access | Conversion of 200 mile petroleum pipeline | 28000 | 1998-10-01 | Done
| Alberta Pipeline Project |  | CU Gas Ltd, Amoco & Shell Can. | Central Alberta to Carbon Hub to Empress | 0 | 1998-11-01 | Dead |  |  |  |  | 326868598.8233
| CIG/PSCO |  | Front Range Pipeline | Cheyenne Compressor to Ft. St. Vrain | 269000 | 1998-11-01 | Done |  | CP98- |  |  | 25000000 | 53
| CIG/WIC |  | Powder River Lateral | Compression at Laramie & Cheyenne | 49000 | 1998-11-01 | Done |  | CP98-128 |  | 10 | 15000000 |  | 7380
| Columbia Gas |  | Storage | Storage Withdrawal | 126000 | 1998-11-01 | Done |  | CP96-213 |  | 15
| Columbia Gulf |  | Onshore Louisiana | Eastern Legs to Rayne (3 phases) | 0 | 1998-11-01 | Dead
| Crowsnest Pipeline |  | CU Gas Ltd and Shell Canada | Waterton Plant to ANG station 4 (BC) | 0 | 1998-11-01 | Dead
| Dominion |  | Market Value Project | Lebanon to Leidy and CNG Citygates | 0 | 1998-11-01 | Dead
| East Tennessee |  | Virginia Expansion Project | Greenbriar, TN to Chilhowie & Roanoke, VA | 10300 | 1998-11-01 | Done | Roanoke Gas | CP98-40 |  | 20 | 8600000 | 10
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 0 | 1998-11-01 | Dead |  |  |  |  | 1000000000
| Great Lakes |  | Security Loop II | Looping in Delta and Mackinac Counties, MI | 5000 | 1998-11-01 | Done |  | CP96-297 |  |  | 44300000 | 25
| Great Lakes |  |  | Emerson to St. Clair | 126000 | 1998-11-01 | Done | 30000 | CP96-647 |  |  | 149000000 | 72 | 14800
| Iroquois |  | Athens | Waddington to Brookfield | 30160 | 1998-11-01 | Done |  | CP96-687 |  | 10 | 22000000 |  | 9500
| Koch Gateway |  | East Texas | Carthage to Perryville | 0 | 1998-11-01 | Dead |  |  |  |  | 31000000
| National Fuel |  | Son of Seaboard | Niagara to Leidy | 0 | 1998-11-01 | Dead
| NGPL |  | Chicago | Harper to Chicago | 110000 | 1998-11-01 | Done | 10000 | CP96-27 |  |  | 24000000 | 5 | 9000
| Noram |  | North Louisiana Expansion | Carthage to Perryville Hub | 170000 | 1998-11-01 | Done | UPRC 50/Amoco 15 | CP97-724 |  | 10/5 | 32200000
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 32000 | 1998-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | NNG Zone E/F Koch | NNG Market Area Expansion (Rosemount) | 20000 | 1998-11-01 | Done - At Risk |  | CP98-132 |  |  | 9400000
| Pacific Gas Transmission |  | Kingsgate to Malin | Duke, Montana Power, El Paso, POCO, Avista | 57000 | 1998-11-01 | Done |  | CP98-167 |  | 3-15 | 6000000
| Southern |  | Zone 2 and 3 Markets | MS/AL Loops | 64911 | 1998-11-01 | Done |  | CP97-526 |  | 12 | 52179005
| TCPL |  | Nexus 98 | Alberta to Ontario/Export | 0 | 1998-11-01 | Dead |  |  |  |  | 1190000000
| TCPL |  | Conventional 98 | 58.5 Domestic/397.4 Export | 455900 | 1998-11-01 | Done | 33539 |  |  |  | 877600000
| Tennessee |  | DOMAC Expansion | DOMAC Everett Plant to Saugus, Mass | 90000 | 1998-11-01 | Done |  | CP96-194 |  |  | 25900000 | 8
| Tennessee/Leviathon |  | Viosca Knoll Expansion | Looping of existing VK Line (Bi-flow) | 250000 | 1998-11-01 | Done
| Texas Eastern |  | Spectrum Related | Lebanon Lateral Expansion | 302290 | 1998-11-01 | Done |  | CP98-336 |  |  | 31000000 |  | 17070 | (Gas City and Glen Karn)
| Texas Gas Transmission |  | Carthage Expansion | Haughton Comp Stn to Bossier Parish, LA | 105000 | 1998-11-01 | Done | UPRC | CP97-656 |  | 10 | 5980000 |  | 4600
| Transco |  | Cherokee Expansion | Stn 85 to Stn 130 Madison Co., GA | 87070 | 1998-11-01 | Done |  | CP97-331 |  | 15 | 68000000 | 15 | 23000
| Transco |  | Mobile Bay Expansion II | Station 85 | 135711 | 1998-11-01 | Done |  | CP97-94
| TransQuebec & Martimies PL |  | TQM Extension | Lachenaie, PQ to East Hereford, NH | 194000 | 1998-11-01 | Done |  |  |  |  | 175000000 | 135
| Union Gas |  |  | System-wide |  | 1998-11-01 | Dead
| Venice Gathering System LLC |  | Venice Expansion |  | 328000 | 1998-11-01 | Done |  | CP97-533/534 |  |  | 40000000 | 52
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Suffield, Alberta to TCPL/Burstall, Sask | 200000 | 1998-12-01 | Done | NEB approval 8/98 |  |  |  | 26200000
| Foothills |  | NBPL Expansion | Nova to NBPL | 698900 | 1998-12-01 | Done | 15000 |  |  |  | 125000000 | 71 | 51000
| Northern Border |  | Expansion | Monchy to Harper | 700463 | 1998-12-01 | Done | 55000 | CP95-194 |  |  | 457900000
| Northern Border |  | Extension | Harper to Chicago | 663050 | 1998-12-01 | Done | 45000 | CP95-194 |  |  | 338900000 | 793 | 293000
| Nova |  | NBPL Expansion | Alberta to Foothills | 500000 | 1998-12-01 | Done | 15000 |  |  |  | 365400000
| Southern |  | Zone 2 Markets | Alabama Power | 34925 | 1998-12-01 | Done |  | CP97-526 | Increm | 12 | 52179005
| El Paso |  | Bondad Compressor Expansion | Ignacio to Blanco Station | 0 | 1999-01-01 | Dead | 100000 | CP98-149 |  |  | 3600000 |  | 5160
| Portland/Maritimes |  | Joint Line Application |  |  | 1999-02-01 | Done |  | CP97-238 |  |  | CP96-178 ???
| Transco |  | Genesis Field | Green Canyon 205 to Transco Ship Shoal | 72000 | 1999-02-01 | Done |  | Non-Jurisdictional
| TransColorado |  | Phase II | Rio Blanco, CO to EP Blanco | 45000 | 1999-02-01 | Done |  | CP90-1777
| Algonquin |  | EMI Dighton, MA Plant | Delivery off mainline to Dighton Plant | 33000 | 1999-03-01 | Done |  | CP98-99 |  |  | 4662000 | 1.5 | 900
| ANR |  | Wisconsin Loop Expansion Proj | 11.7 miles of 30" looping from Joliet to WI | 116000 | 1999-03-01 | Done |  | CP97-765 |  |  | 24000000 | 11
| Portland Natural Gas Transmission |  | Granite State PL replacement | TCPL to Tennessee at Haverhill, Mass. | 178000 | 1999-03-01 | Done | 30000 | CP96-248 |  | 15-20 | 270000000 | 243
| TransColorado |  | KN/Questar | NW Colorado to Red Cedar Lateral | 300000 | 1999-03-01 | Done |  | CP90-1777 |  |  | 170900000 | 295
| AEC |  | Wild Goose Storage | PG&E/Scramento Area | 14.0 Bcf | 1999-04-01 | Done |  | Non-Jurisdictional
| Williams Natural Gas |  | SW Missouri Expansion | waiting on Missouri Comm approval | 15610 | 1999-05-01 | Done |  | CP96-726 |  | 20 |  | 12.5
| Mississippi Canyon Gath System II |  | Compression upgrades | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 200000 | 1999-07-01 | Done |  |  |  |  | 216000
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering | Gillette, WY to Glenrock, WY | 434000 | 1999-09-01 | Done |  |  |  |  | 43000000 | 106
| Transco |  | SE Louisiana Crossover | Garden Banks PL @ SMI 76 to Station 50 | 264020 | 1999-09-01 | Done | at risk | CP99-76 |  | Hess | 80000000 | 53
| Transco |  | SE Louisiana Crossover | SMI 76 to VER 67 offshore | 141970 | 1999-09-01 | Done | at risk | CP99-76
| CIG |  | Wind River II | Lateral Expansion to NWPL/Kern (westward) |  | 1999-10-01 | Dead
| KNE |  | Wyoming Pipeline Project | Wind & Powder River/Big Horn to Rockport |  | 1999-10-01 | Dead |  |  |  |  | 110000000
| Tenneco |  | Donna Lateral | Extension to Reynosa | 220000 | 1999-10-01 | Done |  | CP98-28 |  |  | 15000000 | 10
| Alberta Pipeline Project |  | Phase II | Kaybob region extension |  | 1999-11-01 | Dead |  |  |  |  | 326868598.8233
| Algonquin LNG |  | Providence, RI tie to Algonquin | Northeast City Gates (currently 100,000) | 150000 | 1999-11-01 | Done |  | CP99-113 |  |  | 10705000
| ANR |  | Katy Project | Katy to Eunice |  | 1999-11-01 | Dead
| Columbia Gas |  | Storage | Storage Withdrawal | 80000 | 1999-11-01 | Done |  | CP96-213 |  | 15
| Destin Pipeline Svs Company |  | Shell/Amoco | New Lateral MP 283 to MP 279 (Gemini) | 111675 | 1999-11-01 | Done | Mobil & Phillips | CP98-512 |  |  | 7200000 | 31
| Dominion |  | Bath Petroleum | Storage Withdrawal |  | 1999-11-01 | Dead |  | CP96-492
| Duke Energy |  | Spectrum | Chicago to New Jersey |  | 1999-11-01 | Dead |  | CP97-626
| El Paso Field Services |  | Diana Line | East Breaks 945/6 to HIOS @ EB 165 | 500000 | 1999-11-01 | Med
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS |  | 1999-11-01 | Dead |  |  |  |  | 1000000000
| Great Lakes |  | Security Loop III | Looping in Delta and Mackinac Counties, MI | 0 | 1999-11-01 | Done |  | CP98-143 |  |  | 11000000 | 14
| Great Lakes |  | Nexus 98/99 | Emerson to St. Clair |  | 1999-11-01 | Dead
| Green Canyon Gathering System |  | Tennessee/National Fuel | EB, GC & MC to Lafourche Parish, LA | 515000 | 1999-11-01 | Low |  | CP96-557 |  |  | 200000000 | 133
| KN/Devon |  | Thunder Creek Gas Gathering | Gillette, WY to Glenrock, WY | 450000 | 1999-11-01 | Done |  |  |  |  | 100000000 | 126
| Koch |  | Grand Isles Extension |  |  | 1999-11-01 | Dead | [5 empty] | 5
| National Fuel |  | Grandson of Seaboard | Niagara to Leidy |  | 1999-11-01 | Dead
| National Fuel |  | Ellisburg compression | Ellisburg to Leidy, PA | 60919 | 1999-11-01 | Done |  | CP99-160 |  |  | 223600 |  | 1245
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 31000 | 1999-11-01 | Done |  | CP97-25
| Northwest Pipeline |  | Columbia River Gorge Expansion | Stanfield to Sumas | 50000 | 1999-11-01 | Done | DETM | CP98-554 |  |  | 18570000 |  | 10870
| Northwest Pipeline |  | Jackson Prairie Expansion | Storage Field Expansion of 3.2 Bcf | 300000 | 1999-11-01 | Done |  | CP98-250 |  |  | 30192000 |  | 6960
| Penn West Petroleum, Ltd. |  | Wildboy Project | Wildboy Field (Fort Nelson, BC) to NOVA | 10000 | 1999-11-01 | Done |  |  |  |  | 15000000 | 40
| Pine Needle LNG |  | Transco/Piedmont | North Carolina Peaking 4 Bcf MSQ | 400000 | 1999-11-01 | Done |  | CP96-52 |  | 20 | 107000000
| Portland Natural Gas Transmission |  | TQM Link | TQM from Sable Island to Dracut, Mass |  | 1999-11-01 | Dead |  | CP96-249
| Tatham Offshore (Leviathon) |  | North Atlantic Pipeline Project | Hibernia/Sable Island to New England |  | 1999-11-01 | Dead |  | CP98-29/30/31/32
| TCPL |  | Nexus 99 | Alberta to Ontario/Export |  | 1999-11-01 | Dead
| TCPL |  | Conventional 99 | 108.0 Expansion/44.0 turnback | 108000 | 1999-11-01 | Done |  |  |  |  | 404500000
| TCPL |  | TransVoyageur Transmission | Empress, Alberta to Emerson, Manitoba |  | 1999-11-01 | Dead
| Tennessee |  | Ellisburg Extension (me too) | Niagara to Leidy |  | 1999-11-01 | Dead
| Tennessee |  | Eastern Express | Chicago to Leidy |  | 1999-11-01 | Dead
| Tennessee |  | Express 500 | 500 Line Expansion from offshore LA |  | 1999-11-01 | Low
| Transco/PSNC/Piedmont/NCNG |  | Cardinal Extension Co. | Stn 160 Rockingham, NC to Burlington, NC | 140000 | 1999-11-01 | Done |  | Non-Jurisdictional |  |  | 98300000 | 67
| Viking |  |  | Minnesota Looping | 28000 | 1999-11-01 | Done |  | CP98-761 |  |  | 21300000 | 45
| Viking, TCPL & NICOR |  | Viking Voyaguer | Marshfield, WI to Minn, ND, Wisc and Chicago |  | 1999-11-01 | Dead |  | CP98-60/62/64/65 |  |  | 1200000000 | 773
| CIG |  | Medicine Bow Lateral | Glenrock to Rockport | 368000 | 1999-12-01 | Done | WGR/CMS/ECT/MCN/Devon |  |  |  | 78200000 | 150
| CMS/ENA/NBPL |  | Bighorn Gas Gathering LLC |  | 250000 | 1999-12-01 | Done
| Columbia Gulf |  | Mainline 99 | Rayne to Leach (3 compression upgrades) | 315000 | 1999-12-01 | Done | 27%LDC/63%Mktg/10%Indust |  |  |  | 38000000
| Columbia Gulf |  | Sun Star (SP & WD to GI) | 2 new 24" laterals and one 30" mainline | 660000 | 1999-12-01 | Low | [5 empty] | 56
| Maritimes & Northeast |  | Sable Island Phase I | Wells, Maine to Dracut, MA (flows backwards) | 60000 | 1999-12-01 | Done |  | CP96-178 |  |  | 103726000
| Maritimes & Northeast |  | Sable Island Phase II | Sable Offshore Energy Int. to Dracut, Mass. | 360000 | 1999-12-01 | Done |  | CP96-809 |  |  | 79217000 | 454 | 31160
| Sable Offshore Energy Project |  | Maritimes and Northeast feed | Nova Scotia/New Brunswick to US | 400000 | 1999-12-01 | Done
| Sempra Energy International |  | Rosarito Power Plt/Vecinos | Riverside Co., CA to Tijuana | 500000 | 1999-12-01 | Done | Sempra | CP94-207 |  |  | 35000000 | 23
| El Paso |  | PEMEX | Waco Station to PEMEX Juarez (Guars) | 40000 | 2000-01-01 | Done
| Southern |  | North Alabama PL Exp | N. Alabama to Huntsville (Alatenn Bypass) | 76350 | 2000-01-01 | Done |  | CP96-153 |  |  | 66800000 | 118 | 6300
| Texas Eastern Transmission |  | Lease of Capacity by DIGP | Main Pass 164 to Venice Plant | 100000 | 2000-01-01 | Done | 15 | CP99-18 |  |  |  | 10
| Transwestern |  | Gallup Expansion | Thoreau to California Border | 140000 | 2000-05-01 | Done |  | CP99-552 |  |  | 11600000 |  | 10000
| Westcoast |  | Sunshine Coast Regional Dist | MSQ |  | 2000-05-01 | Dead |  |  |  |  | 87000000
| Westcoast |  | West Liard - NWT Pipeline | West Liard valley to Northern BC (Alliance) | 50000 | 2000-05-01 | Done
| Algonquin |  | EMI Tiverton Plant | Compressor Upgrades & mainline work | 46000 | 2000-06-01 | Done |  | CP99-46 |  |  | 13949960 | 15.98 | 900
| ANR |  | LS Power Batesville lateral | Panola, MS to Tennessee 20" | 235000 | 2000-06-01 | Done |  | CP98-801 |  |  |  | 15
| Questar |  | Fidlar Compressor Station | Expands southern part of system | 58850 | 2000-06-01 | Done |  | CP00-41 |  |  | 3325000 |  | 4829
| Reliant |  | SWEPCO Wilkes Plt Extension |  | 100000 | 2000-06-01 | Done | [5 empty] | 18
| TCPL |  | Merida III Power Plant | Ciudad Pemex, Tabasco to Campeche/Merida | 370000 | 2000-06-01 | Done
| Tennessee |  | LS Power Batesville lateral | Panola, MS to Tennessee | 216000 | 2000-06-01 | Done |  | CP98-770 |  |  |  | 3
| Texas Eastern |  | Duke Vermillion Lateral | Midwestern PL to the plant (Cayuga) | 200000 | 2000-06-01 | High |  | CP 00-67 |  |  | 13000000 | 14
| ANR/Leviathan/NGPL |  | East Breaks Gathering | Alaminos Canyon 25 to HIOS HI A-573 (Diana/Hoover) | 400000 | 2000-07-01 | Done |  |  |  |  | 90000000 | 85
| Maine Natural Gas |  | Westbrook Lateral | MN&E to the Calpine Westbrook Plant | 100000 | 2000-07-01 | High
| Maritimes & Northeast |  | Bangor Gas | Orrington, ME | 50000 | 2000-07-01 | Done |  | CP00-77 |  |  |  | 8.3 | 0
| Algonquin |  | Lake Road Plant | Mainline (Putnam Co) to Killingly CT Plant | 146000 | 2000-08-01 | Done |  | CP99-271 |  |  | 4700000 | 1.8 | 0
| CIG (WIC) |  | Medicine Bow Lateral II | Glenrock to Rockport | 120000 | 2000-08-01 | Done | WGR/CMS/ECT/MCN/Devon | CP99-624 |  |  | 12100000 | 6
| Tennessee |  | Honeoye Storage Expansion | 1.8 Bcf increase in working gas | 15000 | 2000-08-01 | Low |  | CP00-93 |  |  | 3000000
| Maritimes & Northeast |  | Gorham Lateral | Mainline to Gorham, ME Plant | 165000 | 2000-09-01 | Done |  | CP98-724 |  |  | 2000000 | 1
| TETCO |  | AES Ironwood Plant Lateral | Lateral in TETCO M3 (PA) | 120000 | 2000-09-01 | Done | 20 yr | CP99-621 |  |  | 5700000 | 3.6 | 0
| Algonquin |  | ANP Bellingham Lateral | Mainline (Norfolk Co, MA) to Bellingham Plant | 110000 | 2000-10-01 | Done |  | CP98-100 |  |  | 4593000 | 1.1 | 0
| Burlington Resources/ECT |  | Lost Creek Gathering | Madden Field, WY to Wamsutter Plant | 275000 | 2000-10-01 | Done |  |  |  |  | 69500000 | 124
| Questar |  | Southern System Expansion | Southern System to Clay Basin/Kanda |  | 2000-10-01 | Dead
| Questar |  | Wyoming Pipeline Project | Wyoming to Kanda (Pinedale Area Porduction) | 300000 | 2000-10-01 | Low
| Questar |  | Opal Connection | Seven miles to connect to Opal | 100000 | 2000-10-01 | Low
| ANR |  | Wisconsin Loop Expansion I | Comp. additions at Woodstock | 109000 | 2000-11-01 | Done |  | CP99-241 |  |  | 23800000 | 0 | 20000
| BC Gas |  | Alberta Southern Crossing | Alberta to BC interior | 105000 | 2000-11-01 | High | PG&E and BC Hydro |  |  |  | 376000000 | 194
| CIG |  | Pickerwire Lateral |  | 33000 | 2000-11-01 | Done
| CMS |  | TriState Pipeline | Chicago to Dawn |  | 2000-11-01 | Dead |  | CP99-63 |  |  | 361000000 | 226
| Continental States Peaking Svs |  | El Paso/Tennessee/MCN | Maryland/Delaware LNG 2.0 Bcf MSQ |  | 2000-11-01 | Dead |  |  |  |  | 45000000
| Coral Mexico |  | New PEMEX Line/Border Crossing | Kleburg County to Hildago Co., TX | 300000 | 2000-11-01 | Done |  | CP99-564 |  |  | 30000000 | 104
| Granite State |  | Wells LNG | Portland/Northern Utilities 2.0 Bcf MSQ |  | 2000-11-01 | Dead |  | CP96-610 |  | 20 | 44221000
| Great Lakes |  | 300 Expansion | Emerson to St. Clair |  | 2000-11-01 | Dead |  | CP98-309 |  |  | 620000000
| Iroquois/Tennessee |  | EPEM/PDC Milford Plant | Waddington to Milford/Tenn Zone 6 Delivery | 35000 | 2000-11-01 | High
| Maritimes & Northeast |  | Veazie Lateral | Eddington, ME to Veazie (Casco Bay Plant) | 105000 | 2000-11-01 | Done |  | CP98-797 |  |  | 6000000 | 1 | 0
| National Fuel |  | AM-60 Pipeline Replacement | Lamont, PA to Roystone, PA | 30000 | 2000-11-01 | Done |  |  |  |  | 11400000 | 12.9 | 360
| NGPL |  | Hub America | Chicago to Lebanon/TETCO M3 | 100000 | 2000-11-01 | High |  |  | rolled-in
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 21000 | 2000-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | East Leg 2000 | Replaced with Ill/WI Express |  | 2000-11-01 | replaced
| Northwest Pipelne |  | Silver Gem Lateral | Filer, Idaho to Wells, Nevada |  | 2000-11-01 | Dead
| TCPL/ANG Pipeline |  | Kootenay Pacific Pipeline | Yahk, BC to Vancouver/Sumas |  | 2000-11-01 | Dead |  |  |  |  | 530000000
| Tennessee |  | Texas Deepwater link Project | HIOS WC 167 to WC 180 (Tennessee) | 400000 | 2000-11-01 | Med | Vastar | CP00-441 |  |  | 14500000 | 17.5
| TETCO |  | Independence/ML Substitute | ANR/Muncie to Linden, NJ | 663000 | 2000-11-01 | Low
| TETCO |  | Excelsior | New Jersey to New York |  | 2000-11-01 | Dead
| Texas Eastern/NGPL |  | Enhanced Spectrum | Chicago Alliance to M3 | 55000 | 2000-11-01 | High |  |  | 0.46
| Transco |  | Cumberland Pipeline | Walton Co., GA to Chattanooga, TN |  | 2000-11-01 | Dead |  |  |  |  | 115000000 | 141
| Transco |  | Cumberland Pipeline II | Walton Co., GA to Chattanooga, TN |  | 2000-11-01 | Dead
| Transco |  | SouthCoast | Stn 85 to Zone 4 points north of Atlanta, GA | 204999 | 2000-11-01 | Done | PD recvd | CP99-392 | Southern Co 40,000/d | 15 | 108000000 | 44 | 31500
| Alliance |  | Fort St John, BC to Chicago | Canadian Side | 1325000 | 2000-12-01 | Done |  |  |  |  | 1600000000 | 1445
| Alliance |  | Fort St John, BC to Chicago | US Side |  | 2000-12-01 | Done |  | CP97-168 |  |  | 1400000000 | 887 | 320000
| Alliance |  | Chicago Portion | Aux Sable Liquids Plant |  | 2000-12-01 | Done |  |  |  |  | 365000000
| ANG/BC Pipeline |  | BC Pipeline (Southern Crossing) | Cranbrook to Kingsgate to Oliver | 250000 | 2000-12-01 | Done |  |  |  |  | 379000000 | 200
| Enbridge/MCN/Westcoast |  | Vector | Chicago to Dawn (with NIPSCO/Crossroads) | 700000 | 2000-12-01 | Done |  | CP98-131 |  | 10 | 443000000 | 270 | 60000
| Maritimes & Northeast |  | Halifax Lateral | NS Power Tufts Cove Plant | 166000 | 2000-12-01 | Done | [5 empty] | 63
| Midcon Texas |  | Roma Crossing | Bob West Field to Mexican Border | 275000 | 2000-12-01 | Med |  | CP96-770
| Midcon Texas |  | Monterey Pipeline Project | Cuidad Mier to Monterey | 275000 | 2000-12-01 | Med |  | CP96-583 |  |  | 520000 | 92
| NGPL |  | New York | Chicago to New York |  | 2000-12-01 | Dead
| CIG |  | Nixon Plant Lateral | CIG's Watkins Station to Colorado Springs | 85000 | 2000-12-02 | High
| Maritimes & Northeast |  | St John Lateral | JDI & NB Power Bayside Power Station | 105002 | 2001-01-01 | High |  | CP98-799 |  |  | 6000002 | 3
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | ST 292 to GI 116 (Anadarko/Hickory) | 300000 | 2001-03-01 | High | [5 empty] | 22
| Ricks Nova Scotia |  | Ladyfern Pipeline | NE BC to Nova's Owl Lake South Station | 30000 | 2001-03-01 | High | NEB approval 1/01 |  |  |  | 3000000 | 7.5
| TETCO |  | PSI Wabash Power Lateral | Midwestern Int at Vigo County, Ind | 215000 | 2001-04-01 | High |  |  |  |  | 8000000 | 9
| Canyon Express |  | Total/Fina/Elf | Aconcaqua/KingsPeak/CandemHills to EMP 261 | 500000 | 2001-05-01 | Med
| Columbia Gulf |  | Baxter Wilson & Warren Power | Warren Co., MS | 285000 | 2001-05-01 | High
| Columbia Gulf |  | Vicksburg Lateral to Entergy Plants | Mainline (Richland Parish, LA) to Baxter Wilson Plant | 285000 | 2001-05-01 | High |  | CP01-28 |  |  | 20148000 | 36.83 | 0
| Florida Gas Transmission |  | Phase IV | Central and South Central Florida | 272000 | 2001-05-01 | High | PD recvd | CP99-94 |  | DEIS | 351000000 | 205 | 48570
| Trunkline LNG |  | Lake Charles LNG regasification | No increase to terminal, just regasification | 300000 | 2001-05-01 | Med |  |  |  |  | 1155000
| Trunkline LNG |  | Lake Charles Terminal | Increase sendout from 0.7 to 1.0 Bcf | 300000 | 2001-05-01 | Med |  |  |  |  | 2250000
| Bay Gas |  | Mobile County Expansion |  |  | 2001-06-01 | Med | [5 empty] | 18
| CP&L |  | Iredell-Richmond Pipeline | Transco Stn 150 (Sundance) to CP&L Richmond Co | 200000 | 2001-06-01 | Med |  |  |  |  | 100000000 | 82
| El Paso |  | Willcox Lateral | Extension from Willcox to Douglas (Border) | 130000 | 2001-06-01 | High |  | CP99-322 |  |  | 30000000 | 56
| Petal Gas Storage |  | Hattiesburg Storage Lateral | Hattiesburg,MS to Destin, Koch, Sonat & Transco | 700000 | 2001-06-01 | Done |  | CP00-59 |  |  |  | 5.5 | 35000
| Questar/CIG |  | Southern System Expansion | Price, UT to Kern in Salt Lake City Area | 272000 | 2001-06-01 | High |  |  |  | 10 | 80850915 | 75.6 | 9336
| Reliant Energy Gas Transmission |  | Pine Bluff Plant Lateral (Skygen) | Jefferson Co, AR (Line AC) | 40000 | 2001-06-01 | High | Skygen | CP00-137 |  | 10 | 1500000 | 2
| Williams Natural Gas |  | Ottowa Compressor Station | Compression Upgrades/Additions | 44200 | 2001-06-01 | Done |  | CP00-82 |  |  | 9700000 | 1.5
| Williams Natural Gas |  | Blackwell-Cotton Valley Pipeline | Compression Upgrades/Additions | 55000 | 2001-07-01 | High | [5 empty] | 37
| Aiken Creek Storage |  | Unocal Canada | Increase working capacity to 80 Bcf |  | 2001-08-01 | High | [6 empty] | 18500
| Maine Natural Gas |  | Brunswick Lateral | MN&E to Brunswick and Topsham | 50000 | 2001-08-01 | High |  |  |  |  | 10000000 | 18
| Tennessee |  | Stagecoach Lateral | Central New York - Tennessee Line 300 | 500000 | 2001-08-01 | High | FEIS rcvd | CP 00-65 |  | 10 | 81271600 | 23.7 | 13400
| Algonquin |  | Sithe Energy Lateral | Lateral from Canton, MA to Plant (Fore River) | 140000 | 2001-09-01 | High |  | CP 00-34 | AFT-CL | 20 | 32021000 | 7.4 | 0
| Maritimes & Northeast |  | Four Rivers Plant |  |  | 2001-09-01 | Med
| CIG |  | Raton Basin Lateral Expansion | Morton Co, KS to Texas Co, OK | 85000 | 2001-10-01 | High |  | CP00-452 |  |  |  | 48
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering II | Gillette, WY to Glenrock, WY | 200000 | 2001-10-01 | Done |  |  |  |  | 27000000
| El Paso |  | Line 2000 - oil line conversion | Midland to Bakersfield (mostly replacement) | 0 | 2001-10-01 | High
| Questar |  | Southern Trails | San Juan to Long Beach | 120000 | 2001-10-01 | Med |  | CP99-163 |  |  | 155000000 | 705
| Southern Natural Gas |  | Wrens Compression Upgrade | Improve flow on Wrens/Savannah Line |  | 2001-10-01 | Done |  | CP00-231 |  |  | 5151438 |  | 3500
| Tennessee |  | Concord Lateral/AES Loundonderry | Dracut to Loundonderry, NH 20" replacement | 130000 | 2001-10-01 | Done |  | CP 00-48 |  | 20 | 324563678 | 19.3 | 0
| ANR |  | Mountaintop | Brownsville Compressor to Altanta, GA | 500000 | 2001-11-01 | Low
| ANR |  | Wisconsin Loop Expansion II | Comp. additions at Janesville/Weyauwega | 85000 | 2001-11-01 | Done |  | CP99-341 |  |  |  | 3 | 3000
| Crossroads |  | NBPL connection | 25 mile expansion to NGPL/NBPL | 485000 | 2001-11-01 | Low |  |  |  |  | 35000000 | 25
| Dominion |  | Capstone Project | South Webster to Northern CNG Gates (Tenn replacement) | 0 | 2001-11-01 | High |  | CP00-64 |  |  | 63502000 | 13 | 20250
| Dominion |  | Leidy Transportation Project | North Points (Empirer/Tenn/Iroquois) to Liedy | 300000 | 2001-11-01 | High
| Dominion/Tennessee |  | Atlantic Advantage Project | Chicago/Niagara to the Northeast | 0 | 2001-11-01 | Dead
| Duke Energy/Williams/Iroquois |  | Lighthouse Pipeline | Long Island to Milford, CT | 0 | 2001-11-01 | Dead |  |  |  |  | 240000000
| East Tennessee |  | Rocky Top Expansion | Greenbriar, TN to Chilhowie & Roanoke, VA | 35068 | 2001-11-01 | Done |  | CP00-51 |  | 10 | 18129000 | 28.73 | 0
| Enbridge/MCN/Westcoast |  | Vector Expansion | Compression | 300000 | 2001-11-01 | Med |  |  |  | 3
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 0 | 2001-11-01 | Dead
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 0 | 2001-11-01 | Dead
| Iroquois |  | Vermont Extension | EDC Bennington & Rutland Plants | 0 | 2001-11-01 | Dead |  |  |  |  | 105000000 | 70
| Kern River |  | Long Beach Extension | Bakersfield to Long Beach | 300000 | 2001-11-01 | Low
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 0 | 2001-11-01 | on hold
| MCN/Columbia Gulf |  | Volunteer Pipeline | Chicago (via Midw) to Atlanta | 250000 | 2001-11-01 | Low |  |  |  |  | 160000000
| Midwestern |  | PL Reversal | Chicago to Tennessee | 0 | 2001-11-01 | on hold
| Northern Border |  | Chicago Extension | Chicago to NIPSCO | 198300 | 2001-11-01 | High |  | CP99-21 |  |  | 93000000 | 34 | 30500
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 20000 | 2001-11-01 | Done |  | CP97-25
| Paiute Pipeline |  | System Expansion | Wells, Nevada to Paiute @ Elko, Nevada | 0 | 2001-11-01 | Dead | replaced
| Questar |  | Mainline 104 Expansion |  | 272000 | 2001-11-01 | Med | PD Recvd | CP00-68 |  |  | 80800000 | 75 | 9336
| South Georgia |  | Holy Trinity Looping | SoNat to South Georgia gates | 17000 | 2001-11-01 | High |  | CP01-95 |  |  | 5969100 | 7.1 | 0
| Southern Natural Gas |  | AL/GA Expansion |  | 17000 | 2001-11-01 | Med |  | CP01-35 |  |  | 6000000 | 7
| Southern/AGL |  | Etowah LNG | Polk County, Georgia 3 Bcf | 450000 | 2001-11-01 | Med |  | CP98-363 |  | 20
| Tennessee |  | Eastern Express 2001 | Dracut to New England | 288000 | 2001-11-01 | Done |  | CP99-262 | rolled in |  | 28143432 | 0 | 13320
| Tennessee |  | CanEast | Niagara/Gulf Coast to Leidy via CNG lease | 280000 | 2001-11-01 | High
| Totem Storage |  | CIG/PSCO connected storage facility' | 9 Bcf MSQ | 250000 | 2001-11-01 | Low
| Transco |  | MarketLink Phase I | Leidy to New York City | 166000 | 2001-11-01 | Done |  | CP98-540 |  |  | 123300000 | 60.6 | 30000
| Viking |  | 2001 Expansion | Emerson to Marshfield |  | 2001-11-01 | Low |  | CP98-762 |  |  | 21300001 | 46
| Westcoast |  | Howe Sound LNG | 3 Bcf MSQ | 0 | 2001-11-01 | Low |  |  |  |  | 72000000
| Williams |  | Kerr McGee Boomvang/Nansen | connects to CTGS | 300000 | 2001-11-01 | Med |  |  |  |  | 200000000 | 55
| CIG |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 0 | 2001-12-01 | Dead | replaced
| CIG (WIC) |  | Medicine Bow Lateral III | Glenrock to Rockport | 675000 | 2001-12-01 | High |  |  |  |  | 168000000 | 155 | 14340
| Leviathan/Tejas |  | Nemo Gathering | Brutus (GC 158) to Manta Ray | 150000 | 2001-12-01 | Med | [5 empty] | 24
| Trunkline |  | Centennial Project | 720 miles of 26" line (chicago to gulf) | -255000 | 2001-12-01 | Low |  | CP00-114 |  |  | -10200000
| El Paso |  | Yuma Extension | Yuma to Baja California (Mexicali) | 300000 | 2002-01-01 | Med |  |  |  |  | 143000000 | 94
| Southern LNG |  | Elba Island LNG Terminal | 4 Bcf Capacity | 330000 | 2002-01-01 | High | PD recvd | CP99-579 |  |  | 26200000
| TETCO |  | Phildelphia Lateral Expansion | Liberty Plants (Columbia and PG&E) | 84000 | 2002-01-01 | High |  | CP00-404 |  | 14.5 |  | 1 | 4000
| El Paso |  | Dumas Gas Transmission | Raton Basin to EPNG/NNG Dumas |  | 2002-04-01 | Med | [5 empty] | 185
| Florida Gas Transmission |  | Phase V | Plant Smith and Sanford Plant | 428000 | 2002-04-01 | High |  | CP00-40 |  |  | 466000000 | 191 | 125215
| KN Energy/NICOR |  | Horizon | Chicago | 380000 | 2002-04-01 | Med | PD recd | CP00-129 |  | 10 | 75000000 | 28.5 | 8900
| Panda |  | Trans-Union Interstate Pipeline | Claibourne Parish, LA to Arkansas Plant | 400000 | 2002-04-01 | Done |  | CP00-47 |  |  | 41000000 | 41.7
| Peoples/Coastal |  | Whitecap Energy - Land | ANR @ Crete, IL to Southeastern WI | 1500000 | 2002-04-01 | Low | 30000 |  |  |  | 334000000 | 21
| Southern/CP&L |  | Palmetto Interstate Pipeline | SoNat system expansion and extension from Aiken, SC to Robeson CO, NC (NCNG) | 250000 | 2002-04-01 | Dead |  |  |  |  | 450000000 | 175
| Transco |  | Sundance Pipeline | Station 65 to North Carolina (CP&L) | 236383 | 2002-04-01 | Med | PD recvd | CP00-165 | Incremental | 15 | 134674037 | 421 | 41225
| DOMAC |  | Sithe Mystic Plant Expansion | 4 submerged combustion vaporization units | 280000 | 2002-05-01 | High |  | CP00-447
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 124500 | 2002-05-01 | Med |  |  |  |  | 80000000 |  | 3 comps
| Gulf States Pipeline |  | Panda El Dorado Plant | Expansion from the Sharon La tie-in to TGP |  | 2002-06-01 | Med
| NGPL |  | St Louis Lateral |  | 300000 | 2002-06-01 | Med | 311 fac. |  |  |  | 35000000 | 47
| Southern Natural Gas |  | South System Expansion | Phase I Loop from MS to GA/Phase II Loop from MS toAL | 335800 | 2002-06-01 | High |  | CP00-233 |  |  | 140736540 | 67.3 | 53890
| Tennessee |  | Panda El Dorado Plant | Interconnect |  | 2002-06-01 | Med
| Transco/Duke (Formerly Coastal) |  | Gulfstream | Mobile, AL to West Palm Beach, FL | 1100000 | 2002-06-01 | Med |  | CP00-6 |  |  | 1600000000 | 744
| Trans-Union Interstate Pipeline |  | Panda El Dorado Plant | Gulf States Pipeline to the El Dorado Plant | 430000 | 2002-06-01 | Med | [5 empty] | 42
| Trailblazer |  | Expansion/Extension | Glenrock to Gage | 300000 | 2002-07-01 | High |  |  |  |  | 58500000 | 149 | 44800
| Northwest Pipeline |  | Puget Sound Plant Lateral | Snohonmish County, WA | 133000 | 2002-08-01 | High |  |  |  |  | 17200000
| Sempra/PG&E/Proxima Gas SA |  | North Baja Pipeline/Ehrenberg Exp | El Paso Ehrenberg to Baja California | 500000 | 2002-09-01 | Med |  | CP01-22 |  |  | 146000000 | 212
| Algonquin |  | HubLine | Beverly, MA (MNE) to Weymouth, MA | 300500 | 2002-11-01 | Med |  | CP01-5 |  |  | 114048000 | 34.8 | 0
| ANR |  | Supply Link | Sandwich Compressor to Defiance | 750000 | 2002-11-01 | Low |  | CP97-319 |  |  | 124800000 | 73 | 15000
| ANR |  | Wisconsin Loop Expansion III | Chicago to Wisconsin, IL and MN | 100000 | 2002-11-01 | Med | 30000
| CMS/WICOR/Viking |  | Guardian Pipeline | Chicago to Wisconsin | 750000 | 2002-11-01 | High | PD recd | CP00-36 | FEIS recd |  | 224000000 | 147 | 24000
| Columbia Gas/CMS/MCN/Westcoast |  | Millennium | Chicago to New York City | 650000 | 2002-11-01 | Low |  | CP98-150 |  |  | 678000000 | 443
| Dominion |  | High Deliverability Storage | Salt Like Firm Storage (12 cycles) |  | 2002-11-01 | Low
| East Tennessee |  | Patriot Extension | Virginia to North Carolina (Transco) | 200000 | 2002-11-01 | Low |  |  |  |  | 215000000 | 95
| Iroquois |  | Eastchester Bay Marine Ext Proj | Waddington to Eastchester (ConEd) | 220000 | 2002-11-01 | Med | None | CP00-232 | rolled in | 10-30 | 173918000 | 30.3 | 58300
| Maritimes & Northeast |  | Phase III | adds Beverly MA as another Delivery Point | 360000 | 2002-11-01 | Med |  | CP01-4 |  |  | 133995000 | 25.1 | 0
| Northwest Natural Gas |  | Mist Expansion Phases IV | Storage Field Expansion of 14 Bcf |  | 2002-11-01 | Low |  |  |  |  | 58000000 | 32
| Northwest Pipeline |  | Grants Pass Lateral Expansion |  | 50000 | 2002-11-01 | Med
| PGT |  | Kingsgate to Malin | Kingsgate to Malin | 200000 | 2002-11-01 | Med
| TCPL/St. Clair Pipeline |  | Lake Erie Crossing Pipeline | 7 shippers | 650000 | 2002-11-01 | Med |  |  |  |  | 106000000 | 60
| TCPL/Westcoast/CGT/MCN |  | Canadian Millenium | Dawn to Lake Erie | 700000 | 2002-11-01 | on hold |  |  |  |  | 700000000
| Transco |  | MarketLink Phase II | Leidy to New York City | 130000 | 2002-11-01 | Done |  | CP98-540 |  |  | 119600000
| Transco/ANR/National Fuel |  | Independence Pipeline | Chicago to Leidy | 946500 | 2002-11-01 | Med |  | CP97-315/320/321 |  |  | 629600000 | 400 | 60000
| Transwestern |  | San Juan to California | could be 100/d or 300/d | 610000 | 2002-11-01 | Low
| Williams/BC Hydro |  | Gerogia Straight Crossing | Sumas to Vancouver Island | 100000 | 2002-11-01 | Med | NEB Filed |  |  |  | 120000000 | 85
| CIG |  | Valley Line Expansion | Adams Co, CO to Nixon Lateral | 232000 | 2002-12-01 | High |  | CP01-45 |  |  | 72000000 | 85 | 4470
| Duke Energy/Williams/Keyspan |  | Cross Bay Pipeline | Transco/TETCO in NJ to JFK Airport | 125000 | 2002-12-01 | Low |  | CP00-412-414 |  |  | 59500000 | 33.7 | 16000
| Tuscarora |  | Sierra Pacific Power | Lemmon Valley, NV Plant | 75000 | 2002-12-01 | Med |  |  |  |  | 10200000 | 16.4
| CIG/Piaute Pipeline |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 250000 | 2003-01-01 | Low | [5 empty] | 400
| FGT/El Paso |  | Cypress | Elba Island LNG to FGT Jacksonville | 310000 | 2003-04-01 | Med |  |  |  |  | 232000000 | 160 | 0
| Transco/Duke |  | Buccaneer Pipeline | Station 82 to north of Tampa Bay | 900000 | 2003-04-01 | Dead |  | CP00-14 |  |  | 1455173425 | 673.88 | 75000
| Florida Gas Transmission |  | Phase VI | Bayside Plant | 175000 | 2003-05-01 | Med
| Transco |  | Momentum Expansion Project | Station 65 to Station 165 Virginia excl So VA lateral | 475000 | 2003-05-01 | Med | Inc Rates |  |  | 175
| CIG |  | COCO Pipeline | Cheyenne Hub to Midcontinent PLs | 500000 | 2003-10-01 | Low
| Northwest Pipeline |  | Displacement Expansion | Ignacio to Stanfield Corridor | 175000 | 2003-10-01 | High |  |  |  |  | 81000000
| PG&E/Avista |  | Jackson Prairie Expansion | Storage Field Expansion of 5.0 Bcf |  | 2003-10-01 | Med
| Northern Border |  | Bison Pipeline | Gillete, WY to McCabe, MT | 500000 | 2003-11-01 | Med |  |  |  |  | 225000000 | 325
| Peoples/Coastal |  | Whitecap Energy - Lake | ANR @ Crete, IL to Southeastern WI | 1500000 | 2003-11-01 | Low | 30001 |  |  |  |  | 90
| PG&E/Avista |  | Stanfield Storage | Stanfield, OR 15.0 Bcf working gas |  | 2003-11-01 | Med
| Scana |  | Carolinas Pipeline | South Carolina (Elba) to North Carolina (Pembroke) | 250000 | 2003-11-01 | Low |  |  |  |  | 1780000000
| Sumas Energy 2 |  | NWPL bypass | Westcoast Energy to 720 MW CC Plant | 140000 | 2003-11-01 | Med |  | CP99-320 |  |  |  | 4.5
| Williams Natural Gas |  | Western Farmers | Cheyenne Hub to Hugoton | 540000 | 2003-11-01 | Low | [5 empty] | 400 | 13000
| Northwest Pipeline |  | Jackson Prairie Expansion II | Displacement expansion for system operations | 175000 | 2003 | Med |  | CP98-251 |  |  | 100000000 |  | 6961
| Northwest Natural Gas |  | Mist Expansion Phases V | Storage Field Expansion of 14 Bcf |  | 2004-11-01 | Low | [5 empty] | 20
| Maritimes & Northeast |  | New Brunswick to Quebec lateral | M&NE mainline to Edmundston, NB | 184000 | 2004-11-01 | Med |  |  |  |  | 179000000
| Gaz Metropolitain/Enbridge |  | Trans-Quebec & Maritimes | Edmundston, NB to Quebec City (Riviere-du-Loup) | 184000 | 2004-11-01 | Med | [5 empty] | 164
| Transco |  | MarketLink Phase III | Leidy to New York City | 432000 | 2004-11-01 | Med |  | CP98-540
| Westcoast |  | Orca Natural Gas Pipeline | Sumas to Washington areas | 0 | 2004-11-01 | On Hold |  |  |  |  | 195000000 | 140 | 22000
| Dominion |  | Greenbriar Pipeline | Cornwell to Rockingham, NC | 600000 | 2005-01-01 | Low |  |  |  |  | 400000000 | 200 | 31000
| ANGTS |  | TCE/Westcoast | Alaskan Highway to Boundry Link | 2500000 | 2007-11-01 | Low |  |  |  |  | 6000000000 | 1700
| Arctic Resources (ARC) |  | Native Organizations (Hoagland's) | North Slope to Mackenzie to Alta | 1500000 | 2007-11-01 | Low |  |  |  |  | 5300000000 | 1200
| Enbridge Consortium |  | Mackenzie Delta | Mackenzie to Fort Saskatchewan | 1200000 | 2007-11-01 | Low |  |  |  |  | 2850000000 | 1250
|  |  |  | 1994 | 35000 | [6 empty] | 0
|  |  |  | 1995 | 215000 | [6 empty] | 9000000
|  |  |  | 1996 | 1664000 | [6 empty] | 147489000
|  |  |  | 1997 | 5514752 | [6 empty] | 2336732812
|  |  |  | 1998 | 9512817 | [6 empty] | 6453224548.8233
|  |  |  | 1999 | 7867194 | [6 empty] | 4606380198.8233
|  |  |  | 2000 | 8770199 | [6 empty] | 6859708960
|  |  |  | 2001 | 10341570 | [6 empty] | 2658555166
|  |  |  | 2002 | 14560683 | [6 empty] | 7285971577
|  |  |  | 2003 | 5890000 | [6 empty] | 3873173425
|  |  |  | 2004 | 800000 | [6 empty] | 374000000
|  |  |  | 2005 | 600000 | [6 empty] | 400000000
|  |  |  | 2006 | 0 | [6 empty] | 0
|  |  |  | 2007 | 5200000 | [6 empty] | 14150000000
Note on B306: ECT: Trunkline, Marathon Ashland Petroleum and TEPPCO Partners LP
Note on B332: ECT: one third ownership each
Note on D182: Julie Gomez: Serves 620 MW Presidente Juarez power plant
Note on D189: ECT: Producers include Chevron Canada, Canadian Forest, Ranger, Purcell, Anderson Exploration and Talisman
Note on D257: julie gomez: Uses Tennessee 500 line capacity
Note on D309: ECT: The LNG will come from output from the planned second and third trains of Atlantic LNG project in Trinidad and Tobago.
Note on E187: ECT: Includes 50,000/d of capacity from Blanco to Thoreau
Note on E256: ECT: To serve the existing 150MW Hermosillo Plant and a proposed 225MW expansion plant. The 12 mile east branch line will cross the border near Douglas and serve the proposed 225MW El Fresnal/Nogales plant.
Note on E297: jgomez: 19,100 via National Fuel lease from Niagara, the rest is from the Gulf Coast.
Note on E309: ECT: Can take delivery of 80 Bcf annually, or 220,000 M/d fo LNG starting mid 2002
Note on E317: ECT: Southern Company's capacity is in the name of Georgia Power for the Wansley Plant
Note on E328: Julie Gomez: Will interconnect with Sempra'a Rosarito Pipelien south of Tijuana
Note on E332: ECT: Proposed to connect to Alliance, NBPL, NGPL, Midwestern and Joliet Hub
Note on E346: ECT: The Canadian portion of the project would originate on the international border in Boundry Pass, Strait of Georgia and interconnect with the existing Centra transmission system at a point south of Duncan, BC. The Canadian portion would be about 31 miles long with about 23 miles offshore and eight miles onshore. The 16" pipe would move 100,000 M/d and be in service 11/2002
Note on E362: ECT: Scana would extend the system 300 miles to the proposed ethanol facilities and power plants in Onslow, Greene and Martin Counties, NC
Note on F87: ECT: LaClede subscribed
Note on F90: ECT: WGR anchored
Note on F130: jgomez: Dighton Power Assoc 33,000/d from Mendon to Dighton Plant
Note on F144: jgomez: Shippers include: Boston Gas 35000/d, ConEd 20000/d and ProvGas 95000/d.
Note on F158: jgomez: Shippers include: Aquila 16819/d, El Paso Energy 20000/d and FP&L 19100/d
Note on F190: jgomez: Tiverton Power Accos 46000/d Brookfield to Plant
Note on F200: jgomez: Lake Road Generating 146000/d from mainline to plant
Note on F205: jgomez: ANP Bellingham Energy 110,000/d Mainline Int to Plant
Note on F206: jgomez: 171,000 capacity for the public
Note on F210: ECT: 59,000/d contracted to three shippers and an additional 25,000/d as of 11/1/01
Note on F219: jgomez: Casco Bay 105000/d from Ediington to Veazie Plant
Note on F220: jgomez: National Fuel Distribution 30,000/d from Lamont to Roystone
Note on F232: ECT: Southern Company 40,000/d, Visy Paper 4500/d and AGL 61160/d Santee Cooper 80,000/d, Sylacaugh Utilities Board 4000/d, MGAG 14,439/d
Note on F236: ECT: 600,000/d ??
Note on F250: jgomez: Shippers Include: Entergy Miss 200000/d and Warren Power 85000/d.
Note on F257: julie gomez: Southern Co bought 7Bcf of storage at Petal and can deliver to Transco, SoNat, Koch and Deston
Note on F260: ECT: MEP Pleasant Hill Generating Unit (600MW) and Tyson Foods
Note on F261: ECT: Empire District Electric Company State Line Plant in Jasper Co, MO 500 MW (CC)
Note on F264: Julie Gomez: Could be expanded to 1.0 Bcf/d. NJ Natural controls Shipper is eCorp.
Note on F265: jgomez: Sithe Power Marketing 140000/d lateral only
Note on F267: julie gomez: Primero Gas Marketing and El Paso Energy Raton LLC
Note on F280: julie gomez: UCG 27,500, Citizens, APG Industries and City of Pulaski
Note on F292: jgomez: Shippers include CIG Resources 150,000/d, Questar Gas 100,000/d and 40,000 Texaco
Note on F293: jgomez: Shippers inlcude: CE Minerals 782/d, City of Lenox 12/d, Coral Energy 6646/d, Interconn 6646/d, Milwhite 80/d, MGAG 1270/d and P&G Paper 1564/d.
Note on F294: jgomez: Shippers include Coral 6,646/d Interconn 6646/d, P&G Paper 1,564/d MGAG 1270/d CE Mineral 782/d milwhite 80/d and City of Lenox 12/d.
Note on F295: jgomez: AGL signed up for 200,000/d for 20 years.
Note on F296: jgomez: Shippers inlcude: ANP 34000/dand El Paso Gas Svs 139000/d
Note on F299: Julie Gomez: Willaims 100,000/d, ConEd 30,000/d,Aquila 25,000/d, ConEd Energy 10,000/d and St Lawrence Cement 1,000/d
Note on F309: ECT: 540,000 Peak Day Deliverability
Note on F312: ECT: FPL 101142/d. Southern 60937/d, TECO 180,000/d, JEA 14000/d, Tallahassee 2677/d, Peoples 1504/d, US Agri-Chem 115/d
Note on F313: ECT: Nicor is 300,000/d
Note on F317: ECT: Southern Company 140000/d and CP&L 75000/d
Note on F322: ECT: 15 year contracts with Southern Co 284,050 South Carolina PL Corp 50,000 LaGrange, GA 1,750 Phase I of 88,150 will start June 1, 2002
Note on F326: jgomez: Shippers include: Western Gas 57,500/d, ENA 41,000/d, CMS 100,000/d, Barrett 70,000/d, Devon Energy 33,000/d and Pennaco 22,500/d.
Note on F329: Shippers inlcude: Sithe 70,000/d, Southern Kendall 35,000/d Southern Connecticut 20,000 Prov Gas 500/d Mass Water Resource Auth 25,000/d and TETCO 80,000/d
Note on F330: Julie Gomez: DirectLink 507,000/d (contract not allowed by FERC), Dynegy 303,900/d, Cogentrix 101,300/d, Gleason 80,000/d and Duke 50,700/d
Note on F332: ECT: WICOR is 650,000/d
Note on F336: jgomez: Shippers include: Keyspan Ravenswood 60000/d, Engage 90000/d, Riverbay Corp 11470/d, Astoria Generating (Orion) 200000 and ConEd 200000.
Note on F343: jgomez: Virginia Power 100,000/d and PPL 30,000/d
Note on F344: ECT: DirectLink (an affiliate) has contracted for 500,000/d. Dynegy has contracted for 350,000/d.
Note on F346: ECT: BC Hydro has sined up for 97,000/d of capacity Connects two 250MW plants on Shawnigan Lake (81,000/d) and the local LDC Centra Gas
Note on F347: jgomez: Shippers include Front Range Power 85,000/d, PSCO 178,000/d
Note on F348: Julie Gomez: 125,000 is incremental capacity and the remaining 489,628 would be leased back to Transco.
Note on F357: ECT: PITCO's 60% of Max DQ
Note on M264: Julie Gomez: ecorp Marketing (an affiliate of Central New York) has 400,000/d on the lateral and 90,000/d on Tennessee's 300 line
Note on M272: ECT: AES signed for 20 year 10 month contract at a negotiated rate of $.0425 plus fuel
Note on O247: julie gomez: PSI (Cynergi) will reimburse Midw for $6.3 mil
Note on P255: ECT: 30" pipeline