## Kilpatrick Permit Matrix
Alamac Permit Matrix
Permit/Approval | Date of Application |  | Date of Approval |  | Restrictions/Conditions
| Actual | Expected | Actual | Expected
US Federal Aviation Administration
Notice of Proposed Construction
Federal Energy Regulatory Commission
Certification of Exempt Wholesale Generator Status
Power Marketer Certification
US Department of Energy
Exemption to burn natural gas and No. 2 fuel oil
US Army Corps of Engineers
Wetlands (Letter of Concurrence)
US Fish and Wildlife Service
Threatened and endangered species (Letter of Concurrence)
North Carolina Public Utilities Commission
Certificate of Public Convenience and Necessity
North Carolina Department of Environment, Health and Natural Resources
Authority to Construct Permit (Air Permit)
Title IV Operating Permit (Air Permit)
Title V Operating Permit (Air Permit)
NPDES Stormwater Construction Permit
Sedimentation Control Plan Approval
SPCC Plan
Department of Transportation
Driveway Permit
Department of Cultural Resources
Archaeological survey approval (Letter of Concurrence)
North Carolina Secretary of State
Certificate of Authority (Business License)
County of Edgecombe, City of Rocky Mount
Annexation
Conditional Use Permit
Water service
Local Construction Permit
Certificate of Occupancy
Fire Safety Approval

## Perlmit List and Contacts
Permit | Authority | Contact Person | Telephone Number | Status
Certificate of Authority
Lumberton LLC | State of North Carolina
Elizabethtown LLC | State of North Carolina
| City of Elizabethtown | Betty Smith | 910.862.3979
NC Power Holdings, LLC | State of North Carolina
Certificate of EWG Status
Lumberton LLC | FERC | Steve Van Hooser | 37238
Elizabethtown LLC | FERC
NC Power Holdings, LLC | FERC
Power Marketer Certification |  | Steve Van Hooser | 37238
Lumberton LLC
Elizabethtown LLC
NC Power Holdings, LLC
CPCN |  | Tom Chapman | 35309
Elizabethtown, LLC | NC Public Utilities Commission
Lumberton, LLC | NC Public Utilities Commission
Air Permits
Title IV Operating Permit | USEPA | Dave Kellermeyer | 33161 | Apply for the permit once the deal closes. Concurrently, request an extension (beyond the 90 days) to be in compliance.
Lumberton
Elizabethtown
Title V Operating Permit | NCDENR | Tom McKinney | 910.486.1541 910.486.0707 fax | Cogentrix has submitted Title V permit applications and requested name ownership changes. The name ownership change request covers both the Title V permit applications and the state operating permits. Once the deal closes we will have to submit another name ownership change request. Name ownership change request fees are PSD $60 and the non-PSD $25. Seperate requests should be filed for each facility. There is no form, a letter with permit number is OK. Is Cogentrix responsible for getting Lumberton and Elizabethtown LLC created and permits transferred?
Lumberton | NCDENR | Tom McKinney | 910.486.1541 | Title V permit being drafted. Cogentrix submitted Name/Ownership change to Cogentrix Eastern Carolina, LLC. We will have to change it again once the deal closes.
Elizabethtown | NCDENR | Tom McKinney | 910.486.1541 | Title V permit being drafted. Cogentrix submitted Name/Ownership change to Cogentrix Eastern Carolina, LLC. We will have to change it again once the deal closes.
State Operating Permit | NCDENR | Tom McKinney | 910.486.1541
Lumberton | NCDENR | Tom McKinney | 910.486.1541 | The name/ownership change notification required for the Title V permit covers the state operating permit also.
Elizabethtown | NCDENR | Tom McKinney | 910.486.1541 | The name/ownership change notification required for the Title V permit covers the state operating permit also.
Coal Handling Facility
Non-PSD | NCDENR | Tom McKinney | 910.486.1541 | We will need to submit a Name/Ownership Request to NCDENR for the Non-PSD permit. Cogentris has initiated a name change to Cegentrix Eastern Carolina, LLC.
NPDES Permit
Lumberton
Wastewater | NCDENR | Kitty Kramer | 910.486.1541 | Name/Ownership Change form in house, submit once the deal closes. Permit No. NC0058301 We need to find out if the oil/water seperator is listen on this permit.
| City of Lumberton | Karen Lewis | 910.671.3858 | No requirement by the city. They do not discharge to city.
Stormwater | NCDENR | Ricky Revels | 910.486.1541 | Name/Ownership Change form in house, submit once the deal closes. Permit No. NCS000352 We need to find out if the oil/water seperator is listen on this permit.
Coal Handling Facility
Wastewater | NCDENR | Kitty Kramer |  | They have nothing on file for the coal handling facility.
| City of Lumberton | Karen Lewis | 910.671.3858 | No requirement by the city. They do not discharge to city.
Stormwater | NCDENR | Kitty Kramer |  | They have nothing on file for the coal handling facility. I think they should probably have a permit here??
Elizabethtown
Wastewater | NCDENR | Kitty Kramer | 910.486.1541 | Name/Ownership Change form in house, submit once the deal closes. Permit no. NC0058297 We need to find out if the oil/water seperator is listen on this permit.
City of Elizabethtown
Stormwater | NCDENR | Ricky Revels | 910.486.1541 | Name/Ownership Change form in house, submit once the deal closes. Permit No. NCS000349 We need to find out if the oil/water seperator is listen on this permit.
Water Use Approval
Lumberton | City of Lumberton | Dickson Ivy | 910.671.3851 | This was recently renegotiated by Cogentrix. We will need to notify name/ownership change and perhaps amend contract with water supply authority. Dickson Ivy reports that this is an agreement with Robeson County. Please contact Henry Harris.
| Robeson County | Henry Harris | 910.671.3485 | Cogentrix extended their water agreement with the county through December 2001. The rate is in the range of $0.96 per 1000 gallons--they would not specifically tell me. They have plenty of capacity (up to at least 1.6 MGD). We can continue to operate under the Cogentrix agreement after we become the new owners; however, we should begin discussions with the county as soon as possible. If we have a higher guaranteed take, we can likely get a lower price. They will not turn off the water if we do not have a new contract at closing time.
Elizabethtown | City of Lumberton | Mike Prostinak | 910.862.3979 | Water for this plant comes from Alamac. They have on-site groundwater wells. A change in ownership of the power plant would not generate any name/ownership change notifications. There is a separate city water meter for potable water that will need to be transferred.
Sedimentation and Control Plan | NCDENR |  |  | If any construction is on-going, the Sedimentation and Control Plan is filed with the NCDENR. We need to know if there is anything active, construction-wise. If not, these plans are not an issue.
Lumberton
Elizabethtown
Coal Handling Facility
SPCC Plan | NCDENR
Lumberton |  |  |  | SPCC Plan, Site Health and Safety Plan, Stormwater Pollution Prevention Plan: These plans are kept on-site and not filed with any agency. However, the plans should be audited and edited to reflect ownership and contact information that changes once Cogentrix doesn't own them anymore.
Elizabethtown
Coal Handling Facility
Site Health and Safety Plan | NCDENR
Lumberton
Elizabethtown
Coal Handling Facility
Stormwater Pollution Prevention Plan | NCDENR
Lumberton
Elizabethtown
Coal Handling Facility
Certificate of Occupancy
Lumberton | Planning/Zoning | Jody Allen | 910.671.3976 | They issued an occupancy permit when the building was built. They do not change the name on these permits when ownership changes occur. Property is zoned M-2 (wlhich is appropriate for current landuse) and there is no conditional use permit.
Coal Handling Facility (Lumberton) | Planning/Zoning | Jody Allen | 910.671.3976 | They issued an occupancy permit when the building was built. They do not change the name on these permits when ownership changes occur. Property is zoned M-2 (wlhich is appropriate for current landuse) and there is no conditional use permit.
Elizabethtown | Planning/Zoning | Mary Joe Gollnitz | 910.862.3979 | The City of Elizabethtown has no requirements in this area. The property is zoned H-I (Heavy Industrial), and there is no special/conditional use permit associated.
Fire Safety Approval
Lumberton | City Fire Marshall | Kenneth Rhodes | 910.671.3816 | No jurisidcation, facilities are outside of city limits. Contact the Fire Marshall regarding the confined space entry contract.
| Robeson County Fire Marshall | Charles Britt | 910.671.3152 | They inpsect the facility every year. Cogentrix has a contact with the local fire department regarding confined space entry. This is strictly a procedural deal that is part of the site health and safety plan. If there are any petroleum storage tanks, they would have been registered and permitted for construction--not for operation. There is no need to notify the Robeson County Fire Marshall for name/ownership change.
Elizabethtown | City Fire Chief | Mark Haraway | 910.862.6730 | They have not done any inspections of the facility; however, they are happy to do so if we would like once the ownership transfer happens.
Bladen County |  |  |  | Local fire department has jurisdiction here.
Coal Handling Facility | Lumberton Fire Marshall Robeson County Fire Marshall | Kenneth Rhodes Charles Britt | 910.671.3816 910.671.3152 | Charles Britt reports that the county has never been to this facility. He thinks it is in the Lumberton city limits. Kenneth Rhodes reports that they do not have any permits or ownership change notification requirements. Is the coal handling facility in the city limits?
Local Business Licensing
Lumberton | Lumberton Tax Assessor | Livingston Lewis | 910.671.3816 | The plant and coal handling facility are outside the city. They have not jurisdiction and have never done business with Cogentrix at either location. We need to verify if the coal handling facility is in the city limits or not.
Lumberton | Planning/Zoning | Jody Allen | 910.671.3976 | They issued an occupancy permit when the building was built. They do not change the name on these permits when ownership changes occur.
Robeson County | County Tax Assessor | Cindy Lowery | 910.671.3060 | No requirement here for permitting or licensing. As of January 1 every year, the owner is required to list assets and pay tax on depreciated value. Notification of ownership change is not required.
Elizabethtown | Elizabethtown Tax Assessor | Betty Smith | 910.862.6730 | The plant is in the city limits of Elizabethtown and pays property taxes to the city and the county. All that is required here is to register with the Tax Assessor/Collector at the city and establish accounts with the city and the county. The city does the administrative portion for the county.
Elizabethtown | Planning/Zoning | Mary joe Gollnitz | 910.862.3979 | Planning/zoning has no requirements.
| Elizabethtown Clerk | Darlene Smith | 910.862.3979 | We will need a local business license. The fee is $50/year and it expires in June. Our 2001 fees would be $25 due to only one-half year. There is no risk assoicated with timing of the filing and continued operations. They will work with us on the filing, and they will not shut us down.
Bladen County | County Tax Assessor | Betty Smith | 910.862.6730 | Establish an account and pay the taxes. No other requirements for ownership change.
Solid Waste
Toxic Release Inventory
Lumberton | USEPA | SARA/RCRA/Superfund Hotline | 800.424.9346 | TRI ID 28358CGNTRSR220 - Facility Number The only requirement here is to put the new facility name on the reporting form (July of each year). The facility number will not change.
Elizabethtown | USEPA | SARA/RCRA/Superfund Hotline | 800.424.9347 | TRI ID 28337CGNTR3100W - Facility Number The only requirement here is to put the new facility name on the reporting form (July of each year). The facility number will not change.
Non-haz solid waste
Lumberton | NCDENR | Ikie Guyton | 910.486.1541 | No registration/permit/notification requirements as long as ReUse is managing the waste.
Elizabethtown | NCDENR | Ikie Guyton | 910.486.1542 | No registration/permit/notification requirements as long as ReUse is managing the waste.
Haz Waste
Lumberton | NCDENR | Flynt Worrell | 910.486.1542 | No registration/notification/permit on file.
| EPA |  |  | EPA ID Number NCD986218402 We will need to change this.
Elizabethtown | NCDENR | Flynt Worrell | 910.486.1542 | No registration/notification/permit on file.
| EPA |  |  | EPA ID Number NC0001997857 We will need to change this.
Radioactivity Permit/License
Lumberton | Robeson Co. Health Dept | Ambrose Locklear | 910.671.3200 | Robeson County Health Department has nothing to do with the Cogentrix plant. There is nothing Cogentrix would do that the county health department would permit.
| NRC--Atanta |  | 404.562.4416 | North Carolina has NRC regulating authority.
| NCDENR Radiation Protection | James Albright | 919.571.4141 | They do not license coal plants in NC because coal fired power plants and steam generation porcesses do not generate radioactive material. NC has no regs on NORM. The only permits they may have are for radioactive guages. They are doing a permit search on that.
Elizabethtown | Bladen Co. Health Dept
| NRC--Atanta |  | 404.562.4416 | North Carolina has NRC regulating authority.
| NCDENR Radiation Protection | James Albright | 919.571.4141 | They do not license coal plants in NC because coal fired power plants and steam generation porcesses do not generate radioactive material. NC has no regs on NORM. The only permits they may have are for radioactive guages. They are doing a permit search on that.
Federal Aviation Administration
| FAA Wash DC | Ellen Crum | 202.493.4562 | FAA does not permit, they study and make recommendations. FAA must be notified under certain curcumstances (40CFR Part 77). Notice criteria (>200 feet) and location Obstruction criteria (>500 feet) and location. Hazard criteria is based on a location test. FAA will do a aeronautical study and make marking/lighting recomendations. FAA does not enforce these recommendations. They rely on other permitting agencies and insurance companies to get the marking and lighting recommendations incorporated into the design and construction. If you contemplate putting on an antenna/transmitter of some type, FCC is the regulating agency. They look to get FAA study/guidance/recommendations. FCC will incorporate those recommendations into their permit requirements. FAA is interested in antennas/transmitters for two reasons: 1) height and 2) radio frequency interference. We need to know if the plants have antennae/transmitters on the stacks.
| FAA Atlanta | Jill Robinson | 404.305.5587 | We need the lat/long of each facility for the FAA to find if aeronautical studies were completed. She suggested we evaluate the stacks with respect to the FAA notification criteria to determine if they are in compliance. They may have needed aeronautical studies completed and did not get them. This is common. This is a compliance issue--not an ownership change notification issue.
Lumberton Airport | Local airport | Lee Hester | 910.739.6480 | There is a 300ft AM radio tower between the Cogentrix stack and the airport. The radio tower is taller than the Cogentrix stack. He doesn't recall if it is lighted or has an antenna or traqnsmitter on it. The Cogentrix stack is not problematic for the Lumberton airport.
Elizabethtown Airport | Airport Board | Steve Willis | 910.876.2519 | The Elizabettown stack is in line with the runway. Theyare meeting on this issue Monday night to see if they need to do anything about marking, lighting, etc. There is also a new 200 foot tall cell tower 500 feet south of the Cogentrix stack. The cell tower is the reason for the board meeting. It is unlikely the stack will be effected.
Pressure Vessel Permits | NC Department of Labor | Allison Johnson | 919.807.2760 | Pressure vessels need to be inspected and certified. It is a courtesy to notify the Boiler Inspection Division when an ownership change occurs. Lumberton and Elizabethtown have 10 certificates each indicating 10 regulated pressure vessels at each plant. Maintenance of the inspections is critical. If the certificate is out of date by 30 days, the vessel can be taken out of service by the Department of Labor. There is no notification fee and no penalty for not notifying. A complete schedule for each facility has been requested.
Lumberton |  |  |  | Certificate Numbers: 211313, 211314, 211315, 211316, 211317, 211318, 211334, 234522, 287306, 287307
Elizabethtown |  |  |  | Certificate Numbers: 211302, 211303, 211305, 211306, 211307, 211312, 211341, 234331, 287311, 287312
Elevator Permits | NC Department of Labor |  |  | We need to know if there are elevators at either facility.
Material Hauling Permits | NCDOT | Tammy Denning | 919.733.4740 | NCDOT does not issue hauling permits for divisible commodities (I.e. commodities that can be reduced so that legal limits can be observed). There are no permits available for divisible commodities anywhere in the state. The haulers must abide by the posted regulatoions.
Coal Handlng Facility |  |  |  | No requirements here.
Hazardous Waste Transportation | NCDOT Motor Carrier |  | 919.861.3167 | From the Phase I ESA, SafetyKleen is handling the waste for each plant. We need to know if Cogentrix is doing the shipping for any of this waste themselves.
Petroleum Storage Stanks | NCDENR | Shawn Boyles | 910.486.1541 | See June 2, 1998 memo. ASTs that are non-retail and >21,000 gal must be registered with the NCDENR.
Lumberton | Div. of Waste Management
AST | Div. of Water Quality
| USEPA | Bob Rossin | 404.562.8761 | Aggregate storage >1,320 gal must have an SPCC Plan. No notification is required; however the SPCC plan must be updated with new ownership information.
Elizabethtown | Div. of Waste Management | Shawn Boyles | 910.486.1541 | See June 2, 1998 memo. ASTs that are non-retail and >21,000 gal must be registered with the NCDENR.
AST | Div. of Water Quality
| USEPA | Bob Rossin | 404.562.8761 | Aggregate storage >1,320 gal must have an SPCC Plan. No notification is required; however the SPCC plan must be updated with new ownership information.
Oil Water Seperator
Lumberton
| NCDENR - Div. of Waste Management | James Brown | 910.486.1541 | As a UST, an oil/water seperator is exempt by definition (see regs) as long as we can call it a wastewater treatment tank. As such, there are no notification requirements for ownership change.
| NCDENR - Div. of Water Quality | Paul Rawls | 910.486.1541 | Several scenarios are possible: 1) discharge to sanitary sewer permitted by city; 2) discharge to stormwater sewer permitted by state; 3) discharge to either unpermitted. Worst case is discharge to stormwater sewer unpermitted. If this is the case, it must be fixed ASAP--the NCDENR will issue a cease and desist notice--reroute to sanitary with city approval. We need to find out if the NPDES permit lists the oil/water seperator. ENSR indicates that the effluent goes to the stormwater sewer.
Elizabethtown
| NCDENR - Div. of Waste Management | James Brown | 910.486.1541 | As a UST, an oil/water seperator is exempt by definition (see regs) as long as we can call it a wastewater treatment tank. As such, there are no notification requirements for ownership change.
| NCDENR - Div. of Water Quality | Paul Rawls | 910.486.1541 | Several scenarios are possible: 1) discharge to sanitary sewer permitted by city; 2) discharge to stormwater sewer permitted by state; 3) discharge to either unpermitted. Worst case is discharge to stormwater sewer unpermitted. If this is the case, it must be fixed ASAP--the NCDENR will issue a cease and desist notice--reroute to sanitary with city approval. We need to find out if the NPDES permit lists the oil/water seperator. ENSR indicates that the effluent goes to the stormwater sewer.
Wetlands
Lumberton | Corps of Engineers |  |  | ENSR did not report the presence of wet lands at either facility. They are double checking due to an inconsistency in the Phase I ESA. Chuck Cornell with ENSR reports that no wetlands were identified.
Elizabethtown | Corps of Engineers |  |  | ENSR did not report the presence of wet lands at either facility. They are double checking due to an inconsistency in the Phase I ESA. Chuck Cornell with ENSR reports that no wetlands were identified.
Enron corporate secretary typically takes care of this during LLC formation. We are going to have to get a license from the City of Elizabethtown given that the plant is in the city limits. We need to find out who is taking the lead on this.
Filed with FERC on 1/8/01.
Filed with FERC on 1/8/01.
Reagan Rorschach will coordinate Tom Chapman and Alyson Duncan to get a game plan.

## Cogentrix Issues
1 | Are the Lumberton Power and Elizabethtown Power LLCs created?
2 | Is there a stormwater permit for the Coal Handling facility?
3 | Can we get copies of all Name/Ownership Change Request Forms filed for each plant and the Coal Handling Facility?
4 | Are the oil/water seperators covered under the NPDES permits as "miscellaneous plant sumps"?
5 | Is there any site activity currently covered by a Sedimentation and Control Plan?
6 | Are any city taxes being paid to the City of Lumberton or have any tax abatement agreements been made with respect to the Coal Handling facility?
7 | What site-specific plans are in place? For example:
Spill Prevention Control and Countermeasures (SPCC) Plan
OSHA related operations plans
EPCRA/SARA related "right-to-know" plans
Stormwater Pollution Prevention Plan
8 | EPA ID Numbers were found for each plant. Are they active, and if so, can we get copies of the Notice of Registration (NOR)?
Lumberton NCD986218402
Elizabethtown NC0001997857
9 | Who is shipping the waste? Where is the waste being disposed?
10 | How tall are the stacks?
11 | Were aeronautical studies completed for each stack? If so, can we get copies of the studies?
12 | Are any antennae/transmitters present on either stack?
13 | What are the terms of the water supply contract with Robeson County?
14 | Are any radioactive guages?
15 | Can we get a list of pressure vessel certificates and a schedule of expiration?
16 | Are there any elevators at either of the facilities?