## JUNE
PLANNING SERVICES
FLORIDA GAS TRANSMISSION PROJECT REPORT
| PREPARED BY: DENNIS ALTERS | [8 empty] | 2026-07-30
** DENOTES CHANGE FROM LAST MONTH
| PLNG | ENGNR |  |  |  | PLANNING |  | EST. | PLN
| NO. | NO. | SPONSOR | PROJECT NAME | PROJECT DESCRIPTION | RECEIVED | RELEASE | COMPL | ENG | COMMENTS
| F98055 | R98323 | FARRELL | ABANDON CS 2 TO MOPS | ABANDON 4000 HP & 70.2 MILES 20" | 1/15/98 | 1/10/01 B | 2001 | MDH | M.P. 95.6 TO 165.8. ABANDON AND SELL. UPDATED COST ESTIMATE REQUESTED.
| F99045 | C00913 | FARRELL | COPANO - TIVOLI | BUILD 50 MMCF/D INTERCONNECT | 6/09/99 | 2/11/00 CR | 03/00 | MDH | M.P. 165.8. EITHER ONE DIRECTIONAL OR BI-DIRECTIONAL. $136K.
| F99003 |  | FARRELL | MAINLINE PIG LAUNCHER, 20" | INSTALL PIG LAUNCHER AT M.P. 165.8 | 1/04/99 | 2/18/00 C | 2000 | MDH | M.P. 165.8. INSTALL WHEN UPSTREAM MAINLINE IS SOLD AND DISCONNECTED.
| F00080 |  | FARRELL | MITCHELL - PALACIOS | GAS SUPPLY CONNECT | 9/21/00 | 9/26/00 B | 2000 | MDH | M.P. 213.7. CONNECTING PIPE, AND EFM. CONNECT TO EXISTING VALVE 3-25B.
** | F00064 | C.000623.01 | FARRELL | ARROWHEAD - KAIN | INSTALL NEW INTERCONNECT |  | 5/25/01 X | 2001 | MDH | M.P. 1.0 ON KAIN LAT. DECIDED NOT TO CONNECT TO FGT. PROJ. CANCLD. FINAL REPORT.
| F00093 |  | FARRELL | HOWARD EXPL - POWERS #1 | WELL CONNECT | 10/10/00 | NO RELEASE | 2000 | MDH | M.P. 280.1. INSTALL 2" OR 3" TAP, CONNECTING PIPE & EFM.
** | F01002 | C.014081.01 | FARRELL | ASPECT - TOSSUP | WELL CONNECT | 1/05/01 | 5/31/01 X | 2001 | MDH | M.P. 286.3. 5 TO 10 MMCF/D. WELL WAS A DRY HOLE. PROJECT CANCLD. FINAL REPORT.
| F00054 |  | FARRELL | COKINOS - SOUTH ALVIN | WELL CONNECT | 6/26/00 | NO RELEASE | 2000 | MDH | M.P. 0.4 ON SOUTH ALVIN LATERAL. NEW 2" TAP AND CONNECTING PIPE.
** | F01034 |  | FARRELL | ASPECT - TIEMANN NO. 1 | WELL CONNECT | 5/07/01 | NO RELEASE | 2001 | MDH | M.P. 290.3. 2" TAP AND 2000 FT OF 2" CONNECTING PIPE.
| F00082 | C.000741.02 | FARRELL | ALGOA LATERAL | ABANDON ENTIRE 0.6 MI., 4" LATERAL | 9/07/00 | 10/30/00 C | 2000 | MDH | M.P. 293.6. DISCONNECT LATERAL, BLIND FLANGE VALVE NO. 4-45B.
| F00091 |  | FARRELL | PETROL. FUELS - TEXAS CITY | INSTALL VALVE, CONN. PIPE, EFM | 10/02/00 | NO RELEASE | 2000 | MDH | M.P. 303.0. DELIVER UP TO 0.5 MMMBTU/D.
** | F00092 |  | FARRELL | ASPECT RES. - WALL EST. #2 | WELL CONNECT | 10/20/00 | 3/05/01 CR | 2000 | MDH | M.P. 306.7. PROJECT CANCELLED. WORKING ON LEVEL X.
| F01001 |  | FARRELL | COKINOS - TEXAS CITY | BUILD INTERCONNECT | 12/05/00 | 3/13/01 C | 2001 | MDH | M.P. 306.7. INSTALL 10" TAP, 16" CONNECTING PIPE & EFM TO DEL. 300 MMCF/D.
** | F99025 | C.004017.01 | FARRELL | TRANS TEXAS - SMITH POINT | WELL CONNECT | 3/24/99 | 5/25/01 X | 2000 | MDH | M.P. 321.5. PROJECT CANCELLED. FINAL REPORT.
| F01018 |  | FARRELL | RANGE RESOURCES | WELL CONNECT | 2/28/01 | NO RELEASE | 2001 | MDH | M.P. 408.2. 4" TEE ON NEUMIN'S RISER AND EFM.
| F00086 |  | FARRELL | HS RESOURCES - IND. VILL. | ADD CHROMATOGRAPH | 9/15/00 | 10/06/00 B | 2000 | MDH | M.P. 445.5. NEEDED BECAUSE OF INCREASING VOLUME.
** | F01040 |  | FARRELL | DUKE - EGAN STORAGE | BUILD 200 MMCF/D INTERCONNECT | 5/02/01 | NO RELEASE |  | MDH | M.P. 472.6. 12" TAP, CONNECTING PIPE, EFM.
** | F00019 |  | FARRELL | COGENTRIX - EUNICE | BUILD LATERAL AND METER STATON | 2/28/00 | NO RELEASE | 2002 | MDH | M.P. 480.0. DELIVER 6,160 MMBTU/HR AT 500 PSIG. PROJECT CANCELLED. FINAL REPORT.
| F00075 | C.000717.03 | FARRELL | ACADIA POWER PARTNERS | BUILD LATERAL AND METER STATION | 9/12/00 | 3/27/01 B | 2002 | RLM | M.P. 480.0. DELIVER 20,000 MMBTU/HR AT LINE PRESSURE.
** | F00098 |  | FARRELL | SEVARG - SHUTESTON | WELL CONNECT | 10/24/00 | 3/08/01 C | 2000 | RLM | M.P. 7.2 ON SHUTESTON LAT. CONNECT TO VLV NO. 7-110B. I.D. 5/03/01. FINAL REPORT.
| F00025 |  | FARRELL | HS RESOURCES - FUTRAL | WELL CONNECT | 3/02/00 | 3/10/00 B,CR | 2000 | RLM | M.P. 507.2. COST FOR TAP, CONNECTING PIPE, EFM. RELEASED FOR PERMITS.
| F00031 |  | FARRELL | MANTI - PORT BARRE | WELL CONNECT | 3/22/00 | NO RELEASE | 2000 | RLM | M.P. 510.1. BIDIRECTIONAL. UP TO 3,000 MCF/D. TIE ON TO EXISTING MLV 7-27 B.
| F01023 |  | FARRELL | LAFAYETTE UTILITIES | BUILD TAP, EFM, & CONNECTING PIPE | 4/06/01 | NO RELEASE | 2001 | RLM | M.P. 21.5 ON EWL LAT. 6" TAP, CONN. PIPE, EFM. DEL. 35 MMMBTU/D AT 500 PSIG.
** | F98067 |  | FARRELL | ANR - KROTZ SPRINGS | BUILD NEW INTERCONNECT | 7/15/97 | 5/15/01 B | 2001 | RLM | M.P. 7.2 ON EWL 22" LATERAL. 10" TAP, 16" CONNECTING PIPE. 250 MMCFD CAPACITY.
** | F01038 |  | FARRELL | JASMINE - LOTTIE | WELL CONNECT. | 5/15/01 | NO RELEASE | 2001 | EAS | M.P. 525.6. 600 MCF/D.
| F00039 | R00930 | FARRELL | LAKE CHICOT LATERAL | ABANDON 10.6 MILES OF 10" LATERAL |  | NO RELEASE | 2000 | RLM | M.P. 4.4 TO 15.0. SELL 10.2 MILES TO HILLCORP & TAKE UP 0.4 MILES.
** | F01021 |  | FARRELL | CITY OF WALKER | UPGRADE METER STATION | 3/15/01 | 4/02/01 B | 2001 | RLM | M.P. 13.0. INCREASE REGULATOR CAPACITY TO 260 MMBTU/HR.
| F00051 | J00314 | FARRELL | RELIANT - BARRIER CONST. | INSTALL TAP, LATERAL AND EFM | 6/01/00 | 8/29/00 B |  | RLM | M.P. 55.9. 4" TAP, LATERAL AND EFM. DELIVER 120 MMBTU/HR.
| F00102 |  | FARRELL | CALPINE - BOGALUSA | BUILD TAP, LATERAL & METER STA. | 12/15/00 | 1/30/01 B | 12/15/01 | RLM | M.P. 74.2. DELIVER 6.43 MMMBTU/HR AT 500 PSIG. $725K.
| F01013 |  | FARRELL | GAYLORD - BOGALUSA | BUILD TAP, EFM & CONNECTING PIPE | 1/29/01 | 2/01/01 B |  | RLM | M.P. 79.0. DELIVER UP TO 12.0 MMMBTU/D AT LINE PRESSURE. 4" TAP ON 30" .
** | F98071 | C.005066.02 | BOATMAN | LOOP 10-11 FOR PHASE IV | BUILD 9.3 MILES 36" MAINLINE LOOP |  | 5/08/00 C | 2000 | EAS | M.P. 152.7 TO 162.0. OFFICIALLY PLACED IN SERVICE 5/01/01. FINAL REPORT.
| F99061 | C.005061.01 | BOATMAN | LOOP A - PHASE V, MISS. | BUILD 3.2 MILES 36" MAINLINE LOOP |  | 8/24/99 CR | 2002 | EAS | M.P. 162.0 TO 165.2.
| F99061 | C.005061.17 | BOATMAN | LOOP A - PHASE V, ALA. | BUILD 2.9 MILES 36" MAINLINE LOOP |  | 8/24/99 CR | 2002 | EAS | M.P. 165.2 TO 168.1.
| F00057 | C.005061.14 | BOATMAN | CITRONELLE REGULATOR | INST. 24" BLOCK VALVE & REGULATOR | 5/15/00 | 7/24/00 CR | 10/01/01 | EAS | M.P. 170.4. REGULATE TO 847 PSIG.
| F99053 | C.005062.16 | HAYES | MOBILE BAY LATERAL | BUILD 30" LATERAL & COMPRESSOR | 7/28/99 | 8/20/99 CR | 2001 | EAS | M.P. 170.5. 29.1 MILES 30".
| F99095 | C.005064.46 | HAYES | KOCH MOBILE BAY MTR STA | BUILD METER STATION | 7/28/99 | 8/20/99 CR | 2001 | EAS | M.P. 28.8 ON MOBILE BAY LATERAL. MEASURE 400 MMCF/D.
| F99096 | C.005063.31 | HAYES | COMPRESSOR STA NO. 44 | BUILD NEW 3,335 HP STATION | 7/28/99 | 8/20/99 CR | 2001 | EAS | M.P. 28.8 ON MOBILE BAY LATERAL.
| F98085 |  | HAYES | MAINLINE LIQUIDS PLANT | BUILD PLANT TO REMOVE C6+ | 12/01/98 | 12/02/98 B | 1999 | DDA | M.P. 190.8.
| F99047 |  | BOATMAN | STATION 11A FOR AEC | UPGRADE STATION | 6/23/99 | 4/07/00 C | 2001 | EAS | M.P. 190.8. UPGRD TO 30,000 HP, RESTAGE, LOOP SUC, ADD SCRUB. & COOLERS.
| F99011 | C.005063.32 | BOATMAN | STATION 11A - PHASE V | INSTALL 15,700 HP CENT. COMP. | 2/15/99 | 8/20/99 CR | 2002 | EAS | M.P. 190.8. LOOP DISCH. LINE. TOTAL STA. 11A HORSEPOWER WILL BE 45,700.
| F96059 | C98941 | FARRELL | CLARKE MOBILE - MT. VER. B | BUILD TAP, CONNECTING PIPE & EFM | 10/10/96 | 1/08/99 C | 1999 | EAS | M.P. 190.8 ON 36" C/S 11A DISCH. DEL. UP TO 4.5 MMM BTU/HR AT LINE PRESS.
| F99062 | C.005061.02 | BOATMAN | LOOP B - PHASE V | BUILD 11.2 MILES 36" LOOP | 8/12/99 | 8/20/99 CR | 2002 | EAS | M.P. 190.8 TO 202.0. PIPE TO BE INTERNALLY COATED.
| F99050 |  | FARRELL | CONECUH MONROE - BEC | BUILD NEW DELIVERY POINT | 6/06/00 | 8/08/00 B | 2000 | EAS | M.P. 3.1 ON BIG ESCAMBIA CREEK LAT. DELIVER 10 MMMBTU/D AT 600 PSIG.
| F00063 |  | FARRELL | CITY OF BREWTON | BUILD NEW DELIVERY POINT | 6/28/00 | NO RELEASE |  | EAS | M.P. 231.4. DELIVER 10,000 MMBTU/D AT 600 PSIG.
| F99077 | J00248 | BOATMAN | AEC - FLOMATON | UPGRADE 8" TURBINE METER | 9/15/99 | 4/07/00 C | 2001 | EAS | M.P. 238.6. INSTALL HIGH CAPACITY MODULE IN EXISTING METER.
| F01024 | C.010128.02 | FARRELL | FLOMATON LATERAL | ABANDON & SELL 5.5 MILES OF 6" | 3/15/01 | NO RELEASE | 6/01 | EAS | M.P. 0.9 ON WIGGINS LAKE LATERAL.
| F01025 | C.010128.02 | FARRELL | WIGGINS LAKE LATERAL | ABANDON & SELL 0.9 MILES OF 8" | 3/15/01 | NO RELEASE | 6/01 | EAS | M.P. 241.2.
| F01026 | C.010128.02 | FARRELL | EXXON PROCESSING LAT. | ABANDON & SELL 1.9 MI. 12", 0.4 MI. 8" | 3/15/01 | NO RELEASE | 6/01 | EAS | M.P. 0.0 ON WIGGINS LAKE LATERAL.
** | F98011 | C.005068.32 | BOATMAN | STATION 12A - PHASE IV | INSTALL 10,350 HP COMPRESSOR | 2/02/98 | 5/08/00 C | 2001 | EAS | M.P. 260.2. PLACED IN SERVICE 5/01/01. FINAL REPORT.
| F98012 | C.005063.33 | BOATMAN | STATION 12A - PHASE V | INCREASE TO 28,700 HP | 2/15/99 | 8/20/99 CR | 2002 | EAS | M.P. 260.2. UPGRADE PHASE IV UNIT TO 13,000 HP AND ADD 15,700 HP UNIT.
| F98059 | C.005063.34 | HAYES | STATION 13A - PHASE V | INSTALL 24,000 HP OF COMPRESSION |  | 8/20/99 CR | 2002 | EAS | M.P. 324.5. INSTALL 2-12,000 HP ELECTRIC/CENTRIFUGAL COMPRESSORS.
| F98074 | C.005062.17 | BOATMAN | GULF POWER - SMITH LAT. | BUILD 18" LATERAL | 9/15/98 | 6/18/99 CR | 10/01/01 | EAS | M.P. 340.2. 27.9 MILES OF 18" LATERAL. WORK NECESSARY FOR FERC FILING.
| F99075 | C.005064.51 | BOATMAN | GP - SMITH METER STATION | EFM, INSPECTION FOR NEW MTR STA | 9/15/98 | 2/02/00 B | 10/01/01 | EAS | M.P. 27.9 ON SMITH LATERAL. DEL. 5 MMMBTU/HR AT 550 PSIG.
| F95085 | R00928 | NESTOR | PT. ST. JOE FACIL. SALE | ABANDON LATERALS & MTR STATION | 10/27/95 | 3/29/00 C |  | EAS | M.P. 35.2. DISCONNECT 1.3 MILES OF 2-1/2" AND 6". ABANDON METER STATION.
| F01020 |  | DOWDEN | CALPINE NORTH FLA | BUILD NEW DELIVERY POINT | 2/28/01 | 3/1/01 | 2001 | EAS | M.P. ??? BUILD METER STATION TO DELIVER 80,000 MMBTU/D @ 500 PSIG
** | F98082 | C.005068.33 | BOATMAN | STATION 14A - PHASE IV | INSTALL 10,350 COMPRESSOR | 11/02/98 | 5/08/00 C | 2001 | EAS | M.P. 394.7. PLACED IN SERVICE 5/01/01. FINAL REPORT.
| F98060 | C.005063.35 | BOATMAN | STATION 14A - PHASE V | INCREASE TO 28,700 HP | 8/12/99 | 8/20/99 CR | 2002 | EAS | M.P. 394.7. UPGRADE PHASE IV TO UNIT 13,000 HP AND ADD 15,700 HP UNIT.
| F96034 | C96312 | NESTOR | TALLAHASSEE - WAKULLA | BUILD TAP AND METER STATION | 6/24/96 | 9/18/96 C | 1998 | EAS | M.P. 5.6 ON TALLAHASSEE PURDOM LAT. DEL. UP TO 60 MMBTU/HR @ 60 PSIG.
| F99013 | C.005063.36 | BOATMAN | STATION 15A - PHASE V | INCREASE TO 20,200 HP | 2/15/99 | 3/03/99 B | 2001 | EAS | M.P. 468.7. UPGRADE EXISTING UNIT TO 13,000 HP AND ADD 7,200 HP UNIT.
** | F01039 |  | NESTOR | MADISON | RELOCATE DELIVERY POINT | 5/09/01 | NO RELEASE | 2001 | EAS | M.P. 11.7 ON MADISON LAT. ABANDON 11.4 MI. 3" & MTR. STA. BUILD NEW LINE PRS. STA.
| F00033 |  | CULLEN | BP TECHNOLOGY | BUILD TAP, CONN. PIPE, METER STA. | 3/31/00 | NO RELEASE |  | RLM | M.P. 502.8 ON MAINLINE OR 28.7 ON WEST LEG. DELIVER 50 MMBTU/HR
| F99040 | C.005061.07 | BOATMAN | PHASE V - LOOP J | BUILD 7.6 MILES OF 36" LOOP | 5/11/00 | 6/27/00 CR | 2002 | EAS | M.P. 17.8 TO 25.4 ON WEST LEG. RELEASED FOR WORK FOR FERC FILING.
| F01017 |  | JOHN LONG | NORTH FLA HOLSTEINS | UPGRADE ROTARY METER | 2/12/01 | NO RELEASE | 2001 | RLM | M.P. 21.2 ON WEST LEG. DELIVER UP TO 12 MMBTU/D AT 100 PSIG.
| F99063 | C.005063.39 | BOATMAN | STATION 24 - PHASE V | UPGRADE UNIT TO 15,000 HP | 8/12/99 | 8/20/99 CR | 2002 | EAS | M.P. 25.4 ON WEST LEG. WORK REQUIRED FOR FERC FILING.
| F99041 | C.005062.26 | BOATMAN | PHASE V - LOOP K | BUILD 13.1 MILES OF 36" LOOP | 5/11/00 | 6/27/00 CR | 2002 | EAS | M.P. 25.4 TO 38.5 ON WEST LEG. RELEASED FOR WORK FOR FERC FILING.
** | F98013 | C.005068.34 | BOATMAN | STATION 26 - PHASE IV | ADD 7,170 HP COMPRESSOR | 2/02/98 | 5/08/00 C | 2001 | EAS | M.P. 90.6 ON WEST LEG. PLACED IN SERVICE 5/01/01. FINAL REPORT.
| F99064 | C.005063.40 | BOATMAN | STATION 26 - PHASE V | UPGRADE UNIT 2601 TO 7,300 HP | 8/12/99 | 8/20/99 CR | 2002 | EAS | M.P. 90.6 ON WEST LEG. PERMITS & WORK NEEDED FOR FERC FILING.
| F99070 | C.005062.22 | BOATMAN | PHASE V - LOOP G | BUILD 14.3 MILES 36" LOOP | 8/12/99 | 8/20/99 CR | 2002 | DDA | M.P. 90.6 TO 104.9 ON WEST LEG.
| F99036 | C000740.03 | FARRELL | EL PASO - SHADY HILL | 12" TAP, 0.7 MI. LAT. & METER STATION | 4/09/99 | 12/19/00 C | 5/31/01 | DDA | M.P. 125.4 ON WEST LEG. DELIVER UP TO 6,738 MMBTU/HR AT 500 PSIG.
C.005046.01
| F00048 | C000740.03 | FARRELL | PASCO COUNTY SLUDGE PLT | BUILD TAP, LATERAL AND METER STA | 5/05/00 | 12/19/00 C | 5/31/01 | DDA | M.P. 0.5 ON SHADY HILL LATERAL. DELIVER UP TO 0.1 MMMBTU/D.
| F95052 | C.005117.09 | BOATMAN | ST. PETE JUMPER | BUILD 9.0 MILES OF 16" PIPELINE | 8/08/95 | 9/29/00 B |  | DDA | M.P. 11.0 ON ANCLOTE LAT. CNCT W/REGS. TO M.P. 0.0 ON OLDSMAR LAT. & LOOP.
| F99081 | C.005117.07 | DOWDEN | OLDSMAR LOOP | ADD 2.2 MILES OF 12" LOOP | 10/05/99 | 9/29/00 B | 2001 | DDA | M.P. 2.2 TO 4.4 ON OLDSMAR LATERAL.
** | F98033 | C.004933.01 | NESTOR | CLEARWATER - TRINITY | BUILD TAP CONECTNG PIPE AND EFM | 3/20/98 | 5/21/99 C |  | DDA | M.P. 12.8 ON ANCLOTE LATERAL. INITIAL DELIVERY 4/04/01. FINAL REPORT.
| F00017 |  | SWANSON | PGS - OAK GROVE | BUILD TAP, EFM, CONNECTING PIPE | 2/15/00 | 2/29/00 B |  | DDA | M.P. 147.0. 4" TAP VALVE AND PIPE.
| F99033 |  | NESTOR | GAINESVILLE LATERALS | ABANDON 3.6 MI. 4", 3.8 MI. 6" & 3 STA. | 4/15/99 | 8/19/99 B |  | RLM | M.P. 20.4 ON INGLIS LAT. BLD LINE PRES. STA. FOR 2.5 MMMBTU/HR AT 450 PSIG.
| F93055 | C99968-9 | NESTOR | UPGRD INGLIS LAT MAOP | UPGRADE INGLIS, GVLE LAT. MAOP'S | 9/15/93 | 9/20/99 C |  | RLM | RETEST 40.0 MI. INGLIS 8", INST. REG. @ M.P. 22.7. UPRATE 1.8 MI. OF GVLLE 6".
|  | D99786 |  |  | W.O.'S C00915, C00916, D00917 |  | 2/22/00 C |  | RLM | REPLACE UNIV. REGS. WITH SPOOLS AND PLANT REGS. WITH HIGH DIFF. REGS.
| F99043 | C.005062.18 | SWANSON | JACKSONVILLE LAT. LOOP | BUILD 15.5 MILES 20" LOOP | 1/12/99 | 8/20/99 CR | 2002 | RLM | M.P. 0.0 TO 15.5 ON JACKSONVILLE LATERAL.
| F00060 | C005118.03 | BOATMAN | JACKSONVIL LAT. UPGRADE | HYDROTEST SEGMENT & UP MAOP | 6/28/00 | NO RELEASE |  | RLM | M.P. 21.2 TO 27.6 ON JACKSONVILLE LATERAL. RELOCATE LAWTEY REGULATOR.
| F00061 |  | BOATMAN | CYPRESS PIPELINE | BUILD 300 MMCFD INTERCONNECT |  | NO RELEASE |  | RLM | M.P. 27.6 ON JACKSONVILLE LATERAL. 16" TEE & SIDE VALVE.
| F99059 | C005063.37 | BOATMAN | STATION 16 - PHASE V | ADD 7,200 HP CENTRIFUGAL UNIT | 8/13/99 | 8/20/99 CR | 2002 | EAS | M.P. 548.0. ALSO LOOP DISCHARGE YARD PIPING AND ADD AFTERCOOLING.
| F00065 | C.000663.03 | BOATMAN | STATION 16 RECIPS - PH. V | ADD AFTERCOOLING FOR HIGH RATIO | 8/08/00 | 8/12/00 B | 2002 | EAS | M.P. 548.0. ALSO CHECK PUSLATION BOTTLES.
** | F98080 | C.005066.03 | BOATMAN | LOOP 16-17 FOR PHASE IV | BUILD 6.1 MILES 30" LOOP | 11/15/96 | 5/08/00 C | 2001 | EAS | M.P. 548.1 TO 554.2. OFFICIALLY PLACED IN SERVICE 5/01/01. FINAL REPORT.
| F00083 | C.005117.03 | BOATMAN | LOOP 16-17 FOR PHASE VI | BUILD 18 OR 27 MILES OF 30" LOOP | 9/28/00 | 9/29/00 B | 2003 | EAS | M.P. 554.2 TO 571.7 OR 580.7. NOTE: LOOP ROUTE IS 0.5 MILES LONGER.
| F01005 |  | CULLEN | NORTHEAST STARKE PROJ. | BUILD LATERAL AND METER STATION | 12/28/00 | NO RELEASE |  | RLM | M.P. 563.9. DELIVER 1,700 MMBTU/HR AT 300 PSIG. 8 MILES OF 8" LATERAL.
| F00006 |  | CULLEN | SEMPRA - BRADFORD | BUILD TAP, 3 MILES 10" LATERAL, EFM | 1/24/00 | NO RELEASE |  | RLM | M.P. 563.9. DELIVER 3,550 MMBTU/HR AT 500 PSIG.
| F00067 |  | DOWDEN | FPL - PUTNAM AUX. BOILER | CONNECT MTR TO CRES. CTY. REGS. | 7/06/00 | NO RELEASE | 2000 | RLM | CONNECT SMALL METER TO CRESCENT CITY REGULATORS. ADD EFM.
| F99013 | C.005063.38 | BOATMAN | STATION 17 - PHASE V | ADD 15,700 HP CENTRIFUGAL UNIT | 2/15/99 | 8/20/99 CR |  | EAS | M.P. 608.0. ADD AFTERCOOLING.
| F00066 | C.000664.03 | BOATMAN | STATION 17 RECIPS - PH. V | ADD AFTERCOOLING FOR HIGH RATIO | 8/08/00 | 8/12/00 B | 2002 | EAS | M.P. 608.0. ALSO CHECK PULSATION BOTTLES.
| F99067 | C.005061.06 | BOATMAN | PHASE V - LOOP F | BUILD 13.0 MILES OF 30" LOOP | 8/12/99 | 8/24/99 CR | 2002 | EAS | M.P. 608.0 TO 621.0.
| F00084 | C.005117.06 | BOATMAN | STATION 17-18 - PHASE VI | BUILD 11.9 MILES OF 30" LOOP | 9/28/00 | 9/29/00 B | 2003 | EAS | M.P. 621.0 TO 632.9.
| F98064 | C.005064.48 | HAYES | DEBARY CROSSOVER | BUILD REGULATOR STATION | 8/06/99 | 9/13/99 B | 2002 | DDA | M.P. 14.6 ON SANFORD LOOP, 16.0 ON SANFORD LAT. REGULATE TO 713 MAOP.
| F00094 |  | CULLEN | MICROCHIP - DE BARY | BUILD 4" TAP, LATERAL & EFM | 10/10/00 | NO RELEASE | 2002 | RLM | M.P. 3.3 ON DE BARY LAT. OR 2.5 ON DELAND LAT. DEL. UP TO 250 MMBTU/HR.
| F99087 | C.005062.19 | HAYES | SANFORD LOOP | BUILD 14.7 MILES 26" LOOP | 6/15/98 | 7/23/99 CR | 2002 | DDA | M.P. 646.8. ENDS AT M.P. 16.0 ON SANFORD LAT. (SHORTER ROUTE).
| F97052 | C.005062.20 | BOATMAN | DUKE - NEW SMYRNA BEACH | BUILD LATERAL AND METER STATION | 11/15/96 | 7/23/99 CR | 2002 | RLM | M.P. 14.7 ON SANFORD LOOP. 29.8 MI. 16". DEL. 3.5 MMMBTU/HR AT 500 PSIG.
C.005064.47
| F99017 | C.005062.21 | BOATMAN | FPL - SANFORD LAT. LOOP | BUILD NEW LOOP ON FPL LATERAL. | 2/28/99 | 7/23/99 CR | 2001 | DDA | M.P. 0.0 TO 0.4. 0.4 MI. 16"
| F99019 | C.005064.49 | BOATMAN | NEW FPL-SANFORD MTR STA | BUILD NEW METER STATION | 2/28/99 | 7/23/99 CR | 2001 | DDA | M.P. 0.6 ON SANFORD FPL LAT. DEL. 14.1/HR @ 470 PSIG, 1.6/HR @ 85 PSIG.
| F00072 | C.000687.03 | BOATMAN | EXSTNG FPL - SANFORD STA | RETIRE STA & INSTALL JUMPER | SEPT 99 | 8/24/00 B | 2001 | DDA | M.P. 1.0 ON SANFORD FPL LAT. REMOVE STATION, INSTALL 10" JUMPER.
| F99018 |  | BOATMAN | NEW SMYRNA JUMPER | BUILD 4.0 MILES 6" | 2/28/99 | 3/03/99 B | 2001 | RLM | M.P. 45.8 ON DUKE - NEW SMYRNA LATERAL TO M.P. 8.5 ON NEW SMYRNA LAT.
** | F01032 |  | NESTOR | LEESBURG LATERAL LOOP | BUILD 1.2 MILES OF 6" LOOP | 4/19/01 | 5/01/01 B | 2003 | RLM | M.P. 13.0 TO 14.2 ON LEESBURG LATERAL. ADDING 500 MMBTU/D IN PHASE VI.
| F01028 |  | NESTOR | PLYMOUTH - MINUTE MAID | ADD METER STATION FOR COCA COLA | 3/01/01 | NO RELEASE | 2001 | RLM | M.P. 5.4 ON PLYMOUTH LATERAL. ADD METER TO SPLIT DELIVERY.
| F00085 | C.005117.08 | BOATMAN | STATION 18 - PHASE VI | ADD 7,200 HP COMPRESSOR | 9/28/00 | 9/29/00 B | 2003 | EAS | M.P. 668.8.
| F99026 |  | CULLEN | RW BECK COGEN | BUILD TAP, LATERAL AND METER STA | 3/26/99 | NO RELEASE | 2000 | MDH | M.P. 685.7A. DELIVER UP TO 600 MMBTU/HR AT 250 PSIG FOR COGEN.
| F00043 | C.004169.01 | SWANSON | PGS - ORLANDO SOUTHEAST | BUILD TAP, CONNECTING PIPE & EFM | 5/15/00 | 10/05/00 C | 12/08/00 | MDH | M.P. 693.5A. DEL. 800 MMBTU/HR AT LINE PRESS. 6" TAP & CONNECTING PIPE.
| F97057 | C005117.10 | LONG | OUC - STANTON | BUILD LATERAL AND METER STATION | 5/02/97 | 8/24/00 B | 2001 | MDH | M.P. 693.5A. DELIVER UP TO 10 MMMBTU/HR AT 500 PSIG. 4.3 MI. OF 16" LAT.
| F99060 | C.005062.25 | BOATMAN | PALMETTO POWER | BUILD LATERAL AND METER STATION | 8/05/99 | 8/20/99 CR | 2002 | MDH | M.P. 705.9A. 6.8 MILES 16" LAT. DELIVER 5,833 MMBTU/HR AT 500 PSIG.
** | F99041 |  | BOATMAN | CAPE KENNEDY LOOP | BUILD 4.4 MILES OF 16" LOOP | 5/03/99 | 5/23/01 B | 4/01/03 | MDH | M.P. 0.9 TO 5.3 ON CAPE KENNEDY LATERAL.
| F00100 |  | LONG | SPACE CCCC - TITUSVILLE | BUILD TAP, CONNECTING PIPE & EFM | 11/03/00 | NO RELEASE | 2001 | MDH | M.P. 5.2 ON TITUSVILLE LATERAL. 2" TAP & 90 FT OF 2" PIPE.
| F99042 | J00247 | BOATMAN | RELIANT - HOLOPAW | BUILD TAP, CONNECTING PIPE & EFM | 5/03/99 | 2/01/01 C | 5/01/01 | MDH | M.P. 710.3. 50 FT. OF 12". DELIVER 7.0 MMMBTU/HR AT LINE PRESSURE.
| F99016 | C.005063.41 | BOATMAN | COMPRESSOR STATION 31 | BUILD NEW 2500 HP STATION | 2/15/99 | 8/20/99 CR | 2001 | EAS | M.P. 2.0 ON ST. PETERSBURG LATERAL.
| F97069 |  | NESTOR | LANG - HIGHWAY 535 | BUILD NEW METER STATION | 7/07/97 | 9/27/00 B | 2001 | DDA | M.P. 10.6 ON REEDY CREEK LATERAL. SERVE NEW SUBDIVISION.
| F00081 |  | NESTOR | REEDY CREEK VALVES | REMOVE ABOVE GROUND APPURT'S. |  | 9/19/00 B | 2000 | DDA | M.P. 10.0 ON REEDY CREEK LATERAL. VALVES 24-06B & 24-07B.
| F99028 |  | CULLEN | KISSIMMEE - CANE ISLAND | UPGRADE METER STATION | 3/26/99 | 4/05/99 B | 2001 | DDA | M.P. 12.4 ON ST. PETERSBURG LATERAL. INCREASE TO 11.0 MMMBTU/HR.
| F99078 | C00941 | DOWDEN | FPC - INTERCESSION CITY | INSTALL COMMUNICATING EFM | 9/27/99 | 6/19/00 C | 2000 | DDA | M.P. 4.5 ON CANE ISLAND LATERAL. INSTALL CUSTODY TRANSFER EFM.
| F99079 |  | DOWDEN | KUA - CANE ISLAND | UPGRADE METER STATION | 9/27/99 | 1/14/00 B | 2000 | DDA | M.P. 6.8 ON CANE ISL. LAT. UPGRADE EFM TO CUSTODY TRANSFER QUALITY.
| F99080 |  | DOWDEN | CANE ISLAND | REMOVE METERS & EFM FROM STA. | 9/27/99 | 10/15/99 B | 2000 | DDA | M.P. 0.1 ON CANE ISL. LAT. MOVE CUSTODY TRANSFER TO FPC & KUA STATIONS.
** | F01036 |  | BOATMAN | GULFSTREAM - OSCEOLA | BUILD INTERCONNECT | 4/11/01 | NO RELEASE | 2002 | MDH | M.P. 12.4 ON ST. PETE LAT.
| F00027 |  | BOATMAN | CALPINE - OSPREY | BUILD TAP, LATERAL, EFM | 3/10/00 | NO RELEASE | 2002 | DDA | M.P. 36.0 ON ST PETE LATERAL. 11.0 MI. 12". DEL. 4.15 MMMBTU/HR AT 550 PSIG.
| F01003 |  | SWANSON | TAMPA NORTH | INCREASE DELIVERY PRESSURE | 1/10/00 | 2/01/01 C | 2001 | DDA | M.P. 71.9 ON ST PETE LATERAL. RAISE DELIVERY PRESSURE TO 200 PSIG.
| F00005 | C.005062.27 | HAYES | TECO - BAYSIDE LATERAL | TAP AND 14.2 MILES OF 26" LATERAL | 1/05/00 | 1/31/00 B | 2003 | DDA | M.P. 157.8 ON 30" WEST LEG.
| F00078 | C.005064.50 | HAYES | TECO - BAYSIDE EFM | EFM FOR TECO'S METER STATION | 1/05/00 | 1/31/00 B | 2003 | DDA | M.P. 14.2 ON BAYSIDE LATERAL. DELIVER 16.7 MMMBTU/HR AT 650 PSIG.
| F00042 | C.005063.42 | BOATMAN | STATION 27 - PHASE V | BUILD NEW 14,400 HP STATION | 5/11/00 | NO RELEASE | 2002 | EAS | M.P. 160.0 ON 30" WEST LEG.
| F00101 |  | PARKER | CROSSOVER AT VLV 27-1 | BUILD 16" LINE TO 18" CONNECTOR | 9/06/00 | 6/09/00 C | 2001 | DDA | M.P. 165.0 ON WEST LEG. 16" CROSSOVER TO M.P. 3.3 ON SP/SAR CONNECTOR.
| F00058 | C.005064.52 | BOATMAN | THONOTOSASSA REG. | REMOTE CONTROL ON EXISTING REG. | 5/15/00 | 7/02/00 B | 5/01/03 | DDA | M.P. 0.1 ON ST. PETERSBURG/SARASOTA CONNECTOR.
| F98022 | C.005067.17 | SWANSON | NATIONAL GYPSUM BIG BEND | BUILD LATERAL AND METER STATION | 2/27/98 | 12/05/00 C | 2001 | DDA | M.P. 14.6 ON TAMPA SO. LAT. 6.0 MI. 6", 0.2 MI 8". DEL. 5,040 MMBTU/D AT 25 PSIG.
C.005070.83
| F00090 |  | LONG | TEXAS OHIO | BUILD LATERAL AND METER STATION | 9/01/00 | NO RELEASE | 2001 | DDA | M.P. 107.0 ON ST. PETERSBURG LATERAL. DELIVER 450 MMBTU/D AT 100 PSIG.
| F00076 |  | SWANSON | PGS - LAKE BLUE | UPGRADE METER | 9/18/00 | NO RELEASE | 2002 | DDA | M.P. 13.3 ON SARASOTA LATERAL. UPGRADE METER FOR 2.8 MMMBTU/HR LOAD.
| F01006 |  | SWANSON | SUN PAC - LAKE WALES | BUILD TAP, C.P., & METER STATION | 1/22/01 | NO RELEASE | 2001 | DDA | M.P. 1.9 ON LAKE WALES LATERAL. DELIVER 4,000 MMBTU/D AT 300 PSIG.
** | F94023 | C.005067.19 | SWANSON | LAKE WALES LOOP | INSTALL 0.9 MILES OF 6" LOOP | 4/18/94 | 7/31/00 CR | 2001 | DDA | M.P. 2.5 TO 3.4 ON LAKE WALES LAT. PUT IN SERVICE 5/01/01. FINAL REPORT.
| F01032 |  | SWANSON | IMC - WEST POLK | ABANDON 3.6 MILES OF 4" & MTR STA | 4/26/01 | NO RELEASE | 2001 | DDA | M.P. 38.0 ON SARSOTA LATERAL.
| F00007 |  | CULLEN | SEMPRA - PEBBLEDALE | BUILD TAP, 3 MILES OF 10" LAT,EFM | 1/24/00 | NO RELEASE | 2003 | DDA | M.P. 2.5 ON 20" AGRICOLA LATERAL. DELIVER 3,550 MMBTU/HR AT 500 PSIG.
| F00020 |  | BOATMAN | COGENTRIX - PEBBLEDALE | BUILD LATERAL AND METER STATION | 2/22/00 | NO RELEASE | 2002 | DDA | M.P. 2.5 ON AGRICOLA LATERAL. DELIVER 6160 MMBTU/HR AT 500 PSIG.
| F00087 |  | LONG | COMPETITIVE - PEBBLEDALE | BUILD LATERAL AND METER STATION | 8/03/00 | NO RELEASE | 2002 | DDA | M.P. 2.5 ON AGRICOLA LATERAL. DELIVER 2,700 MMBTU/HR AT 550 PSIG.
| F01014 |  | BOATMAN | MIRANT - FT. MEADE | BUILD LOOP AND METER STATION | 1/31/01 | NO RELEASE | 2003 | DDA | M.P. 8.2 ON FT. MEADE LAT. 80 MMMBTU/D. AGRICOLA REG. & 2.5 MI. 12" LOOP.
| F00088 |  | LONG | COMPETITIVE - PINEY POINT | BUILD LATERAL AND METER STATION | 8/03/00 | NO RELEASE | 2002 | DDA | M.P. 31.1 ON SP/SAR CONNECTOR. DELIVER 2,700 MMBTU/HR AT 550 PSIG.
** | F98072 | C.005067.18 | SWANSON | SARASOTA LOOP, PHASE IV | BUILD 4.4 MILES 12" LOOP | 8/10/98 | 10/16/98 CR | 2001 | DDA | M.P. 69.2 TO 73.6. OFFICIALLY PLACED IN SERVICE 5/01/01. FINAL REPORT.
| F98053 | C.005067.16 | PARKER | AGRICOLA REG/XOVER | INSTALL CROSSOVER & REGULATOR | 7/01/98 | 2/08/99 CR | 10/01/00 | DDA | M.P. 193.1 ON WEST LEG, M.P. 37.9 ON SARASOTA LAT, M.P. 0.0 ON AGRICOLA LAT
C.005069.46
| F99029 | C00911,25 | SWANSON | SEMINOLE - PAYNE CREEK | BUILD TAP, CONNECTING PIPE & EFM | 3/29/99 | 2/29/00 C | 6/01/01 | DDA | M.P. 204.1 ON WEST LEG. 12" TAP TO DELIVER 3.3 MMMBTU/HR AT 500 PSIG.
** | F01035 |  | BOATMAN | GULFSTREAM - HARDEE | BUILD 200+ MMCF/D INTERCONNECT | 4/11/01 | NO RELEASE | 6/01/02 | DDA | M.P. 206.2 ON WEST LEG.
| F00096 |  | CULLEN | LSP - HARDEE | BUILD TAP, CONNECTING PIPE & EFM | 10/18/00 | 11/29/00 B | 2002 | DDA | M.P. 211.O ON WEST LEG. 12" TAP TO DELIVER 7.3 MMMBTU/HR AT 500 PSIG.
| F00055 | J00316 | FARRELL | EL PASO - VANDOLAH | BUILD TAP, CONNECTING PIPE & EFM | 6/02/00 | 1/16/01 CR | 10/30/01 | DDA | M.P. 212.8 ON WEST LEG. 12" TAP & 800 FT OF 12" LAT. TO DEL. 9,279 MMBTU/HR.
| F00032 | C.000748.01 | SWANSON | CUC - ARCADIA | BUILD TAP, CONNECTING PIPE & EFM | 3/20/00 | 6/09/00 C | 2000 | DDA | M.P. 227.7 ON WEST LEG. 4" TAP & CONNECTING PIPE.
| F00095 |  | BOATMAN | ENTERGY - DE SOTO | BUILD TAP, CONNECTING PIPE & EFM | 10/23/00 | 1/31/01 B | 2002 | DDA | M.P. 239.1 ON WEST LEG. 16" CNCTNG PIPE. DEL. 6 EXPNDBL TO 10 MMMBTU/HR.
| F00028 |  | BOATMAN | CALPINE - LEE | BUILD TAP, LATERAL, EFM | 3/10/00 | NO RELEASE | 2002 | DDA | M.P. 34 ON FT. MYERS LATERAL. 11.2 MI. 20". DEL. 8.3 MMMBTU/HR AT 550 PSIG.
| F01029 |  | SWANSON | PGS - FT. MYERS | BUILD TAP, CONNECTING PIPE & EFM | 4/12/01 | 4/13/01 B | 12/01 | DDA | M.P. 34.2 ON FT. MYERS LATERAL. REINSTATED PROJECT OUTSIDE OF PHASE IV.
| F00008 |  | CULLEN | SEMPRA - ORANGE RIVER | BUILD TAP, CONNECTING PIPE, EFM | 1/24/00 | NO RELEASE | 2003 | DDA | M.P. 36.4 ON FT. MYERS LATERAL. DELIVER 3,550 MMBTU/HR AT 500 PSIG.
| F00022 |  | BOATMAN | COGENTRIX - LEE COUNTY | BUILD TAP, CONN. PIPE, METER STA. | 2/28/00 | NO RELEASE | 2003 | DDA | M.P. 37.2 ON FT. MYERS LATERAL. DELIVER 8,200 MMBTU/HR AT 500 PSIG.
| F98086 | C.000668.03 | CULLEN | OLEANDER POWER | BUILD 12" LATERAL AND METER STA | 9/02/98 | 3/02/01 C | 2001 | MDH | M.P. 719.5A. 0.3 MI. 12" LAT. & METER STATION. DELIVER UP TO 9 MMMBTU/HR.
| F95040 |  | LONG | NUI - VIERA | BUILD LATERAL AND METER STATION | 6/14/95 | 10/18/00 B |  | MDH | M.P. 728.6A. DELIVER AT LINE PRESSURE.
| F00053 | C.005054.01 | LONG | NUI - PALM BAY | BUILD TAP, CONNECTING PIPE & EFM | 6/14/00 | 3/08/01 C |  | MDH | M.P. 742.3. 4" TAP. DELIVER 210 MMBTU/HR. ALL BUT ON SITE CONSTRUCTION.
| F01004 |  | DOWDEN | VERO BEACH PEAKERS | BUILD LOOP AND/OR COMPRESSION | 1/18/01 | NO RELEASE |  | MDH | M.P. 768.5. DELIVER 500 TO 1500 MMBTU/HR MORE AT 550 PSIG.
| F00026 |  | BOATMAN | CALPINE - BLUE HERON | BUILD TAP, LATERAL, EFM | 3/10/00 | NO RELEASE | 2002 | MDH | M.P. 774.0. 0.3 MI. 10". DELIVER 8.3 MMMBTU/HR AT 550 PSIG.
** | F01037 |  | BOATMAN | GULFSTREAM - ST. LUCIE | BUILD INTERCONNECT. | 4/11/01 | NO RELEASE |  | MDH | M.P. 780.8.
** | F00023 | C.000718.03 | BOATMAN | ENA - FT. PIERCE | BUILD LAT LOOP AND METER STATION | 2/28/00 | 5/14/01 B |  | MDH | M.P. 781.7. DEL. 2,267 MMBTU/HR AT 560 PSIG. 7.5 MI. 12". TAPS EACH SIDE OF STA 20.
| F01007 |  | BOATMAN | ENA - MIDWAY | BUILD LATERAL AND METER STATION | 11/15/00 | 4/26/01 B |  | MDH | M.P. 785.4. DEL. 5472 MMBTU/HR AT LINE PRESSURE. 1.3 MILES OF 12" LATERAL.
| F01015 |  | BOATMAN | MIRANT - MIDWAY | BUILD LATERAL AND METER STATION | 1/31/01 | NO RELEASE |  | MDH | M.P. 786.6. DEL. 80 MMMBTU/D. 2.0 MILES OF 10" LATERAL.
| F00077 |  | DOWDEN | FPL - MIDWAY | BUILD LATERAL AND METER STATION | 6/22/00 | NO RELEASE |  | MDH | M.P. 786.6. 1.9 MILES 12". DELIVER 7.6 MMMBTU/HR AT 500 PSIG. $2.5 MIL.
| F00089 |  | LONG | COMPETITIVE - MIDWAY | BUILD LATERAL AND METER STATION | 8/03/00 | NO RELEASE |  | MDH | M.P. 787.6. 1.0 MILE OF 8". DELIVER 2,700 MMBTU/HR AT 550 PSIG.
| F00097 | C.014056 | HAYES | MARTIN NORTH BACK PRESS. | INST. BACK PRESSURE REGULATOR | 6/15/00 | 1/18/01 C | 3/31/01 | MDH | M.P. 801.7. REMOVE REGS. & CHECK VLV.,INST. BACK PRESS. REG. FOR 700 PSIG
| F01016 |  | BOATMAN | MIRANT - INDIANTOWN | BUILD LATERAL AND METER STATION | 1/31/01 | NO RELEASE |  | MDH | M.P. 807.3. DEL. 160 MMMBTU/D. 14.0 MILES OF 20" LATERAL.
| F01019 |  | LONG | WEST COUNTY PEAKERS | BUILD LATERAL, COMP, AND METER STA | 2/15/01 | NO RELEASE |  | MDH | M.P. 821.4. DEL 6,300 MMBtu/H. 11.0 MILES OF 16" LATERAL, COMP, & MTR STA
| F94004 |  | DOWDEN | FPU - HAVERHILL | BUILD NEW METER STATION | 1/28/94 | 5/09/94 B |  | MDH | M.P. 838.5. DELIVER 7,500 MMBTU/D AT 250 PSIG.
| F01008 |  | BOATMAN | ENA - CORBETT | BUILD LATERAL AND METER STATION | 11/15/00 | 1/29/01 B |  | MDH | M.P. 840.0. DEL. 5472 MMBTU/HR AT LINE PRESSURE. 13.0 MILES OF 16" OR 20".
** | F01033 | C.014083 | LONG | NUI - HAVERHILL | BUILD LINE PRESS. GATE STATION | 7/15/99 | 5/14/01 B |  | MDH | M.P. 840.4. TAPS ON 18" AND 24" MAINLINES, 100 FT OF 8" OR 12" PIPE & EFM.
** | F00047 |  | LONG | FPU - LAKE WORTH GEN. | BUILD NEW METER & REG. STATION | 3/15/00 | 4/13/01 C |  | MDH | M.P. 844.7. DELIVER 4.6 MMBTU/HR AT 525 PSIG.
| F00049 |  | LONG | FPU - BOYNTON BEACH | RELOCATE DELIVERY POINT TO M/L | 6/02/00 | NO RELEASE |  | MDH | M.P. 850.5. ABANDON 5.1 MI. 3" & MTR STA. BUILD LINE PRESS. STA. AT MAINLINE.
| F00059 |  | LONG | FPU - ATLANTIC AVENUE | BUILD NEW METER & REG. STATION | 6/15/00 | NO RELEASE |  | MDH | M.P. 855.5. DELIVER 7,500 MMBTU/D AT 250 PSIG.
| F01009 |  | BOATMAN | ENA - MANCINI | BUILD LATERAL AND METER STATION | 11/15/00 | 1/29/01 B |  | MDH | M.P. 866.5. DELIVER 5472 MMBTU/HR AT LINE PRESSURE. 0.3 MILES OF 16" LAT.
| F01010 |  | BOATMAN | ENA - THORNBOROUGH | BUILD LATERAL AND METER STATION | 11/15/00 | 1/29/01 B |  | MDH | M.P. 868.7. DELIVER 5472 MMBTU/HR AT LINE PRESSURE. 0.5 MILES OF 16" LAT.
| F98026 | C.000712.03 | LONG | SFNG - LAUDERHILL | BUILD TAP, LATERAL, AND METER STA | 2/27/98 | 8/31/00 B |  | MDH | M.P. 877.9 DELIVER UP TO 750 MMBTU/D. REQUESTED UPDATED COST EST.
| F01012 |  | BOATMAN | CALYPSO PIPELINE | BUILD TAP, CONNECTING PIPE, & EFM | 1/29/01 | NO RELEASE |  | DDA | M.P. 1.6 ON LAUDERDALE LAT. REC. UP TO 900 MMMBTU/D OF VAPORIZED LNG.
| F01030 |  | LONG | NUI - MONTENAY | BUILD TAP, 300 FT 6" PIPE AND EFM | 2/15/01 | 3/27/01 CR |  | MDH | M.P. 907.7. DELIVER 320 MMBTU/HR NOW, 720 MMBTU/HR LATER.
| F01031 |  | LONG | NUI - FLYING FOODS | BUILD TAP, 1025 FT 4" PIPE AND EFM | 2/15/01 | 3/27/01 CR |  | MDH | M.P. 910.6. DELIVER 16 MMBTU/HR NOW, 47 MMBTU/HR LATER.
| F00056 |  | BOATMAN | ENA - SWEETWATER | BUILD 3100 HP COMP. & METER STA. | 4/14/00 | NO RELEASE |  | MDH | COMP, M.P. 0.0, MTR STA, M.P. 6.8 RINKER LAT. DEL. 2781 MMBTU/HR @650 PSIG.
| F01011 |  | BOATMAN | ENA - CERTOSA | BUILD LATERAL AND METER STATION | 11/15/00 | 1/29/01 B |  | MDH | M.P. 13.6 ON TURKEY POINT LAT. DEL. 5472 MMBTU/HR AT LINE PRESS. 0.3 MI. 14".